## WBS
WBS Code | WBS Name
EC00515 | City Center Office Building Addition
EC00515.D&E | Design and Engineering
EC00515.Found | Foundation
EC00515.Structure | Structure
EC00515.Mechanicals | Mechanical/Electrical Systems
EC00515.Mechanicals.Lifts | Elevator
EC00515.Mechanicals.HVAC | HVAC
EC00515.Mechanicals.Systems | Plumbing and Electrical
EC00515.Ex-Finish | Exterior Finishes
EC00515.Ex-Finish.Brick | Brick
EC00515.Ex-Finish.Roof | Roof
EC00515.Ex-Finish.Win | Doors and Windows
EC00515.Int-Finish | Interior Finishes
EC00515.Int-Finish.Fixtures | Plumbing and Lighting Fixtures
EC00515.Int-Finish.Coverings | Floor and Carpeting
EC00515.Int-Finish.Carp | Carpentry
EC00515.Int-Finish.Paint | Paint
EC00530 | Nesbid Building Expansion
EC00530.D&E | Design and Engineering
EC00530.Found | Foundation
EC00530.Structure | Structure
EC00530.Mechanicals | Mechanical/Electrical Systems
EC00530.Mechanicals.Lifts | Elevator
EC00530.Mechanicals.HVAC | HVAC
EC00530.Mechanicals.Systems | Plumbing and Electrical
EC00530.Ex-Finish | Exterior Finishes
EC00530.Ex-Finish.Brick | Brick
EC00530.Ex-Finish.Roof | Roof
EC00530.Ex-Finish.Win | Doors and Windows
EC00530.Int-Finish | Interior Finishes
EC00530.Int-Finish.Fixtures | Plumbing and Lighting Fixtures
EC00530.Int-Finish.Coverings | Floor and Carpeting
EC00530.Int-Finish.Carp | Carpentry
EC00530.Int-Finish.Paint | Paint
EC00501 | Haitang Corporate Park
EC00501.D&E | Design and Engineering
EC00501.Found | Foundation
EC00501.Structure | Structure
EC00501.Mechanicals | Mechanical/Electrical Systems
EC00501.Mechanicals.Lifts | Elevator
EC00501.Mechanicals.HVAC | HVAC
EC00501.Mechanicals.Systems | Plumbing and Electrical
EC00501.Ex-Finish | Exterior Finishes
EC00501.Ex-Finish.Brick | Brick
EC00501.Ex-Finish.Roof | Roof
EC00501.Ex-Finish.Win | Doors and Windows
EC00501.Int-Finish | Interior Finishes
EC00501.Int-Finish.Fixtures | Plumbing and Lighting Fixtures
EC00501.Int-Finish.Coverings | Floor and Carpeting
EC00501.Int-Finish.Carp | Carpentry
EC00501.Int-Finish.Paint | Paint
EC00610 | Harbour Pointe Assisted Living Center
EC00610.1 | Building 1
EC00610.1.1 | Structure
EC00610.1.2 | Roof
EC00610.1.3 | Envelope
EC00610.1.4 | Interior Finishes
EC00610.1.5 | Pool & Courtyard
EC00610.2 | Building 2
EC00610.2.1 | Structure
EC00610.2.2 | Roof
EC00610.2.3 | Envelope
EC00610.2.4 | Interior Finishes
EC00610.2.5 | Courtyard
EC00610.5 | Garage 1
EC00610.6 | Garage 2
EC00610.7 | Roads, Utilities & Pavers
EC00610.8 | Landscape & Irrigation
EC00620 | Juniper Nursing Home
EC00620.1 | Building 1
EC00620.1.1 | Structure
EC00620.1.2 | Roof
EC00620.1.3 | Envelope
EC00620.1.4 | Interior Finishes
EC00620.1.5 | Pool & Courtyard
EC00620.2 | Building 2
EC00620.2.1 | Structure
EC00620.2.2 | Roof
EC00620.2.3 | Envelope
EC00620.2.4 | Interior Finishes
EC00620.2.5 | Courtyard
EC00620.5 | Garage 1
EC00620.6 | Garage 2
EC00620.7 | Roads, Utilities & Pavers
EC00620.8 | Landscape & Irrigation
EC00630 | Saratoga Senior Community
EC00630.1 | Building 1
EC00630.1.1 | Structure
EC00630.1.2 | Roof
EC00630.1.3 | Envelope
EC00630.1.4 | Interior Finishes
EC00630.1.5 | Pool & Courtyard
EC00630.2 | Building 2
EC00630.2.1 | Structure
EC00630.2.2 | Roof
EC00630.2.3 | Envelope
EC00630.2.4 | Interior Finishes
EC00630.2.5 | Courtyard
EC00630.5 | Garage 1
EC00630.6 | Garage 2
EC00630.7 | Roads, Utilities & Pavers
EC00630.8 | Landscape & Irrigation

## Activities
Activity ID | Activity Name | WBS | Schedule % Complete | Start | Finish | Spreadsheet Field | time axis 2010-09-01 to 2015-01-01
EC00515 City Center Office Building Addition |  |  | 16.67% | 01-Nov-10 A | 2013-07-03 | Actual Labor Cost | 2010-11-01: 34522.14; 2010-12-01: 34522.14; 2011-01-01: 25464.87; 2011-02-01: 15153.41; 2011-03-01: 50699.13; 2011-04-01: 51661.43
EC00515 City Center Office Building Addition |  |  | 16.67% | 01-Nov-10 A | 2013-07-03 | Budgeted Labor Cost |  |  | 20100 | 20160 | 17916 | 11648 | 53498.5 | 35643.58 | 40791.5 | 72350 | 69385 | 74141 | 63100.6 | 36960 | 39479 | 46200 | 45276.8 | 45528 | 97897.6 | 51305.6 | 37811.4 | 28726.2 | 10776.33 | 16322.17 | 37240 | 35709.83 | 9240 | 8800 | 21366.03 | 20573.03 | 12101.83 | 23024 | 9945.83 | 16888.85 | 1722.1
EC00515 City Center Office Building Addition |  |  | 16.67% | 01-Nov-10 A | 2013-07-03 | Actual Labor Units | 2010-11-01: 575; 2010-12-01: 575; 2011-01-01: 424; 2011-02-01: 247; 2011-03-01: 824; 2011-04-01: 902
EC00515 City Center Office Building Addition |  |  | 16.67% | 01-Nov-10 A | 2013-07-03 | Budgeted Labor Units |  |  | 335 | 336 | 299 | 189 | 867 | 607 | 650 | 1174 | 1328 | 1535 | 1152 | 672 | 718 | 840 | 837 | 840 | 2032 | 1000 | 796 | 609 | 196 | 263 | 456 | 453 | 168 | 160 | 348 | 283 | 180 | 291 | 176 | 286 | 34
EC00515.D&E Design and Engineering |  |  | 100% | 01-Nov-10 A | 06-Apr-11 A | Actual Labor Cost | 2010-11-01: 34522.14; 2010-12-01: 34522.14; 2011-01-01: 25464.87; 2011-02-01: 11498.43; 2011-03-01: 9755.17; 2011-04-01: 1357.24
EC00515.D&E Design and Engineering |  |  | 100% | 01-Nov-10 A | 06-Apr-11 A | Budgeted Labor Cost | 2010-11-01: 20100; 2010-12-01: 20160; 2011-01-01: 17916; 2011-02-01: 6528; 2011-03-01: 14496; 2011-04-01: 576
EC00515.D&E Design and Engineering |  |  | 100% | 01-Nov-10 A | 06-Apr-11 A | Actual Labor Units | 2010-11-01: 575; 2010-12-01: 575; 2011-01-01: 424; 2011-02-01: 192; 2011-03-01: 163; 2011-04-01: 23
EC00515.D&E Design and Engineering |  |  | 100% | 01-Nov-10 A | 06-Apr-11 A | Budgeted Labor Units | 2010-11-01: 335; 2010-12-01: 336; 2011-01-01: 299; 2011-02-01: 109; 2011-03-01: 242; 2011-04-01: 10
EC1000 | Design Building Addition | EC00515.D&E | 100% | 01-Nov-10 A | 19-Jan-11 A | Actual Labor Cost | 2010-11-01: 34522.14; 2010-12-01: 34522.14; 2011-01-01: 20055.72
EC1000 | Design Building Addition | EC00515.D&E | 100% | 01-Nov-10 A | 19-Jan-11 A | Budgeted Labor Cost | 2010-11-01: 20100; 2010-12-01: 20160; 2011-01-01: 12732
EC1000 | Design Building Addition | EC00515.D&E | 100% | 01-Nov-10 A | 19-Jan-11 A | Actual Labor Units | 2010-11-01: 575; 2010-12-01: 575; 2011-01-01: 334
EC1000 | Design Building Addition | EC00515.D&E | 100% | 01-Nov-10 A | 19-Jan-11 A | Budgeted Labor Units | 2010-11-01: 335; 2010-12-01: 336; 2011-01-01: 212
EC1010 | Start Office Building Addition Project | EC00515.D&E | 100% | 01-Nov-10 A |  | Actual Labor Cost
EC1010 | Start Office Building Addition Project | EC00515.D&E | 100% | 01-Nov-10 A |  | Budgeted Labor Cost
EC1010 | Start Office Building Addition Project | EC00515.D&E | 100% | 01-Nov-10 A |  | Actual Labor Units
EC1010 | Start Office Building Addition Project | EC00515.D&E | 100% | 01-Nov-10 A |  | Budgeted Labor Units
EC1030 | Review and Approve Designs | EC00515.D&E | 100% | 17-Jan-11 A | 17-Feb-11 A | Actual Labor Cost | 2011-01-01: 5409.15; 2011-02-01: 6410.85
EC1030 | Review and Approve Designs | EC00515.D&E | 100% | 17-Jan-11 A | 17-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 5184; 2011-02-01: 5184
EC1030 | Review and Approve Designs | EC00515.D&E | 100% | 17-Jan-11 A | 17-Feb-11 A | Actual Labor Units | 2011-01-01: 90; 2011-02-01: 107
EC1030 | Review and Approve Designs | EC00515.D&E | 100% | 17-Jan-11 A | 17-Feb-11 A | Budgeted Labor Units | 2011-01-01: 86; 2011-02-01: 86
EC1050 | Assemble Technical Data for Heat Pump | EC00515.D&E | 100% | 16-Feb-11 A | 25-Feb-11 A | Actual Labor Cost | 2011-02-01: 3900
EC1050 | Assemble Technical Data for Heat Pump | EC00515.D&E | 100% | 16-Feb-11 A | 25-Feb-11 A | Budgeted Labor Cost | 2011-03-01: 3456
EC1050 | Assemble Technical Data for Heat Pump | EC00515.D&E | 100% | 16-Feb-11 A | 25-Feb-11 A | Actual Labor Units | 2011-02-01: 65
EC1050 | Assemble Technical Data for Heat Pump | EC00515.D&E | 100% | 16-Feb-11 A | 25-Feb-11 A | Budgeted Labor Units | 2011-03-01: 58
EC1160 | Review Technical Data on Heat Pumps | EC00515.D&E | 100% | 24-Feb-11 A | 06-Apr-11 A | Actual Labor Cost | 2011-02-01: 1187.59; 2011-03-01: 9755.17; 2011-04-01: 1357.24
EC1160 | Review Technical Data on Heat Pumps | EC00515.D&E | 100% | 24-Feb-11 A | 06-Apr-11 A | Budgeted Labor Cost | 2011-02-01: 1344; 2011-03-01: 11040; 2011-04-01: 576
EC1160 | Review Technical Data on Heat Pumps | EC00515.D&E | 100% | 24-Feb-11 A | 06-Apr-11 A | Actual Labor Units | 2011-02-01: 20; 2011-03-01: 163; 2011-04-01: 23
EC1160 | Review Technical Data on Heat Pumps | EC00515.D&E | 100% | 24-Feb-11 A | 06-Apr-11 A | Budgeted Labor Units | 2011-02-01: 22; 2011-03-01: 184; 2011-04-01: 10
EC00515.Found Foundation |  |  | 22.02% | 23-Feb-11 A | 2011-09-19 | Actual Labor Cost | 2011-02-01: 2235.6; 2011-03-01: 12854.71; 2011-04-01: 6259.69
EC00515.Found Foundation |  |  | 22.02% | 23-Feb-11 A | 2011-09-19 | Budgeted Labor Cost | 2011-02-01: 2240; 2011-03-01: 12880; 2011-04-01: 9072; 2011-05-01: 23450; 2011-06-01: 52550; 2011-07-01: 51785; 2011-08-01: 53901; 2011-09-01: 36579.6
EC00515.Found Foundation |  |  | 22.02% | 23-Feb-11 A | 2011-09-19 | Actual Labor Units | 2011-02-01: 32; 2011-03-01: 184; 2011-04-01: 89
EC00515.Found Foundation |  |  | 22.02% | 23-Feb-11 A | 2011-09-19 | Budgeted Labor Units | 2011-02-01: 32; 2011-03-01: 184; 2011-04-01: 130; 2011-05-01: 335; 2011-06-01: 814; 2011-07-01: 1008; 2011-08-01: 1167; 2011-09-01: 670
EC1090 | Begin Building Construction | EC00515.Found | 100% | 28-Feb-11 A |  | Actual Labor Cost
EC1090 | Begin Building Construction | EC00515.Found | 100% | 28-Feb-11 A |  | Budgeted Labor Cost
EC1090 | Begin Building Construction | EC00515.Found | 100% | 28-Feb-11 A |  | Actual Labor Units
EC1090 | Begin Building Construction | EC00515.Found | 100% | 28-Feb-11 A |  | Budgeted Labor Units
EC1100 | Site Preparation | EC00515.Found | 100% | 23-Feb-11 A | 18-Apr-11 A | Actual Labor Cost | 2011-02-01: 2235.6; 2011-03-01: 12854.71; 2011-04-01: 6259.69
EC1100 | Site Preparation | EC00515.Found | 100% | 23-Feb-11 A | 18-Apr-11 A | Budgeted Labor Cost | 2011-02-01: 2240; 2011-03-01: 12880; 2011-04-01: 9072
EC1100 | Site Preparation | EC00515.Found | 100% | 23-Feb-11 A | 18-Apr-11 A | Actual Labor Units | 2011-02-01: 32; 2011-03-01: 184; 2011-04-01: 89
EC1100 | Site Preparation | EC00515.Found | 100% | 23-Feb-11 A | 18-Apr-11 A | Budgeted Labor Units | 2011-02-01: 32; 2011-03-01: 184; 2011-04-01: 130
EC1230 | Excavation | EC00515.Found | 41.67% | 2011-05-02 | 2011-06-06 | Actual Labor Cost
EC1230 | Excavation | EC00515.Found | 41.67% | 2011-05-02 | 2011-06-06 | Budgeted Labor Cost | 2011-05-01: 23450; 2011-06-01: 3430
EC1230 | Excavation | EC00515.Found | 41.67% | 2011-05-02 | 2011-06-06 | Actual Labor Units
EC1230 | Excavation | EC00515.Found | 41.67% | 2011-05-02 | 2011-06-06 | Budgeted Labor Units | 2011-05-01: 335; 2011-06-01: 49
EC1320 | Install Underground Water Lines | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Actual Labor Cost
EC1320 | Install Underground Water Lines | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Budgeted Labor Cost | 2011-06-01: 10560
EC1320 | Install Underground Water Lines | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Actual Labor Units
EC1320 | Install Underground Water Lines | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Budgeted Labor Units | 2011-06-01: 192
EC1330 | Install Underground Electric Conduit | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Actual Labor Cost
EC1330 | Install Underground Electric Conduit | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Budgeted Labor Cost | 2011-06-01: 18240
EC1330 | Install Underground Electric Conduit | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Actual Labor Units
EC1330 | Install Underground Electric Conduit | EC00515.Found | 0% | 2011-06-03 | 2011-06-21 | Budgeted Labor Units | 2011-06-01: 192
EC1340 | Form/Pour Concrete Footings | EC00515.Found | 0% | 2011-06-21 | 2011-07-26 | Actual Labor Cost
EC1340 | Form/Pour Concrete Footings | EC00515.Found | 0% | 2011-06-21 | 2011-07-26 | Budgeted Labor Cost | 2011-06-01: 20320; 2011-07-01: 41120
EC1340 | Form/Pour Concrete Footings | EC00515.Found | 0% | 2011-06-21 | 2011-07-26 | Actual Labor Units
EC1340 | Form/Pour Concrete Footings | EC00515.Found | 0% | 2011-06-21 | 2011-07-26 | Budgeted Labor Units | 2011-06-01: 381; 2011-07-01: 771
EC1350 | Concrete Foundation Walls | EC00515.Found | 0% | 2011-07-25 | 2011-08-26 | Actual Labor Cost
EC1350 | Concrete Foundation Walls | EC00515.Found | 0% | 2011-07-25 | 2011-08-26 | Budgeted Labor Cost | 2011-07-01: 10665; 2011-08-01: 41175
EC1350 | Concrete Foundation Walls | EC00515.Found | 0% | 2011-07-25 | 2011-08-26 | Actual Labor Units
EC1350 | Concrete Foundation Walls | EC00515.Found | 0% | 2011-07-25 | 2011-08-26 | Budgeted Labor Units | 2011-07-01: 237; 2011-08-01: 915
EC1360 | Form and Pour Slab | EC00515.Found | 0% | 2011-08-26 | 2011-09-14 | Actual Labor Cost
EC1360 | Form and Pour Slab | EC00515.Found | 0% | 2011-08-26 | 2011-09-14 | Budgeted Labor Cost | 2011-08-01: 12726; 2011-09-01: 26058
EC1360 | Form and Pour Slab | EC00515.Found | 0% | 2011-08-26 | 2011-09-14 | Actual Labor Units
EC1360 | Form and Pour Slab | EC00515.Found | 0% | 2011-08-26 | 2011-09-14 | Budgeted Labor Units | 2011-08-01: 252; 2011-09-01: 516
EC1370 | Backfill and Compact Walls | EC00515.Found | 0% | 2011-09-13 | 2011-09-19 | Actual Labor Cost
EC1370 | Backfill and Compact Walls | EC00515.Found | 0% | 2011-09-13 | 2011-09-19 | Budgeted Labor Cost | 2011-09-01: 10521.6
EC1370 | Backfill and Compact Walls | EC00515.Found | 0% | 2011-09-13 | 2011-09-19 | Actual Labor Units
EC1370 | Backfill and Compact Walls | EC00515.Found | 0% | 2011-09-13 | 2011-09-19 | Budgeted Labor Units | 2011-09-01: 154
EC1380 | Foundation Phase Complete | EC00515.Found | 0% |  | 2011-09-19 | Actual Labor Cost
EC1380 | Foundation Phase Complete | EC00515.Found | 0% |  | 2011-09-19 | Budgeted Labor Cost
EC1380 | Foundation Phase Complete | EC00515.Found | 0% |  | 2011-09-19 | Actual Labor Units
EC1380 | Foundation Phase Complete | EC00515.Found | 0% |  | 2011-09-19 | Budgeted Labor Units
EC00515.Structure Structure |  |  | 0% | 2011-09-19 | 2012-04-20 | Actual Labor Cost
EC00515.Structure Structure |  |  | 0% | 2011-09-19 | 2012-04-20 | Budgeted Labor Cost | 2011-09-01: 8041; 2011-10-01: 18480; 2011-11-01: 20999; 2011-12-01: 27720; 2012-01-01: 23148.8; 2012-02-01: 16968; 2012-03-01: 64777.6; 2012-04-01: 16857.6
EC00515.Structure Structure |  |  | 0% | 2011-09-19 | 2012-04-20 | Actual Labor Units
EC00515.Structure Structure |  |  | 0% | 2011-09-19 | 2012-04-20 | Budgeted Labor Units | 2011-09-01: 146; 2011-10-01: 336; 2011-11-01: 382; 2011-12-01: 504; 2012-01-01: 440; 2012-02-01: 336; 2012-03-01: 1389; 2012-04-01: 346
EC1390 | Erect Structural Frame | EC00515.Structure | 0% | 2011-09-19 | 2011-11-25 | Actual Labor Cost
EC1390 | Erect Structural Frame | EC00515.Structure | 0% | 2011-09-19 | 2011-11-25 | Budgeted Labor Cost | 2011-09-01: 8041; 2011-10-01: 18480; 2011-11-01: 15719
EC1390 | Erect Structural Frame | EC00515.Structure | 0% | 2011-09-19 | 2011-11-25 | Actual Labor Units
EC1390 | Erect Structural Frame | EC00515.Structure | 0% | 2011-09-19 | 2011-11-25 | Budgeted Labor Units | 2011-09-01: 146; 2011-10-01: 336; 2011-11-01: 286
EC1410 | Begin Structural Phase | EC00515.Structure | 0% | 2011-11-25 |  | Actual Labor Cost
EC1410 | Begin Structural Phase | EC00515.Structure | 0% | 2011-11-25 |  | Budgeted Labor Cost
EC1410 | Begin Structural Phase | EC00515.Structure | 0% | 2011-11-25 |  | Actual Labor Units
EC1410 | Begin Structural Phase | EC00515.Structure | 0% | 2011-11-25 |  | Budgeted Labor Units
EC1420 | Floor Decking | EC00515.Structure | 0% | 2011-11-25 | 2012-01-13 | Actual Labor Cost
EC1420 | Floor Decking | EC00515.Structure | 0% | 2011-11-25 | 2012-01-13 | Budgeted Labor Cost | 2011-11-01: 5280; 2011-12-01: 27720; 2012-01-01: 11352
EC1420 | Floor Decking | EC00515.Structure | 0% | 2011-11-25 | 2012-01-13 | Actual Labor Units
EC1420 | Floor Decking | EC00515.Structure | 0% | 2011-11-25 | 2012-01-13 | Budgeted Labor Units | 2011-11-01: 96; 2011-12-01: 504; 2012-01-01: 206
EC1430 | Concrete First Floor | EC00515.Structure | 0% | 2012-01-11 | 2012-03-01 | Actual Labor Cost
EC1430 | Concrete First Floor | EC00515.Structure | 0% | 2012-01-11 | 2012-03-01 | Budgeted Labor Cost | 2012-01-01: 11796.8; 2012-02-01: 16968; 2012-03-01: 323.2
EC1430 | Concrete First Floor | EC00515.Structure | 0% | 2012-01-11 | 2012-03-01 | Actual Labor Units
EC1430 | Concrete First Floor | EC00515.Structure | 0% | 2012-01-11 | 2012-03-01 | Budgeted Labor Units | 2012-01-01: 234; 2012-02-01: 336; 2012-03-01: 6
EC1460 | Erect Stairwell and Elevator Walls | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Actual Labor Cost
EC1460 | Erect Stairwell and Elevator Walls | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Budgeted Labor Cost | 2012-03-01: 6048; 2012-04-01: 672
EC1460 | Erect Stairwell and Elevator Walls | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Actual Labor Units
EC1460 | Erect Stairwell and Elevator Walls | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Budgeted Labor Units | 2012-03-01: 173; 2012-04-01: 19
EC1470 | Concrete Basement Slab | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Actual Labor Cost
EC1470 | Concrete Basement Slab | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Budgeted Labor Cost | 2012-03-01: 40953.6; 2012-04-01: 4550.4
EC1470 | Concrete Basement Slab | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Actual Labor Units
EC1470 | Concrete Basement Slab | EC00515.Structure | 0% | 2012-03-01 | 2012-04-04 | Budgeted Labor Units | 2012-03-01: 864; 2012-04-01: 96
EC1480 | Concrete Second Floor | EC00515.Structure | 0% | 2012-03-01 | 2012-04-20 | Actual Labor Cost
EC1480 | Concrete Second Floor | EC00515.Structure | 0% | 2012-03-01 | 2012-04-20 | Budgeted Labor Cost | 2012-03-01: 17452.8; 2012-04-01: 11635.2
EC1480 | Concrete Second Floor | EC00515.Structure | 0% | 2012-03-01 | 2012-04-20 | Actual Labor Units
EC1480 | Concrete Second Floor | EC00515.Structure | 0% | 2012-03-01 | 2012-04-20 | Budgeted Labor Units | 2012-03-01: 346; 2012-04-01: 230
EC1540 | Structure Complete | EC00515.Structure | 0% |  | 2012-04-20 | Actual Labor Cost
EC1540 | Structure Complete | EC00515.Structure | 0% |  | 2012-04-20 | Budgeted Labor Cost
EC1540 | Structure Complete | EC00515.Structure | 0% |  | 2012-04-20 | Actual Labor Units
EC1540 | Structure Complete | EC00515.Structure | 0% |  | 2012-04-20 | Budgeted Labor Units
EC00515.Mechanicals Mechanical/Electrical Systems |  |  | 2.63% | 14-Apr-11 A | 2013-06-26 | Actual Labor Cost | 2011-04-01: 8243.12
EC00515.Mechanicals Mechanical/Electrical Systems |  |  | 2.63% | 14-Apr-11 A | 2013-06-26 | Budgeted Labor Cost | 2011-04-01: 5467.92; 2011-05-01: 6600; 2011-06-01: 9680; 2011-07-01: 8800; 2011-08-01: 10120; 2011-09-01: 9240; 2011-10-01: 9240; 2011-11-01: 9240; 2011-12-01: 9240; 2012-01-01: 12888; 2012-02-01: 19320; 2012-03-01: 23440; 2012-04-01: 19960; 2012-05-01: 9680; 2012-06-01: 12619.2; 2012-07-01: 9240; 2012-08-01: 16322.17; 2012-09-01: 37240; 2012-10-01: 35709.83; 2012-11-01: 9240; 2012-12-01: 8800; 2013-01-01: 21366.03; 2013-02-01: 5324.45; 2013-06-01: 2304
EC00515.Mechanicals Mechanical/Electrical Systems |  |  | 2.63% | 14-Apr-11 A | 2013-06-26 | Actual Labor Units | 2011-04-01: 150
EC00515.Mechanicals Mechanical/Electrical Systems |  |  | 2.63% | 14-Apr-11 A | 2013-06-26 | Budgeted Labor Units | 2011-04-01: 99; 2011-05-01: 120; 2011-06-01: 176; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 229; 2012-02-01: 336; 2012-03-01: 467; 2012-04-01: 358; 2012-05-01: 176; 2012-06-01: 245; 2012-07-01: 168; 2012-08-01: 263; 2012-09-01: 456; 2012-10-01: 453; 2012-11-01: 168; 2012-12-01: 160; 2013-01-01: 348; 2013-02-01: 60; 2013-06-01: 38
EC1490 | Rough-In Phase Begins | EC00515.Mechanicals | 0% | 2012-03-12 |  | Actual Labor Cost
EC1490 | Rough-In Phase Begins | EC00515.Mechanicals | 0% | 2012-03-12 |  | Budgeted Labor Cost
EC1490 | Rough-In Phase Begins | EC00515.Mechanicals | 0% | 2012-03-12 |  | Actual Labor Units
EC1490 | Rough-In Phase Begins | EC00515.Mechanicals | 0% | 2012-03-12 |  | Budgeted Labor Units
EC1690 | Rough In Complete | EC00515.Mechanicals | 0% |  | 2013-02-05 | Actual Labor Cost
EC1690 | Rough In Complete | EC00515.Mechanicals | 0% |  | 2013-02-05 | Budgeted Labor Cost
EC1690 | Rough In Complete | EC00515.Mechanicals | 0% |  | 2013-02-05 | Actual Labor Units
EC1690 | Rough In Complete | EC00515.Mechanicals | 0% |  | 2013-02-05 | Budgeted Labor Units
EC00515.Mechanicals.Lifts Elevator |  |  | 0% | 2012-04-04 | 2013-02-12 | Actual Labor Cost
EC00515.Mechanicals.Lifts Elevator |  |  | 0% | 2012-04-04 | 2013-02-12 | Budgeted Labor Cost | 2012-04-01: 4032; 2013-02-01: 4032
EC00515.Mechanicals.Lifts Elevator |  |  | 0% | 2012-04-04 | 2013-02-12 | Actual Labor Units
EC00515.Mechanicals.Lifts Elevator |  |  | 0% | 2012-04-04 | 2013-02-12 | Budgeted Labor Units | 2012-04-01: 38; 2013-02-01: 38
EC1520 | Install Elevator Rails and Equipment | EC00515.Mechanicals.Lifts | 0% | 2012-04-04 | 2012-04-06 | Actual Labor Cost
EC1520 | Install Elevator Rails and Equipment | EC00515.Mechanicals.Lifts | 0% | 2012-04-04 | 2012-04-06 | Budgeted Labor Cost | 2012-04-01: 4032
EC1520 | Install Elevator Rails and Equipment | EC00515.Mechanicals.Lifts | 0% | 2012-04-04 | 2012-04-06 | Actual Labor Units
EC1520 | Install Elevator Rails and Equipment | EC00515.Mechanicals.Lifts | 0% | 2012-04-04 | 2012-04-06 | Budgeted Labor Units | 2012-04-01: 38
EC1710 | Install Elevator Cab and Finishes | EC00515.Mechanicals.Lifts | 0% | 2013-02-05 | 2013-02-12 | Actual Labor Cost
EC1710 | Install Elevator Cab and Finishes | EC00515.Mechanicals.Lifts | 0% | 2013-02-05 | 2013-02-12 | Budgeted Labor Cost | 2013-02-01: 4032
EC1710 | Install Elevator Cab and Finishes | EC00515.Mechanicals.Lifts | 0% | 2013-02-05 | 2013-02-12 | Actual Labor Units
EC1710 | Install Elevator Cab and Finishes | EC00515.Mechanicals.Lifts | 0% | 2013-02-05 | 2013-02-12 | Budgeted Labor Units | 2013-02-01: 38
EC00515.Mechanicals.HVAC HVAC |  |  | 3.85% | 14-Apr-11 A | 2013-06-26 | Actual Labor Cost | 2011-04-01: 8243.12
EC00515.Mechanicals.HVAC HVAC |  |  | 3.85% | 14-Apr-11 A | 2013-06-26 | Budgeted Labor Cost | 2011-04-01: 5467.92; 2011-05-01: 6600; 2011-06-01: 9680; 2011-07-01: 8800; 2011-08-01: 10120; 2011-09-01: 9240; 2011-10-01: 9240; 2011-11-01: 9240; 2011-12-01: 9240; 2012-01-01: 9240; 2012-02-01: 9240; 2012-03-01: 19888; 2012-04-01: 15928; 2012-05-01: 9680; 2012-06-01: 12619.2; 2012-07-01: 9240; 2012-08-01: 10120; 2012-09-01: 8360; 2012-10-01: 10120; 2012-11-01: 9240; 2012-12-01: 8800; 2013-01-01: 21366.03; 2013-02-01: 1292.45; 2013-06-01: 2304
EC00515.Mechanicals.HVAC HVAC |  |  | 3.85% | 14-Apr-11 A | 2013-06-26 | Actual Labor Units | 2011-04-01: 150
EC00515.Mechanicals.HVAC HVAC |  |  | 3.85% | 14-Apr-11 A | 2013-06-26 | Budgeted Labor Units | 2011-04-01: 99; 2011-05-01: 120; 2011-06-01: 176; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 408; 2012-04-01: 320; 2012-05-01: 176; 2012-06-01: 245; 2012-07-01: 168; 2012-08-01: 184; 2012-09-01: 152; 2012-10-01: 184; 2012-11-01: 168; 2012-12-01: 160; 2013-01-01: 348; 2013-02-01: 21; 2013-06-01: 38
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00515.Mechanicals.HVAC | 100% | 14-Apr-11 A | 2011-05-04 | Actual Labor Cost | 2011-04-01: 8243.12
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00515.Mechanicals.HVAC | 100% | 14-Apr-11 A | 2011-05-04 | Budgeted Labor Cost | 2011-04-01: 5467.92; 2011-05-01: 868.08
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00515.Mechanicals.HVAC | 100% | 14-Apr-11 A | 2011-05-04 | Actual Labor Units | 2011-04-01: 150
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00515.Mechanicals.HVAC | 100% | 14-Apr-11 A | 2011-05-04 | Budgeted Labor Units | 2011-04-01: 99; 2011-05-01: 16
EC1240 | Review Bids for Heat Pump | EC00515.Mechanicals.HVAC | 79.17% | 2011-05-04 | 2011-05-17 | Actual Labor Cost
EC1240 | Review Bids for Heat Pump | EC00515.Mechanicals.HVAC | 79.17% | 2011-05-04 | 2011-05-17 | Budgeted Labor Cost | 2011-05-01: 4224
EC1240 | Review Bids for Heat Pump | EC00515.Mechanicals.HVAC | 79.17% | 2011-05-04 | 2011-05-17 | Actual Labor Units
EC1240 | Review Bids for Heat Pump | EC00515.Mechanicals.HVAC | 79.17% | 2011-05-04 | 2011-05-17 | Budgeted Labor Units | 2011-05-01: 77
EC1270 | Award Contract for Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2011-05-17 | 2011-05-25 | Actual Labor Cost
EC1270 | Award Contract for Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2011-05-17 | 2011-05-25 | Budgeted Labor Cost
EC1270 | Award Contract for Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2011-05-17 | 2011-05-25 | Actual Labor Units
EC1270 | Award Contract for Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2011-05-17 | 2011-05-25 | Budgeted Labor Units
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00515.Mechanicals.HVAC | 0% | 2011-05-25 | 2013-01-23 | Actual Labor Cost
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00515.Mechanicals.HVAC | 0% | 2011-05-25 | 2013-01-23 | Budgeted Labor Cost | 2011-05-01: 1507.92; 2011-06-01: 9680; 2011-07-01: 8800; 2011-08-01: 10120; 2011-09-01: 9240; 2011-10-01: 9240; 2011-11-01: 9240; 2011-12-01: 9240; 2012-01-01: 9240; 2012-02-01: 9240; 2012-03-01: 9680; 2012-04-01: 9240; 2012-05-01: 9680; 2012-06-01: 9240; 2012-07-01: 9240; 2012-08-01: 10120; 2012-09-01: 8360; 2012-10-01: 10120; 2012-11-01: 9240; 2012-12-01: 8800; 2013-01-01: 6588.08
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00515.Mechanicals.HVAC | 0% | 2011-05-25 | 2013-01-23 | Actual Labor Units
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00515.Mechanicals.HVAC | 0% | 2011-05-25 | 2013-01-23 | Budgeted Labor Units | 2011-05-01: 27; 2011-06-01: 176; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 168; 2012-05-01: 176; 2012-06-01: 168; 2012-07-01: 168; 2012-08-01: 184; 2012-09-01: 152; 2012-10-01: 184; 2012-11-01: 168; 2012-12-01: 160; 2013-01-01: 120
EC1500 | Install HVAC Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-03-12 | 2012-04-13 | Actual Labor Cost
EC1500 | Install HVAC Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-03-12 | 2012-04-13 | Budgeted Labor Cost | 2012-03-01: 10208; 2012-04-01: 6688
EC1500 | Install HVAC Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-03-12 | 2012-04-13 | Actual Labor Units
EC1500 | Install HVAC Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-03-12 | 2012-04-13 | Budgeted Labor Units | 2012-03-01: 232; 2012-04-01: 152
EC1630 | Insulate Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-06-18 | 2012-06-25 | Actual Labor Cost
EC1630 | Insulate Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-06-18 | 2012-06-25 | Budgeted Labor Cost | 2012-06-01: 3379.2
EC1630 | Insulate Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-06-18 | 2012-06-25 | Actual Labor Units
EC1630 | Insulate Ducts | EC00515.Mechanicals.HVAC | 0% | 2012-06-18 | 2012-06-25 | Budgeted Labor Units | 2012-06-01: 77
EC1650 | Set Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2013-01-04 | 2013-01-22 | Actual Labor Cost
EC1650 | Set Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2013-01-04 | 2013-01-22 | Budgeted Labor Cost | 2013-01-01: 5760
EC1650 | Set Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2013-01-04 | 2013-01-22 | Actual Labor Units
EC1650 | Set Heat Pump | EC00515.Mechanicals.HVAC | 0% | 2013-01-04 | 2013-01-22 | Budgeted Labor Units | 2013-01-01: 96
EC1670 | Relocate HVAC Chiller | EC00515.Mechanicals.HVAC | 0% | 2013-01-22 | 2013-02-01 | Actual Labor Cost
EC1670 | Relocate HVAC Chiller | EC00515.Mechanicals.HVAC | 0% | 2013-01-22 | 2013-02-01 | Budgeted Labor Cost | 2013-01-01: 9017.95; 2013-02-01: 140.45
EC1670 | Relocate HVAC Chiller | EC00515.Mechanicals.HVAC | 0% | 2013-01-22 | 2013-02-01 | Actual Labor Units
EC1670 | Relocate HVAC Chiller | EC00515.Mechanicals.HVAC | 0% | 2013-01-22 | 2013-02-01 | Budgeted Labor Units | 2013-01-01: 132; 2013-02-01: 2
EC1680 | Startup and Test HVAC | EC00515.Mechanicals.HVAC | 0% | 2013-02-01 | 2013-02-05 | Actual Labor Cost
EC1680 | Startup and Test HVAC | EC00515.Mechanicals.HVAC | 0% | 2013-02-01 | 2013-02-05 | Budgeted Labor Cost | 2013-02-01: 1152
EC1680 | Startup and Test HVAC | EC00515.Mechanicals.HVAC | 0% | 2013-02-01 | 2013-02-05 | Actual Labor Units
EC1680 | Startup and Test HVAC | EC00515.Mechanicals.HVAC | 0% | 2013-02-01 | 2013-02-05 | Budgeted Labor Units | 2013-02-01: 19
EC1770 | Install AC Grills and Registers | EC00515.Mechanicals.HVAC | 0% | 2013-04-08 | 2013-04-15 | Actual Labor Cost
EC1770 | Install AC Grills and Registers | EC00515.Mechanicals.HVAC | 0% | 2013-04-08 | 2013-04-15 | Budgeted Labor Cost
EC1770 | Install AC Grills and Registers | EC00515.Mechanicals.HVAC | 0% | 2013-04-08 | 2013-04-15 | Actual Labor Units
EC1770 | Install AC Grills and Registers | EC00515.Mechanicals.HVAC | 0% | 2013-04-08 | 2013-04-15 | Budgeted Labor Units
EC1830 | Test and Balance HVAC Equipment | EC00515.Mechanicals.HVAC | 0% | 2013-06-21 | 2013-06-26 | Actual Labor Cost
EC1830 | Test and Balance HVAC Equipment | EC00515.Mechanicals.HVAC | 0% | 2013-06-21 | 2013-06-26 | Budgeted Labor Cost | 2013-06-01: 2304
EC1830 | Test and Balance HVAC Equipment | EC00515.Mechanicals.HVAC | 0% | 2013-06-21 | 2013-06-26 | Actual Labor Units
EC1830 | Test and Balance HVAC Equipment | EC00515.Mechanicals.HVAC | 0% | 2013-06-21 | 2013-06-26 | Budgeted Labor Units | 2013-06-01: 38
EC00515.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-01-20 | 2013-01-23 | Actual Labor Cost
EC00515.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-01-20 | 2013-01-23 | Budgeted Labor Cost | 2012-01-01: 3648; 2012-02-01: 10080; 2012-03-01: 3552; 2012-08-01: 6202.17; 2012-09-01: 28880; 2012-10-01: 25589.83
EC00515.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-01-20 | 2013-01-23 | Actual Labor Units
EC00515.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-01-20 | 2013-01-23 | Budgeted Labor Units | 2012-01-01: 61; 2012-02-01: 168; 2012-03-01: 59; 2012-08-01: 79; 2012-09-01: 304; 2012-10-01: 269
EC1440 | Set Mechanical and Electrical Equipment | EC00515.Mechanicals.Systems | 0% | 2012-01-20 | 2012-03-12 | Actual Labor Cost
EC1440 | Set Mechanical and Electrical Equipment | EC00515.Mechanicals.Systems | 0% | 2012-01-20 | 2012-03-12 | Budgeted Labor Cost | 2012-01-01: 3648; 2012-02-01: 10080; 2012-03-01: 3552
EC1440 | Set Mechanical and Electrical Equipment | EC00515.Mechanicals.Systems | 0% | 2012-01-20 | 2012-03-12 | Actual Labor Units
EC1440 | Set Mechanical and Electrical Equipment | EC00515.Mechanicals.Systems | 0% | 2012-01-20 | 2012-03-12 | Budgeted Labor Units | 2012-01-01: 61; 2012-02-01: 168; 2012-03-01: 59
EC1510 | Rough-In Plumbing/Piping | EC00515.Mechanicals.Systems | 0% | 2012-08-24 | 2012-08-29 | Actual Labor Cost
EC1510 | Rough-In Plumbing/Piping | EC00515.Mechanicals.Systems | 0% | 2012-08-24 | 2012-08-29 | Budgeted Labor Cost | 2012-08-01: 5952
EC1510 | Rough-In Plumbing/Piping | EC00515.Mechanicals.Systems | 0% | 2012-08-24 | 2012-08-29 | Actual Labor Units
EC1510 | Rough-In Plumbing/Piping | EC00515.Mechanicals.Systems | 0% | 2012-08-24 | 2012-08-29 | Budgeted Labor Units | 2012-08-01: 77
EC1640 | Install Wiring and Cable | EC00515.Mechanicals.Systems | 0% | 2012-08-31 | 2012-10-23 | Actual Labor Cost
EC1640 | Install Wiring and Cable | EC00515.Mechanicals.Systems | 0% | 2012-08-31 | 2012-10-23 | Budgeted Labor Cost | 2012-08-01: 250.17; 2012-09-01: 28880; 2012-10-01: 25589.83
EC1640 | Install Wiring and Cable | EC00515.Mechanicals.Systems | 0% | 2012-08-31 | 2012-10-23 | Actual Labor Units
EC1640 | Install Wiring and Cable | EC00515.Mechanicals.Systems | 0% | 2012-08-31 | 2012-10-23 | Budgeted Labor Units | 2012-08-01: 3; 2012-09-01: 304; 2012-10-01: 269
EC1660 | Connect Equipment | EC00515.Mechanicals.Systems | 0% | 2013-01-22 | 2013-01-23 | Actual Labor Cost
EC1660 | Connect Equipment | EC00515.Mechanicals.Systems | 0% | 2013-01-22 | 2013-01-23 | Budgeted Labor Cost
EC1660 | Connect Equipment | EC00515.Mechanicals.Systems | 0% | 2013-01-22 | 2013-01-23 | Actual Labor Units
EC1660 | Connect Equipment | EC00515.Mechanicals.Systems | 0% | 2013-01-22 | 2013-01-23 | Budgeted Labor Units
EC00515.Ex-Finish Exterior Finishes |  |  | 43.02% | 17-Feb-11 A | 2012-06-19 | Actual Labor Cost | 2011-02-01: 496.88; 2011-03-01: 17480.5; 2011-04-01: 20197.63
EC00515.Ex-Finish Exterior Finishes |  |  | 43.02% | 17-Feb-11 A | 2012-06-19 | Budgeted Labor Cost | 2011-02-01: 1440; 2011-03-01: 15082.5; 2011-04-01: 11160; 2011-05-01: 1501.5; 2012-04-01: 5248; 2012-05-01: 18451.4; 2012-06-01: 6867
EC00515.Ex-Finish Exterior Finishes |  |  | 43.02% | 17-Feb-11 A | 2012-06-19 | Actual Labor Units | 2011-02-01: 8; 2011-03-01: 301; 2011-04-01: 361
EC00515.Ex-Finish Exterior Finishes |  |  | 43.02% | 17-Feb-11 A | 2012-06-19 | Budgeted Labor Units | 2011-02-01: 24; 2011-03-01: 258; 2011-04-01: 200; 2011-05-01: 27; 2012-04-01: 128; 2012-05-01: 444; 2012-06-01: 196
EC1590 | Close-In Phase Begins | EC00515.Ex-Finish | 0% | 2012-05-15 |  | Actual Labor Cost
EC1590 | Close-In Phase Begins | EC00515.Ex-Finish | 0% | 2012-05-15 |  | Budgeted Labor Cost
EC1590 | Close-In Phase Begins | EC00515.Ex-Finish | 0% | 2012-05-15 |  | Actual Labor Units
EC1590 | Close-In Phase Begins | EC00515.Ex-Finish | 0% | 2012-05-15 |  | Budgeted Labor Units
EC1620 | Building Enclosed | EC00515.Ex-Finish | 0% |  | 2012-06-18 | Actual Labor Cost
EC1620 | Building Enclosed | EC00515.Ex-Finish | 0% |  | 2012-06-18 | Budgeted Labor Cost
EC1620 | Building Enclosed | EC00515.Ex-Finish | 0% |  | 2012-06-18 | Actual Labor Units
EC1620 | Building Enclosed | EC00515.Ex-Finish | 0% |  | 2012-06-18 | Budgeted Labor Units
EC00515.Ex-Finish.Brick Brick |  |  | 59.15% | 17-Feb-11 A | 2012-05-15 | Actual Labor Cost | 2011-02-01: 496.88; 2011-03-01: 17480.5; 2011-04-01: 20197.63
EC00515.Ex-Finish.Brick Brick |  |  | 59.15% | 17-Feb-11 A | 2012-05-15 | Budgeted Labor Cost | 2011-02-01: 1440; 2011-03-01: 15082.5; 2011-04-01: 11160; 2011-05-01: 1501.5; 2012-04-01: 3640; 2012-05-01: 5768
EC00515.Ex-Finish.Brick Brick |  |  | 59.15% | 17-Feb-11 A | 2012-05-15 | Actual Labor Units | 2011-02-01: 8; 2011-03-01: 301; 2011-04-01: 361
EC00515.Ex-Finish.Brick Brick |  |  | 59.15% | 17-Feb-11 A | 2012-05-15 | Budgeted Labor Units | 2011-02-01: 24; 2011-03-01: 258; 2011-04-01: 200; 2011-05-01: 27; 2012-04-01: 104; 2012-05-01: 165
EC1040 | Assemble Brick Samples | EC00515.Ex-Finish.Brick | 100% | 17-Feb-11 A |  | Actual Labor Cost
EC1040 | Assemble Brick Samples | EC00515.Ex-Finish.Brick | 100% | 17-Feb-11 A |  | Budgeted Labor Cost
EC1040 | Assemble Brick Samples | EC00515.Ex-Finish.Brick | 100% | 17-Feb-11 A |  | Actual Labor Units
EC1040 | Assemble Brick Samples | EC00515.Ex-Finish.Brick | 100% | 17-Feb-11 A |  | Budgeted Labor Units
EC1070 | Review and Approve Brick Samples | EC00515.Ex-Finish.Brick | 100% | 28-Feb-11 A | 13-Apr-11 A | Actual Labor Cost | 2011-02-01: 496.88; 2011-03-01: 11428.13; 2011-04-01: 3975
EC1070 | Review and Approve Brick Samples | EC00515.Ex-Finish.Brick | 100% | 28-Feb-11 A | 13-Apr-11 A | Budgeted Labor Cost | 2011-02-01: 1440; 2011-03-01: 11040; 2011-04-01: 1920
EC1070 | Review and Approve Brick Samples | EC00515.Ex-Finish.Brick | 100% | 28-Feb-11 A | 13-Apr-11 A | Actual Labor Units | 2011-02-01: 8; 2011-03-01: 190; 2011-04-01: 66
EC1070 | Review and Approve Brick Samples | EC00515.Ex-Finish.Brick | 100% | 28-Feb-11 A | 13-Apr-11 A | Budgeted Labor Units | 2011-02-01: 24; 2011-03-01: 184; 2011-04-01: 32
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00515.Ex-Finish.Brick | 100% | 18-Mar-11 A | 13-Apr-11 A | Actual Labor Cost | 2011-03-01: 6052.37; 2011-04-01: 5332.63
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00515.Ex-Finish.Brick | 100% | 18-Mar-11 A | 13-Apr-11 A | Budgeted Labor Cost | 2011-03-01: 4042.5; 2011-04-01: 2293.5
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00515.Ex-Finish.Brick | 100% | 18-Mar-11 A | 13-Apr-11 A | Actual Labor Units | 2011-03-01: 110; 2011-04-01: 97
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00515.Ex-Finish.Brick | 100% | 18-Mar-11 A | 13-Apr-11 A | Budgeted Labor Units | 2011-03-01: 74; 2011-04-01: 42
EC1220 | Review Bids for Brick | EC00515.Ex-Finish.Brick | 100% | 08-Apr-11 A | 28-Apr-11 A | Actual Labor Cost | 2011-04-01: 10560
EC1220 | Review Bids for Brick | EC00515.Ex-Finish.Brick | 100% | 08-Apr-11 A | 28-Apr-11 A | Budgeted Labor Cost | 2011-04-01: 6336
EC1220 | Review Bids for Brick | EC00515.Ex-Finish.Brick | 100% | 08-Apr-11 A | 28-Apr-11 A | Actual Labor Units | 2011-04-01: 192
EC1220 | Review Bids for Brick | EC00515.Ex-Finish.Brick | 100% | 08-Apr-11 A | 28-Apr-11 A | Budgeted Labor Units | 2011-04-01: 115
EC1260 | Award Contract for Brick | EC00515.Ex-Finish.Brick | 8.33% | 21-Apr-11 A | 2011-05-05 | Actual Labor Cost | 2011-04-01: 330
EC1260 | Award Contract for Brick | EC00515.Ex-Finish.Brick | 8.33% | 21-Apr-11 A | 2011-05-05 | Budgeted Labor Cost | 2011-04-01: 610.5; 2011-05-01: 1501.5
EC1260 | Award Contract for Brick | EC00515.Ex-Finish.Brick | 8.33% | 21-Apr-11 A | 2011-05-05 | Actual Labor Units | 2011-04-01: 6
EC1260 | Award Contract for Brick | EC00515.Ex-Finish.Brick | 8.33% | 21-Apr-11 A | 2011-05-05 | Budgeted Labor Units | 2011-04-01: 11; 2011-05-01: 27
EC1280 | Deliver Brick | EC00515.Ex-Finish.Brick | 0% | 2011-05-05 | 2011-05-06 | Actual Labor Cost
EC1280 | Deliver Brick | EC00515.Ex-Finish.Brick | 0% | 2011-05-05 | 2011-05-06 | Budgeted Labor Cost
EC1280 | Deliver Brick | EC00515.Ex-Finish.Brick | 0% | 2011-05-05 | 2011-05-06 | Actual Labor Units
EC1280 | Deliver Brick | EC00515.Ex-Finish.Brick | 0% | 2011-05-05 | 2011-05-06 | Budgeted Labor Units
EC1550 | Brick Exterior Walls | EC00515.Ex-Finish.Brick | 0% | 2012-04-20 | 2012-05-15 | Actual Labor Cost
EC1550 | Brick Exterior Walls | EC00515.Ex-Finish.Brick | 0% | 2012-04-20 | 2012-05-15 | Budgeted Labor Cost | 2012-04-01: 3640; 2012-05-01: 5768
EC1550 | Brick Exterior Walls | EC00515.Ex-Finish.Brick | 0% | 2012-04-20 | 2012-05-15 | Actual Labor Units
EC1550 | Brick Exterior Walls | EC00515.Ex-Finish.Brick | 0% | 2012-04-20 | 2012-05-15 | Budgeted Labor Units | 2012-04-01: 104; 2012-05-01: 165
EC00515.Ex-Finish.Roof Roof |  |  | 0% | 2012-05-15 | 2012-06-19 | Actual Labor Cost
EC00515.Ex-Finish.Roof Roof |  |  | 0% | 2012-05-15 | 2012-06-19 | Budgeted Labor Cost | 2012-05-01: 6573; 2012-06-01: 6867
EC00515.Ex-Finish.Roof Roof |  |  | 0% | 2012-05-15 | 2012-06-19 | Actual Labor Units
EC00515.Ex-Finish.Roof Roof |  |  | 0% | 2012-05-15 | 2012-06-19 | Budgeted Labor Units | 2012-05-01: 188; 2012-06-01: 196
EC1600 | Insulation and Built-up Roofing | EC00515.Ex-Finish.Roof | 0% | 2012-05-15 | 2012-06-19 | Actual Labor Cost
EC1600 | Insulation and Built-up Roofing | EC00515.Ex-Finish.Roof | 0% | 2012-05-15 | 2012-06-19 | Budgeted Labor Cost | 2012-05-01: 6573; 2012-06-01: 6867
EC1600 | Insulation and Built-up Roofing | EC00515.Ex-Finish.Roof | 0% | 2012-05-15 | 2012-06-19 | Actual Labor Units
EC1600 | Insulation and Built-up Roofing | EC00515.Ex-Finish.Roof | 0% | 2012-05-15 | 2012-06-19 | Budgeted Labor Units | 2012-05-01: 188; 2012-06-01: 196
EC00515.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-04-27 | 2012-05-08 | Actual Labor Cost
EC00515.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-04-27 | 2012-05-08 | Budgeted Labor Cost | 2012-04-01: 1608; 2012-05-01: 6110.4
EC00515.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-04-27 | 2012-05-08 | Actual Labor Units
EC00515.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-04-27 | 2012-05-08 | Budgeted Labor Units | 2012-04-01: 24; 2012-05-01: 91
EC1560 | Install Door and Window Frames | EC00515.Ex-Finish.Win | 0% | 2012-04-27 | 2012-05-01 | Actual Labor Cost
EC1560 | Install Door and Window Frames | EC00515.Ex-Finish.Win | 0% | 2012-04-27 | 2012-05-01 | Budgeted Labor Cost | 2012-04-01: 1608; 2012-05-01: 964.8
EC1560 | Install Door and Window Frames | EC00515.Ex-Finish.Win | 0% | 2012-04-27 | 2012-05-01 | Actual Labor Units
EC1560 | Install Door and Window Frames | EC00515.Ex-Finish.Win | 0% | 2012-04-27 | 2012-05-01 | Budgeted Labor Units | 2012-04-01: 24; 2012-05-01: 14
EC1580 | Install Exterior Doors and Windows | EC00515.Ex-Finish.Win | 0% | 2012-05-01 | 2012-05-08 | Actual Labor Cost
EC1580 | Install Exterior Doors and Windows | EC00515.Ex-Finish.Win | 0% | 2012-05-01 | 2012-05-08 | Budgeted Labor Cost | 2012-05-01: 5145.6
EC1580 | Install Exterior Doors and Windows | EC00515.Ex-Finish.Win | 0% | 2012-05-01 | 2012-05-08 | Actual Labor Units
EC1580 | Install Exterior Doors and Windows | EC00515.Ex-Finish.Win | 0% | 2012-05-01 | 2012-05-08 | Budgeted Labor Units | 2012-05-01: 77
EC00515.Int-Finish Interior Finishes |  |  | 10.68% | 25-Feb-11 A | 2013-07-03 | Actual Labor Cost | 2011-02-01: 922.5; 2011-03-01: 10608.75; 2011-04-01: 15603.75
EC00515.Int-Finish Interior Finishes |  |  | 10.68% | 25-Feb-11 A | 2013-07-03 | Budgeted Labor Cost | 2011-02-01: 1440; 2011-03-01: 11040; 2011-04-01: 9367.67; 2011-05-01: 9240; 2011-06-01: 10120; 2011-07-01: 8800; 2011-08-01: 10120; 2011-09-01: 9240; 2011-10-01: 9240; 2011-11-01: 9240; 2011-12-01: 9240; 2012-01-01: 9240; 2012-02-01: 9240; 2012-03-01: 9680; 2012-04-01: 9240; 2012-05-01: 9680; 2012-06-01: 9240; 2012-07-01: 1536.33; 2013-02-01: 15248.58; 2013-03-01: 12101.83; 2013-04-01: 23024; 2013-05-01: 9945.83; 2013-06-01: 14584.85; 2013-07-01: 1722.1
EC00515.Int-Finish Interior Finishes |  |  | 10.68% | 25-Feb-11 A | 2013-07-03 | Actual Labor Units | 2011-02-01: 15; 2011-03-01: 177; 2011-04-01: 279
EC00515.Int-Finish Interior Finishes |  |  | 10.68% | 25-Feb-11 A | 2013-07-03 | Budgeted Labor Units | 2011-02-01: 24; 2011-03-01: 184; 2011-04-01: 169; 2011-05-01: 168; 2011-06-01: 184; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 168; 2012-05-01: 176; 2012-06-01: 168; 2012-07-01: 28; 2013-02-01: 224; 2013-03-01: 180; 2013-04-01: 291; 2013-05-01: 176; 2013-06-01: 247; 2013-07-01: 34
EC1700 | Drywall in Offices | EC00515.Int-Finish | 0% | 2013-02-05 | 2013-03-27 | Actual Labor Cost
EC1700 | Drywall in Offices | EC00515.Int-Finish | 0% | 2013-02-05 | 2013-03-27 | Budgeted Labor Cost | 2013-02-01: 9374.42; 2013-03-01: 9921.58
EC1700 | Drywall in Offices | EC00515.Int-Finish | 0% | 2013-02-05 | 2013-03-27 | Actual Labor Units
EC1700 | Drywall in Offices | EC00515.Int-Finish | 0% | 2013-02-05 | 2013-03-27 | Budgeted Labor Units | 2013-02-01: 140; 2013-03-01: 148
EC1820 | Touch-up and Clean-up | EC00515.Int-Finish | 0% | 2013-06-19 | 2013-06-24 | Actual Labor Cost
EC1820 | Touch-up and Clean-up | EC00515.Int-Finish | 0% | 2013-06-19 | 2013-06-24 | Budgeted Labor Cost | 2013-06-01: 2406.4
EC1820 | Touch-up and Clean-up | EC00515.Int-Finish | 0% | 2013-06-19 | 2013-06-24 | Actual Labor Units
EC1820 | Touch-up and Clean-up | EC00515.Int-Finish | 0% | 2013-06-19 | 2013-06-24 | Budgeted Labor Units | 2013-06-01: 45
EC1840 | Finishes Complete | EC00515.Int-Finish | 0% |  | 2013-06-26 | Actual Labor Cost
EC1840 | Finishes Complete | EC00515.Int-Finish | 0% |  | 2013-06-26 | Budgeted Labor Cost
EC1840 | Finishes Complete | EC00515.Int-Finish | 0% |  | 2013-06-26 | Actual Labor Units
EC1840 | Finishes Complete | EC00515.Int-Finish | 0% |  | 2013-06-26 | Budgeted Labor Units
EC1850 | Punch List | EC00515.Int-Finish | 0% | 2013-06-26 | 2013-07-03 | Actual Labor Cost
EC1850 | Punch List | EC00515.Int-Finish | 0% | 2013-06-26 | 2013-07-03 | Budgeted Labor Cost | 2013-06-01: 3090.7; 2013-07-01: 1722.1
EC1850 | Punch List | EC00515.Int-Finish | 0% | 2013-06-26 | 2013-07-03 | Actual Labor Units
EC1850 | Punch List | EC00515.Int-Finish | 0% | 2013-06-26 | 2013-07-03 | Budgeted Labor Units | 2013-06-01: 56; 2013-07-01: 34
EC1860 | Building Addition Complete | EC00515.Int-Finish | 0% |  | 2013-07-03 | Actual Labor Cost
EC1860 | Building Addition Complete | EC00515.Int-Finish | 0% |  | 2013-07-03 | Budgeted Labor Cost
EC1860 | Building Addition Complete | EC00515.Int-Finish | 0% |  | 2013-07-03 | Actual Labor Units
EC1860 | Building Addition Complete | EC00515.Int-Finish | 0% |  | 2013-07-03 | Budgeted Labor Units
EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-04-08 | 2013-06-10 | Actual Labor Cost
EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-04-08 | 2013-06-10 | Budgeted Labor Cost | 2013-04-01: 11232; 2013-06-01: 2112
EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-04-08 | 2013-06-10 | Actual Labor Units
EC00515.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-04-08 | 2013-06-10 | Budgeted Labor Units | 2013-04-01: 115; 2013-06-01: 38
EC1760 | Install Lighting Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-04-08 | 2013-04-17 | Actual Labor Cost
EC1760 | Install Lighting Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-04-08 | 2013-04-17 | Budgeted Labor Cost | 2013-04-01: 11232
EC1760 | Install Lighting Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-04-08 | 2013-04-17 | Actual Labor Units
EC1760 | Install Lighting Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-04-08 | 2013-04-17 | Budgeted Labor Units | 2013-04-01: 115
EC1810 | Install Plumbing Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-06-03 | 2013-06-10 | Actual Labor Cost
EC1810 | Install Plumbing Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-06-03 | 2013-06-10 | Budgeted Labor Cost | 2013-06-01: 2112
EC1810 | Install Plumbing Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-06-03 | 2013-06-10 | Actual Labor Units
EC1810 | Install Plumbing Fixtures | EC00515.Int-Finish.Fixtures | 0% | 2013-06-03 | 2013-06-10 | Budgeted Labor Units | 2013-06-01: 38
EC00515.Int-Finish.Coverings Floor and Carpeting |  |  | 20.72% | 25-Feb-11 A | 2013-06-04 | Actual Labor Cost | 2011-02-01: 922.5; 2011-03-01: 10608.75; 2011-04-01: 15603.75
EC00515.Int-Finish.Coverings Floor and Carpeting |  |  | 20.72% | 25-Feb-11 A | 2013-06-04 | Budgeted Labor Cost | 2011-02-01: 1440; 2011-03-01: 11040; 2011-04-01: 9367.67; 2011-05-01: 9240; 2011-06-01: 10120; 2011-07-01: 8800; 2011-08-01: 10120; 2011-09-01: 9240; 2011-10-01: 9240; 2011-11-01: 9240; 2011-12-01: 9240; 2012-01-01: 9240; 2012-02-01: 9240; 2012-03-01: 9680; 2012-04-01: 9240; 2012-05-01: 9680; 2012-06-01: 9240; 2012-07-01: 1536.33; 2013-05-01: 3776.25; 2013-06-01: 543.75
EC00515.Int-Finish.Coverings Floor and Carpeting |  |  | 20.72% | 25-Feb-11 A | 2013-06-04 | Actual Labor Units | 2011-02-01: 15; 2011-03-01: 177; 2011-04-01: 279
EC00515.Int-Finish.Coverings Floor and Carpeting |  |  | 20.72% | 25-Feb-11 A | 2013-06-04 | Budgeted Labor Units | 2011-02-01: 24; 2011-03-01: 184; 2011-04-01: 169; 2011-05-01: 168; 2011-06-01: 184; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 168; 2012-05-01: 176; 2012-06-01: 168; 2012-07-01: 28; 2013-05-01: 84; 2013-06-01: 12
EC1060 | Assemble and Submit Flooring Samples | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A |  | Actual Labor Cost
EC1060 | Assemble and Submit Flooring Samples | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A |  | Budgeted Labor Cost
EC1060 | Assemble and Submit Flooring Samples | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A |  | Actual Labor Units
EC1060 | Assemble and Submit Flooring Samples | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A |  | Budgeted Labor Units
EC1080 | Review and Approve Flooring | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A | 11-Apr-11 A | Actual Labor Cost | 2011-02-01: 922.5; 2011-03-01: 10608.75; 2011-04-01: 3228.75
EC1080 | Review and Approve Flooring | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A | 11-Apr-11 A | Budgeted Labor Cost | 2011-02-01: 1440; 2011-03-01: 11040; 2011-04-01: 960
EC1080 | Review and Approve Flooring | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A | 11-Apr-11 A | Actual Labor Units | 2011-02-01: 15; 2011-03-01: 177; 2011-04-01: 54
EC1080 | Review and Approve Flooring | EC00515.Int-Finish.Coverings | 100% | 25-Feb-11 A | 11-Apr-11 A | Budgeted Labor Units | 2011-02-01: 24; 2011-03-01: 184; 2011-04-01: 16
EC1170 | Prepare and Solicit Bids for Flooring | EC00515.Int-Finish.Coverings | 100% | 04-Apr-11 A | 2011-05-06 | Actual Labor Cost | 2011-04-01: 12375
EC1170 | Prepare and Solicit Bids for Flooring | EC00515.Int-Finish.Coverings | 100% | 04-Apr-11 A | 2011-05-06 | Budgeted Labor Cost | 2011-04-01: 8407.67; 2011-05-01: 2152.33
EC1170 | Prepare and Solicit Bids for Flooring | EC00515.Int-Finish.Coverings | 100% | 04-Apr-11 A | 2011-05-06 | Actual Labor Units | 2011-04-01: 225
EC1170 | Prepare and Solicit Bids for Flooring | EC00515.Int-Finish.Coverings | 100% | 04-Apr-11 A | 2011-05-06 | Budgeted Labor Units | 2011-04-01: 153; 2011-05-01: 39
EC1250 | Review Bids for Flooring | EC00515.Int-Finish.Coverings | 36.11% | 2011-05-06 | 2011-05-27 | Actual Labor Cost
EC1250 | Review Bids for Flooring | EC00515.Int-Finish.Coverings | 36.11% | 2011-05-06 | 2011-05-27 | Budgeted Labor Cost | 2011-05-01: 6336
EC1250 | Review Bids for Flooring | EC00515.Int-Finish.Coverings | 36.11% | 2011-05-06 | 2011-05-27 | Actual Labor Units
EC1250 | Review Bids for Flooring | EC00515.Int-Finish.Coverings | 36.11% | 2011-05-06 | 2011-05-27 | Budgeted Labor Units | 2011-05-01: 115
EC1300 | Award Contract for Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-05-27 | 2011-06-06 | Actual Labor Cost
EC1300 | Award Contract for Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-05-27 | 2011-06-06 | Budgeted Labor Cost | 2011-05-01: 751.67; 2011-06-01: 1360.33
EC1300 | Award Contract for Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-05-27 | 2011-06-06 | Actual Labor Units
EC1300 | Award Contract for Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-05-27 | 2011-06-06 | Budgeted Labor Units | 2011-05-01: 14; 2011-06-01: 25
EC1310 | Fabricate and Deliver Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-06-03 | 2012-07-06 | Actual Labor Cost
EC1310 | Fabricate and Deliver Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-06-03 | 2012-07-06 | Budgeted Labor Cost | 2011-06-01: 8759.67; 2011-07-01: 8800; 2011-08-01: 10120; 2011-09-01: 9240; 2011-10-01: 9240; 2011-11-01: 9240; 2011-12-01: 9240; 2012-01-01: 9240; 2012-02-01: 9240; 2012-03-01: 9680; 2012-04-01: 9240; 2012-05-01: 9680; 2012-06-01: 9240; 2012-07-01: 1536.33
EC1310 | Fabricate and Deliver Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-06-03 | 2012-07-06 | Actual Labor Units
EC1310 | Fabricate and Deliver Flooring | EC00515.Int-Finish.Coverings | 0% | 2011-06-03 | 2012-07-06 | Budgeted Labor Units | 2011-06-01: 159; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 168; 2012-05-01: 176; 2012-06-01: 168; 2012-07-01: 28
EC1790 | Install Floor and Carpeting | EC00515.Int-Finish.Coverings | 0% | 2013-05-16 | 2013-06-04 | Actual Labor Cost
EC1790 | Install Floor and Carpeting | EC00515.Int-Finish.Coverings | 0% | 2013-05-16 | 2013-06-04 | Budgeted Labor Cost | 2013-05-01: 3776.25; 2013-06-01: 543.75
EC1790 | Install Floor and Carpeting | EC00515.Int-Finish.Coverings | 0% | 2013-05-16 | 2013-06-04 | Actual Labor Units
EC1790 | Install Floor and Carpeting | EC00515.Int-Finish.Coverings | 0% | 2013-05-16 | 2013-06-04 | Budgeted Labor Units | 2013-05-01: 84; 2013-06-01: 12
EC00515.Int-Finish.Carp Carpentry |  |  | 0% | 2013-03-27 | 2013-06-19 | Actual Labor Cost
EC00515.Int-Finish.Carp Carpentry |  |  | 0% | 2013-03-27 | 2013-06-19 | Budgeted Labor Cost | 2013-03-01: 1334.42; 2013-04-01: 11792; 2013-05-01: 6169.58; 2013-06-01: 6432
EC00515.Int-Finish.Carp Carpentry |  |  | 0% | 2013-03-27 | 2013-06-19 | Actual Labor Units
EC00515.Int-Finish.Carp Carpentry |  |  | 0% | 2013-03-27 | 2013-06-19 | Budgeted Labor Units | 2013-03-01: 20; 2013-04-01: 176; 2013-05-01: 92; 2013-06-01: 96
EC1740 | Install Ceiling Grid | EC00515.Int-Finish.Carp | 0% | 2013-03-27 | 2013-05-16 | Actual Labor Cost
EC1740 | Install Ceiling Grid | EC00515.Int-Finish.Carp | 0% | 2013-03-27 | 2013-05-16 | Budgeted Labor Cost | 2013-03-01: 1334.42; 2013-04-01: 11792; 2013-05-01: 6169.58
EC1740 | Install Ceiling Grid | EC00515.Int-Finish.Carp | 0% | 2013-03-27 | 2013-05-16 | Actual Labor Units
EC1740 | Install Ceiling Grid | EC00515.Int-Finish.Carp | 0% | 2013-03-27 | 2013-05-16 | Budgeted Labor Units | 2013-03-01: 20; 2013-04-01: 176; 2013-05-01: 92
EC1800 | Finish Carpentry and Millwork | EC00515.Int-Finish.Carp | 0% | 2013-06-03 | 2013-06-19 | Actual Labor Cost
EC1800 | Finish Carpentry and Millwork | EC00515.Int-Finish.Carp | 0% | 2013-06-03 | 2013-06-19 | Budgeted Labor Cost | 2013-06-01: 6432
EC1800 | Finish Carpentry and Millwork | EC00515.Int-Finish.Carp | 0% | 2013-06-03 | 2013-06-19 | Actual Labor Units
EC1800 | Finish Carpentry and Millwork | EC00515.Int-Finish.Carp | 0% | 2013-06-03 | 2013-06-19 | Budgeted Labor Units | 2013-06-01: 96
EC00515.Int-Finish.Paint Paint |  |  | 0% | 2013-02-14 | 2013-03-04 | Actual Labor Cost
EC00515.Int-Finish.Paint Paint |  |  | 0% | 2013-02-14 | 2013-03-04 | Budgeted Labor Cost | 2013-02-01: 5874.17; 2013-03-01: 845.83
EC00515.Int-Finish.Paint Paint |  |  | 0% | 2013-02-14 | 2013-03-04 | Actual Labor Units
EC00515.Int-Finish.Paint Paint |  |  | 0% | 2013-02-14 | 2013-03-04 | Budgeted Labor Units | 2013-02-01: 84; 2013-03-01: 12
EC1720 | Paint Building Interior | EC00515.Int-Finish.Paint | 0% | 2013-02-14 | 2013-03-04 | Actual Labor Cost
EC1720 | Paint Building Interior | EC00515.Int-Finish.Paint | 0% | 2013-02-14 | 2013-03-04 | Budgeted Labor Cost | 2013-02-01: 5874.17; 2013-03-01: 845.83
EC1720 | Paint Building Interior | EC00515.Int-Finish.Paint | 0% | 2013-02-14 | 2013-03-04 | Actual Labor Units
EC1720 | Paint Building Interior | EC00515.Int-Finish.Paint | 0% | 2013-02-14 | 2013-03-04 | Budgeted Labor Units | 2013-02-01: 84; 2013-03-01: 12
EC00530 Nesbid Building Expansion |  |  | 0% | 2011-07-01 | 2013-10-17 | Actual Labor Cost
EC00530 Nesbid Building Expansion |  |  | 0% | 2011-07-01 | 2013-10-17 | Budgeted Labor Cost | 2011-07-01: 9600; 2011-08-01: 10272; 2011-09-01: 12800; 2011-10-01: 36072; 2011-11-01: 23156; 2011-12-01: 33960; 2012-01-01: 33520; 2012-02-01: 34625.6; 2012-03-01: 19360; 2012-04-01: 16764; 2012-05-01: 20655.2; 2012-06-01: 34560; 2012-07-01: 76228.8; 2012-08-01: 27830.4; 2012-09-01: 15745.6; 2012-10-01: 22821.6; 2012-11-01: 5532; 2012-12-01: 4400; 2013-01-01: 4840; 2013-02-01: 4972; 2013-03-01: 14020.8; 2013-06-01: 1441.62; 2013-07-01: 16832; 2013-08-01: 20216; 2013-09-01: 10720; 2013-10-01: 9124.78
EC00530 Nesbid Building Expansion |  |  | 0% | 2011-07-01 | 2013-10-17 | Actual Labor Units
EC00530 Nesbid Building Expansion |  |  | 0% | 2011-07-01 | 2013-10-17 | Budgeted Labor Units | 2011-07-01: 160; 2011-08-01: 183; 2011-09-01: 322; 2011-10-01: 581; 2011-11-01: 375; 2011-12-01: 568; 2012-01-01: 672; 2012-02-01: 661; 2012-03-01: 352; 2012-04-01: 305; 2012-05-01: 380; 2012-06-01: 643; 2012-07-01: 1565; 2012-08-01: 547; 2012-09-01: 322; 2012-10-01: 282; 2012-11-01: 94; 2012-12-01: 80; 2013-01-01: 88; 2013-02-01: 89; 2013-03-01: 198; 2013-06-01: 22; 2013-07-01: 248; 2013-08-01: 262; 2013-09-01: 189; 2013-10-01: 158
EC00530.D&E Design and Engineering |  |  | 0% | 2011-07-01 | 2011-10-26 | Actual Labor Cost
EC00530.D&E Design and Engineering |  |  | 0% | 2011-07-01 | 2011-10-26 | Budgeted Labor Cost | 2011-07-01: 9600; 2011-08-01: 10272; 2011-09-01: 3072; 2011-10-01: 8160
EC00530.D&E Design and Engineering |  |  | 0% | 2011-07-01 | 2011-10-26 | Actual Labor Units
EC00530.D&E Design and Engineering |  |  | 0% | 2011-07-01 | 2011-10-26 | Budgeted Labor Units | 2011-07-01: 160; 2011-08-01: 183; 2011-09-01: 169; 2011-10-01: 136
EC1000 | Design Building Addition | EC00530.D&E | 0% | 2011-07-01 | 2011-08-30 | Actual Labor Cost
EC1000 | Design Building Addition | EC00530.D&E | 0% | 2011-07-01 | 2011-08-30 | Budgeted Labor Cost | 2011-07-01: 9600; 2011-08-01: 10272
EC1000 | Design Building Addition | EC00530.D&E | 0% | 2011-07-01 | 2011-08-30 | Actual Labor Units
EC1000 | Design Building Addition | EC00530.D&E | 0% | 2011-07-01 | 2011-08-30 | Budgeted Labor Units | 2011-07-01: 160; 2011-08-01: 171
EC1010 | Start Office Building Addition Project | EC00530.D&E | 0% | 2011-07-01 |  | Actual Labor Cost
EC1010 | Start Office Building Addition Project | EC00530.D&E | 0% | 2011-07-01 |  | Budgeted Labor Cost
EC1010 | Start Office Building Addition Project | EC00530.D&E | 0% | 2011-07-01 |  | Actual Labor Units
EC1010 | Start Office Building Addition Project | EC00530.D&E | 0% | 2011-07-01 |  | Budgeted Labor Units
EC1030 | Review and Approve Designs | EC00530.D&E | 0% | 2011-08-30 | 2011-09-22 | Actual Labor Cost
EC1030 | Review and Approve Designs | EC00530.D&E | 0% | 2011-08-30 | 2011-09-22 | Budgeted Labor Cost
EC1030 | Review and Approve Designs | EC00530.D&E | 0% | 2011-08-30 | 2011-09-22 | Actual Labor Units
EC1030 | Review and Approve Designs | EC00530.D&E | 0% | 2011-08-30 | 2011-09-22 | Budgeted Labor Units | 2011-08-01: 12; 2011-09-01: 118
EC1050 | Assemble Technical Data for Heat Pump | EC00530.D&E | 0% | 2011-09-22 | 2011-09-30 | Actual Labor Cost
EC1050 | Assemble Technical Data for Heat Pump | EC00530.D&E | 0% | 2011-09-22 | 2011-09-30 | Budgeted Labor Cost | 2011-09-01: 2592
EC1050 | Assemble Technical Data for Heat Pump | EC00530.D&E | 0% | 2011-09-22 | 2011-09-30 | Actual Labor Units
EC1050 | Assemble Technical Data for Heat Pump | EC00530.D&E | 0% | 2011-09-22 | 2011-09-30 | Budgeted Labor Units | 2011-09-01: 43
EC1160 | Review Technical Data on Heat Pumps | EC00530.D&E | 0% | 2011-09-30 | 2011-10-26 | Actual Labor Cost
EC1160 | Review Technical Data on Heat Pumps | EC00530.D&E | 0% | 2011-09-30 | 2011-10-26 | Budgeted Labor Cost | 2011-09-01: 480; 2011-10-01: 8160
EC1160 | Review Technical Data on Heat Pumps | EC00530.D&E | 0% | 2011-09-30 | 2011-10-26 | Actual Labor Units
EC1160 | Review Technical Data on Heat Pumps | EC00530.D&E | 0% | 2011-09-30 | 2011-10-26 | Budgeted Labor Units | 2011-09-01: 8; 2011-10-01: 136
EC00530.Found Foundation |  |  | 0% | 2011-09-22 | 2012-02-24 | Actual Labor Cost
EC00530.Found Foundation |  |  | 0% | 2011-09-22 | 2012-02-24 | Budgeted Labor Cost | 2011-09-01: 3584; 2011-10-01: 11760; 2011-11-01: 11760; 2011-12-01: 24720; 2012-01-01: 24280; 2012-02-01: 23889.6
EC00530.Found Foundation |  |  | 0% | 2011-09-22 | 2012-02-24 | Actual Labor Units
EC00530.Found Foundation |  |  | 0% | 2011-09-22 | 2012-02-24 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 400; 2012-01-01: 504; 2012-02-01: 466
EC1090 | Begin Building Construction | EC00530.Found | 0% | 2011-09-22 |  | Actual Labor Cost
EC1090 | Begin Building Construction | EC00530.Found | 0% | 2011-09-22 |  | Budgeted Labor Cost
EC1090 | Begin Building Construction | EC00530.Found | 0% | 2011-09-22 |  | Actual Labor Units
EC1090 | Begin Building Construction | EC00530.Found | 0% | 2011-09-22 |  | Budgeted Labor Units
EC1100 | Site Preparation | EC00530.Found | 0% | 2011-09-22 | 2011-11-08 | Actual Labor Cost
EC1100 | Site Preparation | EC00530.Found | 0% | 2011-09-22 | 2011-11-08 | Budgeted Labor Cost | 2011-09-01: 3584; 2011-10-01: 11760; 2011-11-01: 2800
EC1100 | Site Preparation | EC00530.Found | 0% | 2011-09-22 | 2011-11-08 | Actual Labor Units
EC1100 | Site Preparation | EC00530.Found | 0% | 2011-09-22 | 2011-11-08 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 168; 2011-11-01: 40
EC1230 | Excavation | EC00530.Found | 0% | 2011-11-08 | 2011-12-02 | Actual Labor Cost
EC1230 | Excavation | EC00530.Found | 0% | 2011-11-08 | 2011-12-02 | Budgeted Labor Cost | 2011-11-01: 8960; 2011-12-01: 1120
EC1230 | Excavation | EC00530.Found | 0% | 2011-11-08 | 2011-12-02 | Actual Labor Units
EC1230 | Excavation | EC00530.Found | 0% | 2011-11-08 | 2011-12-02 | Budgeted Labor Units | 2011-11-01: 128; 2011-12-01: 16
EC1320 | Install Underground Water Lines | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Actual Labor Cost
EC1320 | Install Underground Water Lines | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Budgeted Labor Cost | 2011-12-01: 3960
EC1320 | Install Underground Water Lines | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Actual Labor Units
EC1320 | Install Underground Water Lines | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Budgeted Labor Units | 2011-12-01: 72
EC1330 | Install Underground Electric Conduit | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Actual Labor Cost
EC1330 | Install Underground Electric Conduit | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Budgeted Labor Cost | 2011-12-01: 6840
EC1330 | Install Underground Electric Conduit | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Actual Labor Units
EC1330 | Install Underground Electric Conduit | EC00530.Found | 0% | 2011-12-05 | 2011-12-15 | Budgeted Labor Units | 2011-12-01: 72
EC1340 | Form/Pour Concrete Footings | EC00530.Found | 0% | 2011-12-16 | 2012-01-12 | Actual Labor Cost
EC1340 | Form/Pour Concrete Footings | EC00530.Found | 0% | 2011-12-16 | 2012-01-12 | Budgeted Labor Cost | 2011-12-01: 12800; 2012-01-01: 10240
EC1340 | Form/Pour Concrete Footings | EC00530.Found | 0% | 2011-12-16 | 2012-01-12 | Actual Labor Units
EC1340 | Form/Pour Concrete Footings | EC00530.Found | 0% | 2011-12-16 | 2012-01-12 | Budgeted Labor Units | 2011-12-01: 240; 2012-01-01: 192
EC1350 | Concrete Foundation Walls | EC00530.Found | 0% | 2012-01-13 | 2012-02-07 | Actual Labor Cost
EC1350 | Concrete Foundation Walls | EC00530.Found | 0% | 2012-01-13 | 2012-02-07 | Budgeted Labor Cost | 2012-01-01: 14040; 2012-02-01: 5400
EC1350 | Concrete Foundation Walls | EC00530.Found | 0% | 2012-01-13 | 2012-02-07 | Actual Labor Units
EC1350 | Concrete Foundation Walls | EC00530.Found | 0% | 2012-01-13 | 2012-02-07 | Budgeted Labor Units | 2012-01-01: 312; 2012-02-01: 120
EC1360 | Form and Pour Slab | EC00530.Found | 0% | 2012-02-08 | 2012-02-20 | Actual Labor Cost
EC1360 | Form and Pour Slab | EC00530.Found | 0% | 2012-02-08 | 2012-02-20 | Budgeted Labor Cost | 2012-02-01: 14544
EC1360 | Form and Pour Slab | EC00530.Found | 0% | 2012-02-08 | 2012-02-20 | Actual Labor Units
EC1360 | Form and Pour Slab | EC00530.Found | 0% | 2012-02-08 | 2012-02-20 | Budgeted Labor Units | 2012-02-01: 288
EC1370 | Backfill and Compact Walls | EC00530.Found | 0% | 2012-02-21 | 2012-02-24 | Actual Labor Cost
EC1370 | Backfill and Compact Walls | EC00530.Found | 0% | 2012-02-21 | 2012-02-24 | Budgeted Labor Cost | 2012-02-01: 3945.6
EC1370 | Backfill and Compact Walls | EC00530.Found | 0% | 2012-02-21 | 2012-02-24 | Actual Labor Units
EC1370 | Backfill and Compact Walls | EC00530.Found | 0% | 2012-02-21 | 2012-02-24 | Budgeted Labor Units | 2012-02-01: 58
EC1380 | Foundation Phase Complete | EC00530.Found | 0% |  | 2012-02-24 | Actual Labor Cost
EC1380 | Foundation Phase Complete | EC00530.Found | 0% |  | 2012-02-24 | Budgeted Labor Cost
EC1380 | Foundation Phase Complete | EC00530.Found | 0% |  | 2012-02-24 | Actual Labor Units
EC1380 | Foundation Phase Complete | EC00530.Found | 0% |  | 2012-02-24 | Budgeted Labor Units
EC00530.Structure Structure |  |  | 0% | 2012-02-24 | 2012-08-13 | Actual Labor Cost
EC00530.Structure Structure |  |  | 0% | 2012-02-24 | 2012-08-13 | Budgeted Labor Cost | 2012-02-01: 1496; 2012-03-01: 9680; 2012-04-01: 7524; 2012-05-01: 10975.2; 2012-06-01: 16968; 2012-07-01: 56136; 2012-08-01: 6948.8
EC00530.Structure Structure |  |  | 0% | 2012-02-24 | 2012-08-13 | Actual Labor Units
EC00530.Structure Structure |  |  | 0% | 2012-02-24 | 2012-08-13 | Budgeted Labor Units | 2012-02-01: 27; 2012-03-01: 176; 2012-04-01: 137; 2012-05-01: 204; 2012-06-01: 336; 2012-07-01: 1200; 2012-08-01: 138
EC1390 | Erect Structural Frame | EC00530.Structure | 0% | 2012-02-24 | 2012-04-16 | Actual Labor Cost
EC1390 | Erect Structural Frame | EC00530.Structure | 0% | 2012-02-24 | 2012-04-16 | Budgeted Labor Cost | 2012-02-01: 1496; 2012-03-01: 9680; 2012-04-01: 4664
EC1390 | Erect Structural Frame | EC00530.Structure | 0% | 2012-02-24 | 2012-04-16 | Actual Labor Units
EC1390 | Erect Structural Frame | EC00530.Structure | 0% | 2012-02-24 | 2012-04-16 | Budgeted Labor Units | 2012-02-01: 27; 2012-03-01: 176; 2012-04-01: 85
EC1410 | Begin Structural Phase | EC00530.Structure | 0% | 2012-04-16 |  | Actual Labor Cost
EC1410 | Begin Structural Phase | EC00530.Structure | 0% | 2012-04-16 |  | Budgeted Labor Cost
EC1410 | Begin Structural Phase | EC00530.Structure | 0% | 2012-04-16 |  | Actual Labor Units
EC1410 | Begin Structural Phase | EC00530.Structure | 0% | 2012-04-16 |  | Budgeted Labor Units
EC1420 | Floor Decking | EC00530.Structure | 0% | 2012-04-20 | 2012-05-25 | Actual Labor Cost
EC1420 | Floor Decking | EC00530.Structure | 0% | 2012-04-20 | 2012-05-25 | Budgeted Labor Cost | 2012-04-01: 2860; 2012-05-01: 8228
EC1420 | Floor Decking | EC00530.Structure | 0% | 2012-04-20 | 2012-05-25 | Actual Labor Units
EC1420 | Floor Decking | EC00530.Structure | 0% | 2012-04-20 | 2012-05-25 | Budgeted Labor Units | 2012-04-01: 52; 2012-05-01: 150
EC1430 | Concrete First Floor | EC00530.Structure | 0% | 2012-05-25 | 2012-07-05 | Actual Labor Cost
EC1430 | Concrete First Floor | EC00530.Structure | 0% | 2012-05-25 | 2012-07-05 | Budgeted Labor Cost | 2012-05-01: 2747.2; 2012-06-01: 16968; 2012-07-01: 2100.8
EC1430 | Concrete First Floor | EC00530.Structure | 0% | 2012-05-25 | 2012-07-05 | Actual Labor Units
EC1430 | Concrete First Floor | EC00530.Structure | 0% | 2012-05-25 | 2012-07-05 | Budgeted Labor Units | 2012-05-01: 54; 2012-06-01: 336; 2012-07-01: 42
EC1460 | Erect Stairwell and Elevator Walls | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Actual Labor Cost
EC1460 | Erect Stairwell and Elevator Walls | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Budgeted Labor Cost | 2012-07-01: 5040
EC1460 | Erect Stairwell and Elevator Walls | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Actual Labor Units
EC1460 | Erect Stairwell and Elevator Walls | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Budgeted Labor Units | 2012-07-01: 144
EC1470 | Concrete Basement Slab | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Actual Labor Cost
EC1470 | Concrete Basement Slab | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Budgeted Labor Cost | 2012-07-01: 34128
EC1470 | Concrete Basement Slab | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Actual Labor Units
EC1470 | Concrete Basement Slab | EC00530.Structure | 0% | 2012-07-05 | 2012-07-31 | Budgeted Labor Units | 2012-07-01: 720
EC1480 | Concrete Second Floor | EC00530.Structure | 0% | 2012-07-05 | 2012-08-13 | Actual Labor Cost
EC1480 | Concrete Second Floor | EC00530.Structure | 0% | 2012-07-05 | 2012-08-13 | Budgeted Labor Cost | 2012-07-01: 14867.2; 2012-08-01: 6948.8
EC1480 | Concrete Second Floor | EC00530.Structure | 0% | 2012-07-05 | 2012-08-13 | Actual Labor Units
EC1480 | Concrete Second Floor | EC00530.Structure | 0% | 2012-07-05 | 2012-08-13 | Budgeted Labor Units | 2012-07-01: 294; 2012-08-01: 138
EC1540 | Structure Complete | EC00530.Structure | 0% |  | 2012-08-13 | Actual Labor Cost
EC1540 | Structure Complete | EC00530.Structure | 0% |  | 2012-08-13 | Budgeted Labor Cost
EC1540 | Structure Complete | EC00530.Structure | 0% |  | 2012-08-13 | Actual Labor Units
EC1540 | Structure Complete | EC00530.Structure | 0% |  | 2012-08-13 | Budgeted Labor Units
EC00530.Mechanicals Mechanical/Electrical Systems |  |  | 0% | 2011-10-26 | 2013-10-14 | Actual Labor Cost
EC00530.Mechanicals Mechanical/Electrical Systems |  |  | 0% | 2011-10-26 | 2013-10-14 | Budgeted Labor Cost | 2011-10-01: 880; 2011-11-01: 3300; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 4620; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 12972; 2012-07-01: 15472.8; 2012-08-01: 8895.2; 2012-09-01: 7293.6; 2012-10-01: 22821.6; 2012-11-01: 5532; 2012-12-01: 4400; 2013-01-01: 4840; 2013-02-01: 4972; 2013-03-01: 14020.8; 2013-10-01: 864
EC00530.Mechanicals Mechanical/Electrical Systems |  |  | 0% | 2011-10-26 | 2013-10-14 | Actual Labor Units
EC00530.Mechanicals Mechanical/Electrical Systems |  |  | 0% | 2011-10-26 | 2013-10-14 | Budgeted Labor Units | 2011-10-01: 16; 2011-11-01: 60; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 84; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 223; 2012-07-01: 281; 2012-08-01: 159; 2012-09-01: 121; 2012-10-01: 282; 2012-11-01: 94; 2012-12-01: 80; 2013-01-01: 88; 2013-02-01: 89; 2013-03-01: 198; 2013-10-01: 14
EC1490 | Rough-In Phase Begins | EC00530.Mechanicals | 0% | 2012-08-29 |  | Actual Labor Cost
EC1490 | Rough-In Phase Begins | EC00530.Mechanicals | 0% | 2012-08-29 |  | Budgeted Labor Cost
EC1490 | Rough-In Phase Begins | EC00530.Mechanicals | 0% | 2012-08-29 |  | Actual Labor Units
EC1490 | Rough-In Phase Begins | EC00530.Mechanicals | 0% | 2012-08-29 |  | Budgeted Labor Units
EC1690 | Rough In Complete | EC00530.Mechanicals | 0% |  | 2013-03-21 | Actual Labor Cost
EC1690 | Rough In Complete | EC00530.Mechanicals | 0% |  | 2013-03-21 | Budgeted Labor Cost
EC1690 | Rough In Complete | EC00530.Mechanicals | 0% |  | 2013-03-21 | Actual Labor Units
EC1690 | Rough In Complete | EC00530.Mechanicals | 0% |  | 2013-03-21 | Budgeted Labor Units
EC00530.Mechanicals.Lifts Elevator |  |  | 0% | 2012-08-29 | 2013-03-26 | Actual Labor Cost
EC00530.Mechanicals.Lifts Elevator |  |  | 0% | 2012-08-29 | 2013-03-26 | Budgeted Labor Cost | 2012-08-01: 1512; 2013-03-01: 3024
EC00530.Mechanicals.Lifts Elevator |  |  | 0% | 2012-08-29 | 2013-03-26 | Actual Labor Units
EC00530.Mechanicals.Lifts Elevator |  |  | 0% | 2012-08-29 | 2013-03-26 | Budgeted Labor Units | 2012-08-01: 14; 2013-03-01: 29
EC1520 | Install Elevator Rails and Equipment | EC00530.Mechanicals.Lifts | 0% | 2012-08-29 | 2012-08-31 | Actual Labor Cost
EC1520 | Install Elevator Rails and Equipment | EC00530.Mechanicals.Lifts | 0% | 2012-08-29 | 2012-08-31 | Budgeted Labor Cost | 2012-08-01: 1512
EC1520 | Install Elevator Rails and Equipment | EC00530.Mechanicals.Lifts | 0% | 2012-08-29 | 2012-08-31 | Actual Labor Units
EC1520 | Install Elevator Rails and Equipment | EC00530.Mechanicals.Lifts | 0% | 2012-08-29 | 2012-08-31 | Budgeted Labor Units | 2012-08-01: 14
EC1710 | Install Elevator Cab and Finishes | EC00530.Mechanicals.Lifts | 0% | 2013-03-21 | 2013-03-26 | Actual Labor Cost
EC1710 | Install Elevator Cab and Finishes | EC00530.Mechanicals.Lifts | 0% | 2013-03-21 | 2013-03-26 | Budgeted Labor Cost | 2013-03-01: 3024
EC1710 | Install Elevator Cab and Finishes | EC00530.Mechanicals.Lifts | 0% | 2013-03-21 | 2013-03-26 | Actual Labor Units
EC1710 | Install Elevator Cab and Finishes | EC00530.Mechanicals.Lifts | 0% | 2013-03-21 | 2013-03-26 | Budgeted Labor Units | 2013-03-01: 29
EC00530.Mechanicals.HVAC HVAC |  |  | 0% | 2011-10-26 | 2013-10-14 | Actual Labor Cost
EC00530.Mechanicals.HVAC HVAC |  |  | 0% | 2011-10-26 | 2013-10-14 | Budgeted Labor Cost | 2011-10-01: 880; 2011-11-01: 3300; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 4620; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 8632.8; 2012-08-01: 7383.2; 2012-09-01: 5165.6; 2012-10-01: 5341.6; 2012-11-01: 4620; 2012-12-01: 4400; 2013-01-01: 4840; 2013-02-01: 4972; 2013-03-01: 10996.8; 2013-10-01: 864
EC00530.Mechanicals.HVAC HVAC |  |  | 0% | 2011-10-26 | 2013-10-14 | Actual Labor Units
EC00530.Mechanicals.HVAC HVAC |  |  | 0% | 2011-10-26 | 2013-10-14 | Budgeted Labor Units | 2011-10-01: 16; 2011-11-01: 60; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 84; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 175; 2012-08-01: 145; 2012-09-01: 98; 2012-10-01: 98; 2012-11-01: 84; 2012-12-01: 80; 2013-01-01: 88; 2013-02-01: 89; 2013-03-01: 170; 2013-10-01: 14
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-10-26 | 2011-11-09 | Actual Labor Cost
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-10-26 | 2011-11-09 | Budgeted Labor Cost | 2011-10-01: 880; 2011-11-01: 1496
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-10-26 | 2011-11-09 | Actual Labor Units
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-10-26 | 2011-11-09 | Budgeted Labor Units | 2011-10-01: 16; 2011-11-01: 27
EC1240 | Review Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-09 | 2011-11-18 | Actual Labor Cost
EC1240 | Review Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-09 | 2011-11-18 | Budgeted Labor Cost | 2011-11-01: 1584
EC1240 | Review Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-09 | 2011-11-18 | Actual Labor Units
EC1240 | Review Bids for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-09 | 2011-11-18 | Budgeted Labor Units | 2011-11-01: 29
EC1270 | Award Contract for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-21 | 2011-11-29 | Actual Labor Cost
EC1270 | Award Contract for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-21 | 2011-11-29 | Budgeted Labor Cost
EC1270 | Award Contract for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-21 | 2011-11-29 | Actual Labor Units
EC1270 | Award Contract for Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2011-11-21 | 2011-11-29 | Budgeted Labor Units
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00530.Mechanicals.HVAC | 0% | 2011-11-30 | 2013-02-26 | Actual Labor Cost
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00530.Mechanicals.HVAC | 0% | 2011-11-30 | 2013-02-26 | Budgeted Labor Cost | 2011-11-01: 220; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 4620; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 4620; 2012-08-01: 5060; 2012-09-01: 4180; 2012-10-01: 5060; 2012-11-01: 4620; 2012-12-01: 4400; 2013-01-01: 4840; 2013-02-01: 3916
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00530.Mechanicals.HVAC | 0% | 2011-11-30 | 2013-02-26 | Actual Labor Units
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00530.Mechanicals.HVAC | 0% | 2011-11-30 | 2013-02-26 | Budgeted Labor Units | 2011-11-01: 4; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 84; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 84; 2012-08-01: 92; 2012-09-01: 76; 2012-10-01: 92; 2012-11-01: 84; 2012-12-01: 80; 2013-01-01: 88; 2013-02-01: 71
EC1500 | Install HVAC Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-07-16 | 2012-08-09 | Actual Labor Cost
EC1500 | Install HVAC Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-07-16 | 2012-08-09 | Budgeted Labor Cost | 2012-07-01: 4012.8; 2012-08-01: 2323.2
EC1500 | Install HVAC Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-07-16 | 2012-08-09 | Actual Labor Units
EC1500 | Install HVAC Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-07-16 | 2012-08-09 | Budgeted Labor Units | 2012-07-01: 91; 2012-08-01: 53
EC1630 | Insulate Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-09-26 | 2012-10-01 | Actual Labor Cost
EC1630 | Insulate Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-09-26 | 2012-10-01 | Budgeted Labor Cost | 2012-09-01: 985.6; 2012-10-01: 281.6
EC1630 | Insulate Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-09-26 | 2012-10-01 | Actual Labor Units
EC1630 | Insulate Ducts | EC00530.Mechanicals.HVAC | 0% | 2012-09-26 | 2012-10-01 | Budgeted Labor Units | 2012-09-01: 22; 2012-10-01: 6
EC1650 | Set Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2013-02-26 | 2013-03-11 | Actual Labor Cost
EC1650 | Set Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2013-02-26 | 2013-03-11 | Budgeted Labor Cost | 2013-02-01: 1056; 2013-03-01: 3264
EC1650 | Set Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2013-02-26 | 2013-03-11 | Actual Labor Units
EC1650 | Set Heat Pump | EC00530.Mechanicals.HVAC | 0% | 2013-02-26 | 2013-03-11 | Budgeted Labor Units | 2013-02-01: 18; 2013-03-01: 54
EC1670 | Relocate HVAC Chiller | EC00530.Mechanicals.HVAC | 0% | 2013-03-11 | 2013-03-19 | Actual Labor Cost
EC1670 | Relocate HVAC Chiller | EC00530.Mechanicals.HVAC | 0% | 2013-03-11 | 2013-03-19 | Budgeted Labor Cost | 2013-03-01: 6868.8
EC1670 | Relocate HVAC Chiller | EC00530.Mechanicals.HVAC | 0% | 2013-03-11 | 2013-03-19 | Actual Labor Units
EC1670 | Relocate HVAC Chiller | EC00530.Mechanicals.HVAC | 0% | 2013-03-11 | 2013-03-19 | Budgeted Labor Units | 2013-03-01: 101
EC1680 | Startup and Test HVAC | EC00530.Mechanicals.HVAC | 0% | 2013-03-19 | 2013-03-21 | Actual Labor Cost
EC1680 | Startup and Test HVAC | EC00530.Mechanicals.HVAC | 0% | 2013-03-19 | 2013-03-21 | Budgeted Labor Cost | 2013-03-01: 864
EC1680 | Startup and Test HVAC | EC00530.Mechanicals.HVAC | 0% | 2013-03-19 | 2013-03-21 | Actual Labor Units
EC1680 | Startup and Test HVAC | EC00530.Mechanicals.HVAC | 0% | 2013-03-19 | 2013-03-21 | Budgeted Labor Units | 2013-03-01: 14
EC1770 | Install AC Grills and Registers | EC00530.Mechanicals.HVAC | 0% | 2013-08-15 | 2013-08-22 | Actual Labor Cost
EC1770 | Install AC Grills and Registers | EC00530.Mechanicals.HVAC | 0% | 2013-08-15 | 2013-08-22 | Budgeted Labor Cost
EC1770 | Install AC Grills and Registers | EC00530.Mechanicals.HVAC | 0% | 2013-08-15 | 2013-08-22 | Actual Labor Units
EC1770 | Install AC Grills and Registers | EC00530.Mechanicals.HVAC | 0% | 2013-08-15 | 2013-08-22 | Budgeted Labor Units
EC1830 | Test and Balance HVAC Equipment | EC00530.Mechanicals.HVAC | 0% | 2013-10-10 | 2013-10-14 | Actual Labor Cost
EC1830 | Test and Balance HVAC Equipment | EC00530.Mechanicals.HVAC | 0% | 2013-10-10 | 2013-10-14 | Budgeted Labor Cost | 2013-10-01: 864
EC1830 | Test and Balance HVAC Equipment | EC00530.Mechanicals.HVAC | 0% | 2013-10-10 | 2013-10-14 | Actual Labor Units
EC1830 | Test and Balance HVAC Equipment | EC00530.Mechanicals.HVAC | 0% | 2013-10-10 | 2013-10-14 | Budgeted Labor Units | 2013-10-01: 14
EC00530.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-06-06 | 2013-03-12 | Actual Labor Cost
EC00530.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-06-06 | 2013-03-12 | Budgeted Labor Cost | 2012-06-01: 8352; 2012-07-01: 6840; 2012-09-01: 2128; 2012-10-01: 17480; 2012-11-01: 912
EC00530.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-06-06 | 2013-03-12 | Actual Labor Units
EC00530.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2012-06-06 | 2013-03-12 | Budgeted Labor Units | 2012-06-01: 139; 2012-07-01: 106; 2012-09-01: 22; 2012-10-01: 184; 2012-11-01: 10
EC1440 | Set Mechanical and Electrical Equipment | EC00530.Mechanicals.Systems | 0% | 2012-06-06 | 2012-07-16 | Actual Labor Cost
EC1440 | Set Mechanical and Electrical Equipment | EC00530.Mechanicals.Systems | 0% | 2012-06-06 | 2012-07-16 | Budgeted Labor Cost | 2012-06-01: 8352; 2012-07-01: 4608
EC1440 | Set Mechanical and Electrical Equipment | EC00530.Mechanicals.Systems | 0% | 2012-06-06 | 2012-07-16 | Actual Labor Units
EC1440 | Set Mechanical and Electrical Equipment | EC00530.Mechanicals.Systems | 0% | 2012-06-06 | 2012-07-16 | Budgeted Labor Units | 2012-06-01: 139; 2012-07-01: 77
EC1510 | Rough-In Plumbing/Piping | EC00530.Mechanicals.Systems | 0% | 2012-07-20 | 2012-07-24 | Actual Labor Cost
EC1510 | Rough-In Plumbing/Piping | EC00530.Mechanicals.Systems | 0% | 2012-07-20 | 2012-07-24 | Budgeted Labor Cost | 2012-07-01: 2232
EC1510 | Rough-In Plumbing/Piping | EC00530.Mechanicals.Systems | 0% | 2012-07-20 | 2012-07-24 | Actual Labor Units
EC1510 | Rough-In Plumbing/Piping | EC00530.Mechanicals.Systems | 0% | 2012-07-20 | 2012-07-24 | Budgeted Labor Units | 2012-07-01: 29
EC1640 | Install Wiring and Cable | EC00530.Mechanicals.Systems | 0% | 2012-09-26 | 2012-11-02 | Actual Labor Cost
EC1640 | Install Wiring and Cable | EC00530.Mechanicals.Systems | 0% | 2012-09-26 | 2012-11-02 | Budgeted Labor Cost | 2012-09-01: 2128; 2012-10-01: 17480; 2012-11-01: 912
EC1640 | Install Wiring and Cable | EC00530.Mechanicals.Systems | 0% | 2012-09-26 | 2012-11-02 | Actual Labor Units
EC1640 | Install Wiring and Cable | EC00530.Mechanicals.Systems | 0% | 2012-09-26 | 2012-11-02 | Budgeted Labor Units | 2012-09-01: 22; 2012-10-01: 184; 2012-11-01: 10
EC1660 | Connect Equipment | EC00530.Mechanicals.Systems | 0% | 2013-03-11 | 2013-03-12 | Actual Labor Cost
EC1660 | Connect Equipment | EC00530.Mechanicals.Systems | 0% | 2013-03-11 | 2013-03-12 | Budgeted Labor Cost
EC1660 | Connect Equipment | EC00530.Mechanicals.Systems | 0% | 2013-03-11 | 2013-03-12 | Actual Labor Units
EC1660 | Connect Equipment | EC00530.Mechanicals.Systems | 0% | 2013-03-11 | 2013-03-12 | Budgeted Labor Units
EC00530.Ex-Finish Exterior Finishes |  |  | 0% | 2011-09-22 | 2012-09-26 | Actual Labor Cost
EC00530.Ex-Finish Exterior Finishes |  |  | 0% | 2011-09-22 | 2012-09-26 | Budgeted Labor Cost | 2011-09-01: 3072; 2011-10-01: 7636; 2011-11-01: 3476; 2012-08-01: 6926.4; 2012-09-01: 4536
EC00530.Ex-Finish Exterior Finishes |  |  | 0% | 2011-09-22 | 2012-09-26 | Actual Labor Units
EC00530.Ex-Finish Exterior Finishes |  |  | 0% | 2011-09-22 | 2012-09-26 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 130; 2011-11-01: 63; 2012-08-01: 158; 2012-09-01: 130
EC1590 | Close-In Phase Begins | EC00530.Ex-Finish | 0% | 2012-08-30 |  | Actual Labor Cost
EC1590 | Close-In Phase Begins | EC00530.Ex-Finish | 0% | 2012-08-30 |  | Budgeted Labor Cost
EC1590 | Close-In Phase Begins | EC00530.Ex-Finish | 0% | 2012-08-30 |  | Actual Labor Units
EC1590 | Close-In Phase Begins | EC00530.Ex-Finish | 0% | 2012-08-30 |  | Budgeted Labor Units
EC1620 | Building Enclosed | EC00530.Ex-Finish | 0% |  | 2012-09-26 | Actual Labor Cost
EC1620 | Building Enclosed | EC00530.Ex-Finish | 0% |  | 2012-09-26 | Budgeted Labor Cost
EC1620 | Building Enclosed | EC00530.Ex-Finish | 0% |  | 2012-09-26 | Actual Labor Units
EC1620 | Building Enclosed | EC00530.Ex-Finish | 0% |  | 2012-09-26 | Budgeted Labor Units
EC00530.Ex-Finish.Brick Brick |  |  | 0% | 2011-09-22 | 2012-08-30 | Actual Labor Cost
EC00530.Ex-Finish.Brick Brick |  |  | 0% | 2011-09-22 | 2012-08-30 | Budgeted Labor Cost | 2011-09-01: 3072; 2011-10-01: 7636; 2011-11-01: 3476; 2012-08-01: 3528
EC00530.Ex-Finish.Brick Brick |  |  | 0% | 2011-09-22 | 2012-08-30 | Actual Labor Units
EC00530.Ex-Finish.Brick Brick |  |  | 0% | 2011-09-22 | 2012-08-30 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 130; 2011-11-01: 63; 2012-08-01: 101
EC1040 | Assemble Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 |  | Actual Labor Cost
EC1040 | Assemble Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 |  | Budgeted Labor Cost
EC1040 | Assemble Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 |  | Actual Labor Units
EC1040 | Assemble Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 |  | Budgeted Labor Units
EC1070 | Review and Approve Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 | 2011-10-18 | Actual Labor Cost
EC1070 | Review and Approve Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 | 2011-10-18 | Budgeted Labor Cost | 2011-09-01: 3072; 2011-10-01: 5568
EC1070 | Review and Approve Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 | 2011-10-18 | Actual Labor Units
EC1070 | Review and Approve Brick Samples | EC00530.Ex-Finish.Brick | 0% | 2011-09-22 | 2011-10-18 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 93
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00530.Ex-Finish.Brick | 0% | 2011-10-18 | 2011-11-02 | Actual Labor Cost
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00530.Ex-Finish.Brick | 0% | 2011-10-18 | 2011-11-02 | Budgeted Labor Cost | 2011-10-01: 2068; 2011-11-01: 308
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00530.Ex-Finish.Brick | 0% | 2011-10-18 | 2011-11-02 | Actual Labor Units
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00530.Ex-Finish.Brick | 0% | 2011-10-18 | 2011-11-02 | Budgeted Labor Units | 2011-10-01: 38; 2011-11-01: 6
EC1220 | Review Bids for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-02 | 2011-11-17 | Actual Labor Cost
EC1220 | Review Bids for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-02 | 2011-11-17 | Budgeted Labor Cost | 2011-11-01: 2376
EC1220 | Review Bids for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-02 | 2011-11-17 | Actual Labor Units
EC1220 | Review Bids for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-02 | 2011-11-17 | Budgeted Labor Units | 2011-11-01: 43
EC1260 | Award Contract for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-17 | 2011-11-22 | Actual Labor Cost
EC1260 | Award Contract for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-17 | 2011-11-22 | Budgeted Labor Cost | 2011-11-01: 792
EC1260 | Award Contract for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-17 | 2011-11-22 | Actual Labor Units
EC1260 | Award Contract for Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-17 | 2011-11-22 | Budgeted Labor Units | 2011-11-01: 14
EC1280 | Deliver Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-22 | 2011-11-23 | Actual Labor Cost
EC1280 | Deliver Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-22 | 2011-11-23 | Budgeted Labor Cost
EC1280 | Deliver Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-22 | 2011-11-23 | Actual Labor Units
EC1280 | Deliver Brick | EC00530.Ex-Finish.Brick | 0% | 2011-11-22 | 2011-11-23 | Budgeted Labor Units
EC1550 | Brick Exterior Walls | EC00530.Ex-Finish.Brick | 0% | 2012-08-13 | 2012-08-30 | Actual Labor Cost
EC1550 | Brick Exterior Walls | EC00530.Ex-Finish.Brick | 0% | 2012-08-13 | 2012-08-30 | Budgeted Labor Cost | 2012-08-01: 3528
EC1550 | Brick Exterior Walls | EC00530.Ex-Finish.Brick | 0% | 2012-08-13 | 2012-08-30 | Actual Labor Units
EC1550 | Brick Exterior Walls | EC00530.Ex-Finish.Brick | 0% | 2012-08-13 | 2012-08-30 | Budgeted Labor Units | 2012-08-01: 101
EC00530.Ex-Finish.Roof Roof |  |  | 0% | 2012-08-30 | 2012-09-26 | Actual Labor Cost
EC00530.Ex-Finish.Roof Roof |  |  | 0% | 2012-08-30 | 2012-09-26 | Budgeted Labor Cost | 2012-08-01: 504; 2012-09-01: 4536
EC00530.Ex-Finish.Roof Roof |  |  | 0% | 2012-08-30 | 2012-09-26 | Actual Labor Units
EC00530.Ex-Finish.Roof Roof |  |  | 0% | 2012-08-30 | 2012-09-26 | Budgeted Labor Units | 2012-08-01: 14; 2012-09-01: 130
EC1600 | Insulation and Built-up Roofing | EC00530.Ex-Finish.Roof | 0% | 2012-08-30 | 2012-09-26 | Actual Labor Cost
EC1600 | Insulation and Built-up Roofing | EC00530.Ex-Finish.Roof | 0% | 2012-08-30 | 2012-09-26 | Budgeted Labor Cost | 2012-08-01: 504; 2012-09-01: 4536
EC1600 | Insulation and Built-up Roofing | EC00530.Ex-Finish.Roof | 0% | 2012-08-30 | 2012-09-26 | Actual Labor Units
EC1600 | Insulation and Built-up Roofing | EC00530.Ex-Finish.Roof | 0% | 2012-08-30 | 2012-09-26 | Budgeted Labor Units | 2012-08-01: 14; 2012-09-01: 130
EC00530.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-08-20 | 2012-08-28 | Actual Labor Cost
EC00530.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-08-20 | 2012-08-28 | Budgeted Labor Cost | 2012-08-01: 2894.4
EC00530.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-08-20 | 2012-08-28 | Actual Labor Units
EC00530.Ex-Finish.Win Doors and Windows |  |  | 0% | 2012-08-20 | 2012-08-28 | Budgeted Labor Units | 2012-08-01: 43
EC1560 | Install Door and Window Frames | EC00530.Ex-Finish.Win | 0% | 2012-08-20 | 2012-08-22 | Actual Labor Cost
EC1560 | Install Door and Window Frames | EC00530.Ex-Finish.Win | 0% | 2012-08-20 | 2012-08-22 | Budgeted Labor Cost | 2012-08-01: 964.8
EC1560 | Install Door and Window Frames | EC00530.Ex-Finish.Win | 0% | 2012-08-20 | 2012-08-22 | Actual Labor Units
EC1560 | Install Door and Window Frames | EC00530.Ex-Finish.Win | 0% | 2012-08-20 | 2012-08-22 | Budgeted Labor Units | 2012-08-01: 14
EC1580 | Install Exterior Doors and Windows | EC00530.Ex-Finish.Win | 0% | 2012-08-22 | 2012-08-28 | Actual Labor Cost
EC1580 | Install Exterior Doors and Windows | EC00530.Ex-Finish.Win | 0% | 2012-08-22 | 2012-08-28 | Budgeted Labor Cost | 2012-08-01: 1929.6
EC1580 | Install Exterior Doors and Windows | EC00530.Ex-Finish.Win | 0% | 2012-08-22 | 2012-08-28 | Actual Labor Units
EC1580 | Install Exterior Doors and Windows | EC00530.Ex-Finish.Win | 0% | 2012-08-22 | 2012-08-28 | Budgeted Labor Units | 2012-08-01: 29
EC00530.Int-Finish Interior Finishes |  |  | 0% | 2011-09-22 | 2013-10-17 | Actual Labor Cost
EC00530.Int-Finish Interior Finishes |  |  | 0% | 2011-09-22 | 2013-10-17 | Budgeted Labor Cost | 2011-09-01: 3072; 2011-10-01: 7636; 2011-11-01: 4620; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 4620; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 4620; 2012-08-01: 5060; 2012-09-01: 3916; 2013-06-01: 1441.62; 2013-07-01: 16832; 2013-08-01: 20216; 2013-09-01: 10720; 2013-10-01: 8260.78
EC00530.Int-Finish Interior Finishes |  |  | 0% | 2011-09-22 | 2013-10-17 | Actual Labor Units
EC00530.Int-Finish Interior Finishes |  |  | 0% | 2011-09-22 | 2013-10-17 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 130; 2011-11-01: 84; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 84; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 84; 2012-08-01: 92; 2012-09-01: 71; 2013-06-01: 22; 2013-07-01: 248; 2013-08-01: 262; 2013-09-01: 189; 2013-10-01: 143
EC1700 | Drywall in Offices | EC00530.Int-Finish | 0% | 2013-06-26 | 2013-08-05 | Actual Labor Cost
EC1700 | Drywall in Offices | EC00530.Int-Finish | 0% | 2013-06-26 | 2013-08-05 | Budgeted Labor Cost | 2013-06-01: 1441.62; 2013-07-01: 11792; 2013-08-01: 1238.38
EC1700 | Drywall in Offices | EC00530.Int-Finish | 0% | 2013-06-26 | 2013-08-05 | Actual Labor Units
EC1700 | Drywall in Offices | EC00530.Int-Finish | 0% | 2013-06-26 | 2013-08-05 | Budgeted Labor Units | 2013-06-01: 22; 2013-07-01: 176; 2013-08-01: 18
EC1820 | Touch-up and Clean-up | EC00530.Int-Finish | 0% | 2013-10-08 | 2013-10-10 | Actual Labor Cost
EC1820 | Touch-up and Clean-up | EC00530.Int-Finish | 0% | 2013-10-08 | 2013-10-10 | Budgeted Labor Cost | 2013-10-01: 1804.8
EC1820 | Touch-up and Clean-up | EC00530.Int-Finish | 0% | 2013-10-08 | 2013-10-10 | Actual Labor Units
EC1820 | Touch-up and Clean-up | EC00530.Int-Finish | 0% | 2013-10-08 | 2013-10-10 | Budgeted Labor Units | 2013-10-01: 34
EC1840 | Finishes Complete | EC00530.Int-Finish | 0% |  | 2013-10-11 | Actual Labor Cost
EC1840 | Finishes Complete | EC00530.Int-Finish | 0% |  | 2013-10-11 | Budgeted Labor Cost
EC1840 | Finishes Complete | EC00530.Int-Finish | 0% |  | 2013-10-11 | Actual Labor Units
EC1840 | Finishes Complete | EC00530.Int-Finish | 0% |  | 2013-10-11 | Budgeted Labor Units
EC1850 | Punch List | EC00530.Int-Finish | 0% | 2013-10-14 | 2013-10-17 | Actual Labor Cost
EC1850 | Punch List | EC00530.Int-Finish | 0% | 2013-10-14 | 2013-10-17 | Budgeted Labor Cost | 2013-10-01: 3609.6
EC1850 | Punch List | EC00530.Int-Finish | 0% | 2013-10-14 | 2013-10-17 | Actual Labor Units
EC1850 | Punch List | EC00530.Int-Finish | 0% | 2013-10-14 | 2013-10-17 | Budgeted Labor Units | 2013-10-01: 67
EC1860 | Building Addition Complete | EC00530.Int-Finish | 0% |  | 2013-10-17 | Actual Labor Cost
EC1860 | Building Addition Complete | EC00530.Int-Finish | 0% |  | 2013-10-17 | Budgeted Labor Cost
EC1860 | Building Addition Complete | EC00530.Int-Finish | 0% |  | 2013-10-17 | Actual Labor Units
EC1860 | Building Addition Complete | EC00530.Int-Finish | 0% |  | 2013-10-17 | Budgeted Labor Units
EC00530.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-08-15 | 2013-10-01 | Actual Labor Cost
EC00530.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-08-15 | 2013-10-01 | Budgeted Labor Cost | 2013-08-01: 8424; 2013-09-01: 1584
EC00530.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-08-15 | 2013-10-01 | Actual Labor Units
EC00530.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2013-08-15 | 2013-10-01 | Budgeted Labor Units | 2013-08-01: 86; 2013-09-01: 29
EC1760 | Install Lighting Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-08-15 | 2013-08-22 | Actual Labor Cost
EC1760 | Install Lighting Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-08-15 | 2013-08-22 | Budgeted Labor Cost | 2013-08-01: 8424
EC1760 | Install Lighting Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-08-15 | 2013-08-22 | Actual Labor Units
EC1760 | Install Lighting Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-08-15 | 2013-08-22 | Budgeted Labor Units | 2013-08-01: 86
EC1810 | Install Plumbing Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-09-25 | 2013-10-01 | Actual Labor Cost
EC1810 | Install Plumbing Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-09-25 | 2013-10-01 | Budgeted Labor Cost | 2013-09-01: 1584
EC1810 | Install Plumbing Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-09-25 | 2013-10-01 | Actual Labor Units
EC1810 | Install Plumbing Fixtures | EC00530.Int-Finish.Fixtures | 0% | 2013-09-25 | 2013-10-01 | Budgeted Labor Units | 2013-09-01: 29
EC00530.Int-Finish.Coverings Floor and Carpeting |  |  | 0% | 2011-09-22 | 2013-09-25 | Actual Labor Cost
EC00530.Int-Finish.Coverings Floor and Carpeting |  |  | 0% | 2011-09-22 | 2013-09-25 | Budgeted Labor Cost | 2011-09-01: 3072; 2011-10-01: 7636; 2011-11-01: 4620; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 4620; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 4620; 2012-08-01: 5060; 2012-09-01: 3916; 2013-09-01: 3240
EC00530.Int-Finish.Coverings Floor and Carpeting |  |  | 0% | 2011-09-22 | 2013-09-25 | Actual Labor Units
EC00530.Int-Finish.Coverings Floor and Carpeting |  |  | 0% | 2011-09-22 | 2013-09-25 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 130; 2011-11-01: 84; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 84; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 84; 2012-08-01: 92; 2012-09-01: 71; 2013-09-01: 72
EC1060 | Assemble and Submit Flooring Samples | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 |  | Actual Labor Cost
EC1060 | Assemble and Submit Flooring Samples | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 |  | Budgeted Labor Cost
EC1060 | Assemble and Submit Flooring Samples | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 |  | Actual Labor Units
EC1060 | Assemble and Submit Flooring Samples | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 |  | Budgeted Labor Units
EC1080 | Review and Approve Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 | 2011-10-18 | Actual Labor Cost
EC1080 | Review and Approve Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 | 2011-10-18 | Budgeted Labor Cost | 2011-09-01: 3072; 2011-10-01: 5568
EC1080 | Review and Approve Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 | 2011-10-18 | Actual Labor Units
EC1080 | Review and Approve Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-09-22 | 2011-10-18 | Budgeted Labor Units | 2011-09-01: 51; 2011-10-01: 93
EC1170 | Prepare and Solicit Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-10-18 | 2011-11-11 | Actual Labor Cost
EC1170 | Prepare and Solicit Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-10-18 | 2011-11-11 | Budgeted Labor Cost | 2011-10-01: 2068; 2011-11-01: 1892
EC1170 | Prepare and Solicit Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-10-18 | 2011-11-11 | Actual Labor Units
EC1170 | Prepare and Solicit Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-10-18 | 2011-11-11 | Budgeted Labor Units | 2011-10-01: 38; 2011-11-01: 34
EC1250 | Review Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-11 | 2011-11-29 | Actual Labor Cost
EC1250 | Review Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-11 | 2011-11-29 | Budgeted Labor Cost | 2011-11-01: 2376
EC1250 | Review Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-11 | 2011-11-29 | Actual Labor Units
EC1250 | Review Bids for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-11 | 2011-11-29 | Budgeted Labor Units | 2011-11-01: 43
EC1300 | Award Contract for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-29 | 2011-12-02 | Actual Labor Cost
EC1300 | Award Contract for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-29 | 2011-12-02 | Budgeted Labor Cost | 2011-11-01: 352; 2011-12-01: 440
EC1300 | Award Contract for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-29 | 2011-12-02 | Actual Labor Units
EC1300 | Award Contract for Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-11-29 | 2011-12-02 | Budgeted Labor Units | 2011-11-01: 6; 2011-12-01: 8
EC1310 | Fabricate and Deliver Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-12-05 | 2012-09-27 | Actual Labor Cost
EC1310 | Fabricate and Deliver Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-12-05 | 2012-09-27 | Budgeted Labor Cost | 2011-12-01: 4180; 2012-01-01: 4620; 2012-02-01: 4620; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 4620; 2012-08-01: 5060; 2012-09-01: 3916
EC1310 | Fabricate and Deliver Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-12-05 | 2012-09-27 | Actual Labor Units
EC1310 | Fabricate and Deliver Flooring | EC00530.Int-Finish.Coverings | 0% | 2011-12-05 | 2012-09-27 | Budgeted Labor Units | 2011-12-01: 76; 2012-01-01: 84; 2012-02-01: 84; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 84; 2012-08-01: 92; 2012-09-01: 71
EC1790 | Install Floor and Carpeting | EC00530.Int-Finish.Coverings | 0% | 2013-09-12 | 2013-09-25 | Actual Labor Cost
EC1790 | Install Floor and Carpeting | EC00530.Int-Finish.Coverings | 0% | 2013-09-12 | 2013-09-25 | Budgeted Labor Cost | 2013-09-01: 3240
EC1790 | Install Floor and Carpeting | EC00530.Int-Finish.Coverings | 0% | 2013-09-12 | 2013-09-25 | Actual Labor Units
EC1790 | Install Floor and Carpeting | EC00530.Int-Finish.Coverings | 0% | 2013-09-12 | 2013-09-25 | Budgeted Labor Units | 2013-09-01: 72
EC00530.Int-Finish.Carp Carpentry |  |  | 0% | 2013-08-05 | 2013-10-08 | Actual Labor Cost
EC00530.Int-Finish.Carp Carpentry |  |  | 0% | 2013-08-05 | 2013-10-08 | Budgeted Labor Cost | 2013-08-01: 10553.62; 2013-09-01: 5896; 2013-10-01: 2846.38
EC00530.Int-Finish.Carp Carpentry |  |  | 0% | 2013-08-05 | 2013-10-08 | Actual Labor Units
EC00530.Int-Finish.Carp Carpentry |  |  | 0% | 2013-08-05 | 2013-10-08 | Budgeted Labor Units | 2013-08-01: 158; 2013-09-01: 88; 2013-10-01: 42
EC1740 | Install Ceiling Grid | EC00530.Int-Finish.Carp | 0% | 2013-08-05 | 2013-09-12 | Actual Labor Cost
EC1740 | Install Ceiling Grid | EC00530.Int-Finish.Carp | 0% | 2013-08-05 | 2013-09-12 | Budgeted Labor Cost | 2013-08-01: 10553.62; 2013-09-01: 3918.38
EC1740 | Install Ceiling Grid | EC00530.Int-Finish.Carp | 0% | 2013-08-05 | 2013-09-12 | Actual Labor Units
EC1740 | Install Ceiling Grid | EC00530.Int-Finish.Carp | 0% | 2013-08-05 | 2013-09-12 | Budgeted Labor Units | 2013-08-01: 158; 2013-09-01: 58
EC1800 | Finish Carpentry and Millwork | EC00530.Int-Finish.Carp | 0% | 2013-09-25 | 2013-10-08 | Actual Labor Cost
EC1800 | Finish Carpentry and Millwork | EC00530.Int-Finish.Carp | 0% | 2013-09-25 | 2013-10-08 | Budgeted Labor Cost | 2013-09-01: 1977.62; 2013-10-01: 2846.38
EC1800 | Finish Carpentry and Millwork | EC00530.Int-Finish.Carp | 0% | 2013-09-25 | 2013-10-08 | Actual Labor Units
EC1800 | Finish Carpentry and Millwork | EC00530.Int-Finish.Carp | 0% | 2013-09-25 | 2013-10-08 | Budgeted Labor Units | 2013-09-01: 30; 2013-10-01: 42
EC00530.Int-Finish.Paint Paint |  |  | 0% | 2013-07-08 | 2013-07-19 | Actual Labor Cost
EC00530.Int-Finish.Paint Paint |  |  | 0% | 2013-07-08 | 2013-07-19 | Budgeted Labor Cost | 2013-07-01: 5040
EC00530.Int-Finish.Paint Paint |  |  | 0% | 2013-07-08 | 2013-07-19 | Actual Labor Units
EC00530.Int-Finish.Paint Paint |  |  | 0% | 2013-07-08 | 2013-07-19 | Budgeted Labor Units | 2013-07-01: 72
EC1720 | Paint Building Interior | EC00530.Int-Finish.Paint | 0% | 2013-07-08 | 2013-07-19 | Actual Labor Cost
EC1720 | Paint Building Interior | EC00530.Int-Finish.Paint | 0% | 2013-07-08 | 2013-07-19 | Budgeted Labor Cost | 2013-07-01: 5040
EC1720 | Paint Building Interior | EC00530.Int-Finish.Paint | 0% | 2013-07-08 | 2013-07-19 | Actual Labor Units
EC1720 | Paint Building Interior | EC00530.Int-Finish.Paint | 0% | 2013-07-08 | 2013-07-19 | Budgeted Labor Units | 2013-07-01: 72
EC00501 Haitang Corporate Park |  |  | 31.03% | 01-Sep-10 A | 2013-01-11 | Actual Labor Cost | 2010-09-01: 10293.11; 2010-10-01: 10293.11; 2010-11-01: 10554.79; 2010-12-01: 40913.18; 2011-01-01: 27465.56; 2011-02-01: 30553.06; 2011-03-01: 28748.86; 2011-04-01: 31669.35
EC00501 Haitang Corporate Park |  |  | 31.03% | 01-Sep-10 A | 2013-01-11 | Budgeted Labor Cost | 2010-09-01: 10080; 2010-10-01: 10080; 2010-11-01: 10560; 2010-12-01: 39136; 2011-01-01: 31458; 2011-02-01: 14118; 2011-03-01: 43340; 2011-04-01: 33620; 2011-05-01: 37580; 2011-06-01: 16667.2; 2011-07-01: 13200; 2011-08-01: 20416; 2011-09-01: 28619.2; 2011-10-01: 46950.4; 2011-11-01: 73270.4; 2011-12-01: 22752.8; 2012-01-01: 18478.4; 2012-02-01: 22648; 2012-03-01: 10008; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 3872; 2012-08-01: 12960.85; 2012-09-01: 21072.07; 2012-10-01: 14398.25; 2012-11-01: 19013.75; 2012-12-01: 11256; 2013-01-01: 10059.08
EC00501 Haitang Corporate Park |  |  | 31.03% | 01-Sep-10 A | 2013-01-11 | Actual Labor Units | 2010-09-01: 172; 2010-10-01: 172; 2010-11-01: 176; 2010-12-01: 655; 2011-01-01: 449; 2011-02-01: 458; 2011-03-01: 533; 2011-04-01: 638
EC00501 Haitang Corporate Park |  |  | 31.03% | 01-Sep-10 A | 2013-01-11 | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 176; 2010-12-01: 627; 2011-01-01: 512; 2011-02-01: 220; 2011-03-01: 736; 2011-04-01: 672; 2011-05-01: 740; 2011-06-01: 294; 2011-07-01: 240; 2011-08-01: 371; 2011-09-01: 534; 2011-10-01: 907; 2011-11-01: 1495; 2011-12-01: 464; 2012-01-01: 374; 2012-02-01: 290; 2012-03-01: 142; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 70; 2012-08-01: 200; 2012-09-01: 295; 2012-10-01: 205; 2012-11-01: 248; 2012-12-01: 202; 2013-01-01: 183
EC00501.D&E Design and Engineering |  |  | 100% | 01-Sep-10 A | 07-Jan-11 A | Actual Labor Cost | 2010-09-01: 10293.11; 2010-10-01: 10293.11; 2010-11-01: 10554.79; 2010-12-01: 11562.05; 2011-01-01: 2572.94
EC00501.D&E Design and Engineering |  |  | 100% | 01-Sep-10 A | 07-Jan-11 A | Budgeted Labor Cost | 2010-09-01: 10080; 2010-10-01: 10080; 2010-11-01: 10560; 2010-12-01: 10560; 2011-01-01: 4080
EC00501.D&E Design and Engineering |  |  | 100% | 01-Sep-10 A | 07-Jan-11 A | Actual Labor Units | 2010-09-01: 172; 2010-10-01: 172; 2010-11-01: 176; 2010-12-01: 193; 2011-01-01: 43
EC00501.D&E Design and Engineering |  |  | 100% | 01-Sep-10 A | 07-Jan-11 A | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 176; 2010-12-01: 176; 2011-01-01: 68
EC1000 | Design Building Addition | EC00501.D&E | 100% | 01-Sep-10 A | 08-Nov-10 A | Actual Labor Cost | 2010-09-01: 10293.11; 2010-10-01: 10293.11; 2010-11-01: 2597.78
EC1000 | Design Building Addition | EC00501.D&E | 100% | 01-Sep-10 A | 08-Nov-10 A | Budgeted Labor Cost | 2010-09-01: 10080; 2010-10-01: 10080; 2010-11-01: 3024
EC1000 | Design Building Addition | EC00501.D&E | 100% | 01-Sep-10 A | 08-Nov-10 A | Actual Labor Units | 2010-09-01: 172; 2010-10-01: 172; 2010-11-01: 43
EC1000 | Design Building Addition | EC00501.D&E | 100% | 01-Sep-10 A | 08-Nov-10 A | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 50
EC1010 | Start Office Building Addition Project | EC00501.D&E | 100% | 01-Sep-10 A |  | Actual Labor Cost
EC1010 | Start Office Building Addition Project | EC00501.D&E | 100% | 01-Sep-10 A |  | Budgeted Labor Cost
EC1010 | Start Office Building Addition Project | EC00501.D&E | 100% | 01-Sep-10 A |  | Actual Labor Units
EC1010 | Start Office Building Addition Project | EC00501.D&E | 100% | 01-Sep-10 A |  | Budgeted Labor Units
EC1030 | Review and Approve Designs | EC00501.D&E | 100% | 08-Nov-10 A | 03-Dec-10 A | Actual Labor Cost | 2010-11-01: 7957.01; 2010-12-01: 1114.99
EC1030 | Review and Approve Designs | EC00501.D&E | 100% | 08-Nov-10 A | 03-Dec-10 A | Budgeted Labor Cost | 2010-11-01: 7536; 2010-12-01: 1536
EC1030 | Review and Approve Designs | EC00501.D&E | 100% | 08-Nov-10 A | 03-Dec-10 A | Actual Labor Units | 2010-11-01: 133; 2010-12-01: 19
EC1030 | Review and Approve Designs | EC00501.D&E | 100% | 08-Nov-10 A | 03-Dec-10 A | Budgeted Labor Units | 2010-11-01: 126; 2010-12-01: 26
EC1050 | Assemble Technical Data for Heat Pump | EC00501.D&E | 100% | 06-Dec-10 A | 15-Dec-10 A | Actual Labor Cost | 2010-12-01: 3300
EC1050 | Assemble Technical Data for Heat Pump | EC00501.D&E | 100% | 06-Dec-10 A | 15-Dec-10 A | Budgeted Labor Cost | 2010-12-01: 3024
EC1050 | Assemble Technical Data for Heat Pump | EC00501.D&E | 100% | 06-Dec-10 A | 15-Dec-10 A | Actual Labor Units | 2010-12-01: 55
EC1050 | Assemble Technical Data for Heat Pump | EC00501.D&E | 100% | 06-Dec-10 A | 15-Dec-10 A | Budgeted Labor Units | 2010-12-01: 50
EC1160 | Review Technical Data on Heat Pumps | EC00501.D&E | 100% | 13-Dec-10 A | 07-Jan-11 A | Actual Labor Cost | 2010-12-01: 7147.06; 2011-01-01: 2572.94
EC1160 | Review Technical Data on Heat Pumps | EC00501.D&E | 100% | 13-Dec-10 A | 07-Jan-11 A | Budgeted Labor Cost | 2010-12-01: 6000; 2011-01-01: 4080
EC1160 | Review Technical Data on Heat Pumps | EC00501.D&E | 100% | 13-Dec-10 A | 07-Jan-11 A | Actual Labor Units | 2010-12-01: 119; 2011-01-01: 43
EC1160 | Review Technical Data on Heat Pumps | EC00501.D&E | 100% | 13-Dec-10 A | 07-Jan-11 A | Budgeted Labor Units | 2010-12-01: 100; 2011-01-01: 68
EC00501.Found Foundation |  |  | 76.3% | 03-Dec-10 A | 2011-06-03 | Actual Labor Cost | 2010-12-01: 11291.12; 2011-01-01: 11102.21; 2011-02-01: 22386.67; 2011-03-01: 17676.19; 2011-04-01: 22098.81
EC00501.Found Foundation |  |  | 76.3% | 03-Dec-10 A | 2011-06-03 | Budgeted Labor Cost | 2010-12-01: 10528; 2011-01-01: 12880; 2011-02-01: 9520; 2011-03-01: 28600; 2011-04-01: 24380; 2011-05-01: 28340; 2011-06-01: 2411.2
EC00501.Found Foundation |  |  | 76.3% | 03-Dec-10 A | 2011-06-03 | Actual Labor Units | 2010-12-01: 161; 2011-01-01: 159; 2011-02-01: 309; 2011-03-01: 331; 2011-04-01: 464
EC00501.Found Foundation |  |  | 76.3% | 03-Dec-10 A | 2011-06-03 | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 184; 2011-02-01: 136; 2011-03-01: 468; 2011-04-01: 504; 2011-05-01: 572; 2011-06-01: 35
EC1090 | Begin Building Construction | EC00501.Found | 100% | 03-Dec-10 A |  | Actual Labor Cost
EC1090 | Begin Building Construction | EC00501.Found | 100% | 03-Dec-10 A |  | Budgeted Labor Cost
EC1090 | Begin Building Construction | EC00501.Found | 100% | 03-Dec-10 A |  | Actual Labor Units
EC1090 | Begin Building Construction | EC00501.Found | 100% | 03-Dec-10 A |  | Budgeted Labor Units
EC1100 | Site Preparation | EC00501.Found | 100% | 03-Dec-10 A | 24-Jan-11 A | Actual Labor Cost | 2010-12-01: 11291.12; 2011-01-01: 9008.88
EC1100 | Site Preparation | EC00501.Found | 100% | 03-Dec-10 A | 24-Jan-11 A | Budgeted Labor Cost | 2010-12-01: 10528; 2011-01-01: 10640
EC1100 | Site Preparation | EC00501.Found | 100% | 03-Dec-10 A | 24-Jan-11 A | Actual Labor Units | 2010-12-01: 161; 2011-01-01: 129
EC1100 | Site Preparation | EC00501.Found | 100% | 03-Dec-10 A | 24-Jan-11 A | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 152
EC1230 | Excavation | EC00501.Found | 100% | 26-Jan-11 A | 24-Feb-11 A | Actual Labor Cost | 2011-01-01: 2093.33; 2011-02-01: 8896.67
EC1230 | Excavation | EC00501.Found | 100% | 26-Jan-11 A | 24-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 2240; 2011-02-01: 9520
EC1230 | Excavation | EC00501.Found | 100% | 26-Jan-11 A | 24-Feb-11 A | Actual Labor Units | 2011-01-01: 30; 2011-02-01: 127
EC1230 | Excavation | EC00501.Found | 100% | 26-Jan-11 A | 24-Feb-11 A | Budgeted Labor Units | 2011-01-01: 32; 2011-02-01: 136
EC1320 | Install Underground Water Lines | EC00501.Found | 100% | 22-Feb-11 A | 28-Feb-11 A | Actual Labor Cost | 2011-02-01: 5225
EC1320 | Install Underground Water Lines | EC00501.Found | 100% | 22-Feb-11 A | 28-Feb-11 A | Budgeted Labor Cost | 2011-03-01: 4620
EC1320 | Install Underground Water Lines | EC00501.Found | 100% | 22-Feb-11 A | 28-Feb-11 A | Actual Labor Units | 2011-02-01: 95
EC1320 | Install Underground Water Lines | EC00501.Found | 100% | 22-Feb-11 A | 28-Feb-11 A | Budgeted Labor Units | 2011-03-01: 84
EC1330 | Install Underground Electric Conduit | EC00501.Found | 100% | 17-Feb-11 A | 25-Feb-11 A | Actual Labor Cost | 2011-02-01: 8265
EC1330 | Install Underground Electric Conduit | EC00501.Found | 100% | 17-Feb-11 A | 25-Feb-11 A | Budgeted Labor Cost | 2011-03-01: 7980
EC1330 | Install Underground Electric Conduit | EC00501.Found | 100% | 17-Feb-11 A | 25-Feb-11 A | Actual Labor Units | 2011-02-01: 87
EC1330 | Install Underground Electric Conduit | EC00501.Found | 100% | 17-Feb-11 A | 25-Feb-11 A | Budgeted Labor Units | 2011-03-01: 84
EC1340 | Form/Pour Concrete Footings | EC00501.Found | 100% | 11-Mar-11 A | 11-Apr-11 A | Actual Labor Cost | 2011-03-01: 17676.19; 2011-04-01: 7923.81
EC1340 | Form/Pour Concrete Footings | EC00501.Found | 100% | 11-Mar-11 A | 11-Apr-11 A | Budgeted Labor Cost | 2011-03-01: 16000; 2011-04-01: 10880
EC1340 | Form/Pour Concrete Footings | EC00501.Found | 100% | 11-Mar-11 A | 11-Apr-11 A | Actual Labor Units | 2011-03-01: 331; 2011-04-01: 149
EC1340 | Form/Pour Concrete Footings | EC00501.Found | 100% | 11-Mar-11 A | 11-Apr-11 A | Budgeted Labor Units | 2011-03-01: 300; 2011-04-01: 204
EC1350 | Concrete Foundation Walls | EC00501.Found | 73.81% | 15-Apr-11 A | 2011-05-12 | Actual Labor Cost | 2011-04-01: 14175
EC1350 | Concrete Foundation Walls | EC00501.Found | 73.81% | 15-Apr-11 A | 2011-05-12 | Budgeted Labor Cost | 2011-04-01: 13500; 2011-05-01: 9180
EC1350 | Concrete Foundation Walls | EC00501.Found | 73.81% | 15-Apr-11 A | 2011-05-12 | Actual Labor Units | 2011-04-01: 315
EC1350 | Concrete Foundation Walls | EC00501.Found | 73.81% | 15-Apr-11 A | 2011-05-12 | Budgeted Labor Units | 2011-04-01: 300; 2011-05-01: 204
EC1360 | Form and Pour Slab | EC00501.Found | 0% | 2011-05-12 | 2011-05-27 | Actual Labor Cost
EC1360 | Form and Pour Slab | EC00501.Found | 0% | 2011-05-12 | 2011-05-27 | Budgeted Labor Cost | 2011-05-01: 16968
EC1360 | Form and Pour Slab | EC00501.Found | 0% | 2011-05-12 | 2011-05-27 | Actual Labor Units
EC1360 | Form and Pour Slab | EC00501.Found | 0% | 2011-05-12 | 2011-05-27 | Budgeted Labor Units | 2011-05-01: 336
EC1370 | Backfill and Compact Walls | EC00501.Found | 0% | 2011-05-27 | 2011-06-03 | Actual Labor Cost
EC1370 | Backfill and Compact Walls | EC00501.Found | 0% | 2011-05-27 | 2011-06-03 | Budgeted Labor Cost | 2011-05-01: 2192; 2011-06-01: 2411.2
EC1370 | Backfill and Compact Walls | EC00501.Found | 0% | 2011-05-27 | 2011-06-03 | Actual Labor Units
EC1370 | Backfill and Compact Walls | EC00501.Found | 0% | 2011-05-27 | 2011-06-03 | Budgeted Labor Units | 2011-05-01: 32; 2011-06-01: 35
EC1380 | Foundation Phase Complete | EC00501.Found | 0% |  | 2011-06-02 | Actual Labor Cost
EC1380 | Foundation Phase Complete | EC00501.Found | 0% |  | 2011-06-02 | Budgeted Labor Cost
EC1380 | Foundation Phase Complete | EC00501.Found | 0% |  | 2011-06-02 | Actual Labor Units
EC1380 | Foundation Phase Complete | EC00501.Found | 0% |  | 2011-06-02 | Budgeted Labor Units
EC00501.Structure Structure |  |  | 0% | 2011-06-02 | 2011-12-08 | Actual Labor Cost
EC00501.Structure Structure |  |  | 0% | 2011-06-02 | 2011-12-08 | Budgeted Labor Cost | 2011-06-01: 4576; 2011-07-01: 4400; 2011-08-01: 10296; 2011-09-01: 15347.2; 2011-10-01: 27630.4; 2011-11-01: 52001.6; 2011-12-01: 4524.8
EC00501.Structure Structure |  |  | 0% | 2011-06-02 | 2011-12-08 | Actual Labor Units
EC00501.Structure Structure |  |  | 0% | 2011-06-02 | 2011-12-08 | Budgeted Labor Units | 2011-06-01: 83; 2011-07-01: 80; 2011-08-01: 187; 2011-09-01: 299; 2011-10-01: 571; 2011-11-01: 1109; 2011-12-01: 90
EC1390 | Erect Structural Frame | EC00501.Structure | 0% | 2011-06-02 | 2011-08-02 | Actual Labor Cost
EC1390 | Erect Structural Frame | EC00501.Structure | 0% | 2011-06-02 | 2011-08-02 | Budgeted Labor Cost | 2011-06-01: 4576; 2011-07-01: 4400; 2011-08-01: 264
EC1390 | Erect Structural Frame | EC00501.Structure | 0% | 2011-06-02 | 2011-08-02 | Actual Labor Units
EC1390 | Erect Structural Frame | EC00501.Structure | 0% | 2011-06-02 | 2011-08-02 | Budgeted Labor Units | 2011-06-01: 83; 2011-07-01: 80; 2011-08-01: 5
EC1410 | Begin Structural Phase | EC00501.Structure | 0% | 2011-08-01 |  | Actual Labor Cost
EC1410 | Begin Structural Phase | EC00501.Structure | 0% | 2011-08-01 |  | Budgeted Labor Cost
EC1410 | Begin Structural Phase | EC00501.Structure | 0% | 2011-08-01 |  | Actual Labor Units
EC1410 | Begin Structural Phase | EC00501.Structure | 0% | 2011-08-01 |  | Budgeted Labor Units
EC1420 | Floor Decking | EC00501.Structure | 0% | 2011-08-01 | 2011-09-12 | Actual Labor Cost
EC1420 | Floor Decking | EC00501.Structure | 0% | 2011-08-01 | 2011-09-12 | Budgeted Labor Cost | 2011-08-01: 10032; 2011-09-01: 2904
EC1420 | Floor Decking | EC00501.Structure | 0% | 2011-08-01 | 2011-09-12 | Actual Labor Units
EC1420 | Floor Decking | EC00501.Structure | 0% | 2011-08-01 | 2011-09-12 | Budgeted Labor Units | 2011-08-01: 182; 2011-09-01: 53
EC1430 | Concrete First Floor | EC00501.Structure | 0% | 2011-09-09 | 2011-10-25 | Actual Labor Cost
EC1430 | Concrete First Floor | EC00501.Structure | 0% | 2011-09-09 | 2011-10-25 | Budgeted Labor Cost | 2011-09-01: 12443.2; 2011-10-01: 13008.8
EC1430 | Concrete First Floor | EC00501.Structure | 0% | 2011-09-09 | 2011-10-25 | Actual Labor Units
EC1430 | Concrete First Floor | EC00501.Structure | 0% | 2011-09-09 | 2011-10-25 | Budgeted Labor Units | 2011-09-01: 246; 2011-10-01: 258
EC1460 | Erect Stairwell and Elevator Walls | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Actual Labor Cost
EC1460 | Erect Stairwell and Elevator Walls | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Budgeted Labor Cost | 2011-10-01: 1372; 2011-11-01: 4508
EC1460 | Erect Stairwell and Elevator Walls | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Actual Labor Units
EC1460 | Erect Stairwell and Elevator Walls | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Budgeted Labor Units | 2011-10-01: 39; 2011-11-01: 129
EC1470 | Concrete Basement Slab | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Actual Labor Cost
EC1470 | Concrete Basement Slab | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Budgeted Labor Cost | 2011-10-01: 9290.4; 2011-11-01: 30525.6
EC1470 | Concrete Basement Slab | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Actual Labor Units
EC1470 | Concrete Basement Slab | EC00501.Structure | 0% | 2011-10-25 | 2011-11-23 | Budgeted Labor Units | 2011-10-01: 196; 2011-11-01: 644
EC1480 | Concrete Second Floor | EC00501.Structure | 0% | 2011-10-25 | 2011-12-08 | Actual Labor Cost
EC1480 | Concrete Second Floor | EC00501.Structure | 0% | 2011-10-25 | 2011-12-08 | Budgeted Labor Cost | 2011-10-01: 3959.2; 2011-11-01: 16968; 2011-12-01: 4524.8
EC1480 | Concrete Second Floor | EC00501.Structure | 0% | 2011-10-25 | 2011-12-08 | Actual Labor Units
EC1480 | Concrete Second Floor | EC00501.Structure | 0% | 2011-10-25 | 2011-12-08 | Budgeted Labor Units | 2011-10-01: 78; 2011-11-01: 336; 2011-12-01: 90
EC1540 | Structure Complete | EC00501.Structure | 0% |  | 2011-12-07 | Actual Labor Cost
EC1540 | Structure Complete | EC00501.Structure | 0% |  | 2011-12-07 | Budgeted Labor Cost
EC1540 | Structure Complete | EC00501.Structure | 0% |  | 2011-12-07 | Actual Labor Units
EC1540 | Structure Complete | EC00501.Structure | 0% |  | 2011-12-07 | Budgeted Labor Units
EC00501.Mechanicals Mechanical/Electrical Systems |  |  | 10.01% | 07-Jan-11 A | 2013-01-07 | Actual Labor Cost | 2011-01-01: 2925.41; 2011-02-01: 2267.04; 2011-03-01: 5163.27; 2011-04-01: 4714.29
EC00501.Mechanicals Mechanical/Electrical Systems |  |  | 10.01% | 07-Jan-11 A | 2013-01-07 | Budgeted Labor Cost | 2011-01-01: 3190; 2011-02-01: 3630; 2011-03-01: 5060; 2011-04-01: 4620; 2011-05-01: 4620; 2011-06-01: 4840; 2011-07-01: 4400; 2011-08-01: 5060; 2011-09-01: 8652; 2011-10-01: 14700; 2011-11-01: 16648.8; 2011-12-01: 5359.2; 2012-01-01: 8734.4; 2012-02-01: 20756; 2012-03-01: 10008; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 3872; 2012-08-01: 12960.85; 2012-09-01: 5636.75; 2013-01-01: 1008
EC00501.Mechanicals Mechanical/Electrical Systems |  |  | 10.01% | 07-Jan-11 A | 2013-01-07 | Actual Labor Units | 2011-01-01: 53; 2011-02-01: 41; 2011-03-01: 94; 2011-04-01: 86
EC00501.Mechanicals Mechanical/Electrical Systems |  |  | 10.01% | 07-Jan-11 A | 2013-01-07 | Budgeted Labor Units | 2011-01-01: 58; 2011-02-01: 66; 2011-03-01: 92; 2011-04-01: 84; 2011-05-01: 84; 2011-06-01: 88; 2011-07-01: 80; 2011-08-01: 92; 2011-09-01: 151; 2011-10-01: 252; 2011-11-01: 302; 2011-12-01: 101; 2012-01-01: 143; 2012-02-01: 256; 2012-03-01: 142; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 70; 2012-08-01: 200; 2012-09-01: 69; 2013-01-01: 17
EC1490 | Rough-In Phase Begins | EC00501.Mechanicals | 0% | 2011-11-03 |  | Actual Labor Cost
EC1490 | Rough-In Phase Begins | EC00501.Mechanicals | 0% | 2011-11-03 |  | Budgeted Labor Cost
EC1490 | Rough-In Phase Begins | EC00501.Mechanicals | 0% | 2011-11-03 |  | Actual Labor Units
EC1490 | Rough-In Phase Begins | EC00501.Mechanicals | 0% | 2011-11-03 |  | Budgeted Labor Units
EC1690 | Rough In Complete | EC00501.Mechanicals | 0% |  | 2012-09-05 | Actual Labor Cost
EC1690 | Rough In Complete | EC00501.Mechanicals | 0% |  | 2012-09-05 | Budgeted Labor Cost
EC1690 | Rough In Complete | EC00501.Mechanicals | 0% |  | 2012-09-05 | Actual Labor Units
EC1690 | Rough In Complete | EC00501.Mechanicals | 0% |  | 2012-09-05 | Budgeted Labor Units
EC00501.Mechanicals.Lifts Elevator |  |  | 0% | 2011-11-23 | 2012-09-11 | Actual Labor Cost
EC00501.Mechanicals.Lifts Elevator |  |  | 0% | 2011-11-23 | 2012-09-11 | Budgeted Labor Cost | 2011-11-01: 1764; 2012-09-01: 3528
EC00501.Mechanicals.Lifts Elevator |  |  | 0% | 2011-11-23 | 2012-09-11 | Actual Labor Units
EC00501.Mechanicals.Lifts Elevator |  |  | 0% | 2011-11-23 | 2012-09-11 | Budgeted Labor Units | 2011-11-01: 17; 2012-09-01: 34
EC1520 | Install Elevator Rails and Equipment | EC00501.Mechanicals.Lifts | 0% | 2011-11-23 | 2011-11-28 | Actual Labor Cost
EC1520 | Install Elevator Rails and Equipment | EC00501.Mechanicals.Lifts | 0% | 2011-11-23 | 2011-11-28 | Budgeted Labor Cost | 2011-11-01: 1764
EC1520 | Install Elevator Rails and Equipment | EC00501.Mechanicals.Lifts | 0% | 2011-11-23 | 2011-11-28 | Actual Labor Units
EC1520 | Install Elevator Rails and Equipment | EC00501.Mechanicals.Lifts | 0% | 2011-11-23 | 2011-11-28 | Budgeted Labor Units | 2011-11-01: 17
EC1710 | Install Elevator Cab and Finishes | EC00501.Mechanicals.Lifts | 0% | 2012-09-05 | 2012-09-11 | Actual Labor Cost
EC1710 | Install Elevator Cab and Finishes | EC00501.Mechanicals.Lifts | 0% | 2012-09-05 | 2012-09-11 | Budgeted Labor Cost | 2012-09-01: 3528
EC1710 | Install Elevator Cab and Finishes | EC00501.Mechanicals.Lifts | 0% | 2012-09-05 | 2012-09-11 | Actual Labor Units
EC1710 | Install Elevator Cab and Finishes | EC00501.Mechanicals.Lifts | 0% | 2012-09-05 | 2012-09-11 | Budgeted Labor Units | 2012-09-01: 34
EC00501.Mechanicals.HVAC HVAC |  |  | 14.75% | 07-Jan-11 A | 2013-01-07 | Actual Labor Cost | 2011-01-01: 2925.41; 2011-02-01: 2267.04; 2011-03-01: 5163.27; 2011-04-01: 4714.29
EC00501.Mechanicals.HVAC HVAC |  |  | 14.75% | 07-Jan-11 A | 2013-01-07 | Budgeted Labor Cost | 2011-01-01: 3190; 2011-02-01: 3630; 2011-03-01: 5060; 2011-04-01: 4620; 2011-05-01: 4620; 2011-06-01: 4840; 2011-07-01: 4400; 2011-08-01: 5060; 2011-09-01: 4620; 2011-10-01: 4620; 2011-11-01: 11272.8; 2011-12-01: 5359.2; 2012-01-01: 5922.4; 2012-02-01: 4796; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 3872; 2012-08-01: 12960.85; 2012-09-01: 2108.75; 2013-01-01: 1008
EC00501.Mechanicals.HVAC HVAC |  |  | 14.75% | 07-Jan-11 A | 2013-01-07 | Actual Labor Units | 2011-01-01: 53; 2011-02-01: 41; 2011-03-01: 94; 2011-04-01: 86
EC00501.Mechanicals.HVAC HVAC |  |  | 14.75% | 07-Jan-11 A | 2013-01-07 | Budgeted Labor Units | 2011-01-01: 58; 2011-02-01: 66; 2011-03-01: 92; 2011-04-01: 84; 2011-05-01: 84; 2011-06-01: 88; 2011-07-01: 80; 2011-08-01: 92; 2011-09-01: 84; 2011-10-01: 84; 2011-11-01: 235; 2011-12-01: 101; 2012-01-01: 114; 2012-02-01: 88; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 70; 2012-08-01: 200; 2012-09-01: 35; 2013-01-01: 17
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 07-Jan-11 A | 24-Jan-11 A | Actual Labor Cost | 2011-01-01: 2530
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 07-Jan-11 A | 24-Jan-11 A | Budgeted Labor Cost | 2011-01-01: 2772
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 07-Jan-11 A | 24-Jan-11 A | Actual Labor Units | 2011-01-01: 46
EC1190 | Prepare and Solicit Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 07-Jan-11 A | 24-Jan-11 A | Budgeted Labor Units | 2011-01-01: 50
EC1240 | Review Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 28-Jan-11 A | 08-Feb-11 A | Actual Labor Cost | 2011-01-01: 395.41; 2011-02-01: 1144.59
EC1240 | Review Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 28-Jan-11 A | 08-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 418; 2011-02-01: 1430
EC1240 | Review Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 28-Jan-11 A | 08-Feb-11 A | Actual Labor Units | 2011-01-01: 7; 2011-02-01: 21
EC1240 | Review Bids for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 28-Jan-11 A | 08-Feb-11 A | Budgeted Labor Units | 2011-01-01: 8; 2011-02-01: 26
EC1270 | Award Contract for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 02-Mar-11 A | 14-Mar-11 A | Actual Labor Cost
EC1270 | Award Contract for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 02-Mar-11 A | 14-Mar-11 A | Budgeted Labor Cost
EC1270 | Award Contract for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 02-Mar-11 A | 14-Mar-11 A | Actual Labor Units
EC1270 | Award Contract for Heat Pump | EC00501.Mechanicals.HVAC | 100% | 02-Mar-11 A | 14-Mar-11 A | Budgeted Labor Units
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00501.Mechanicals.HVAC | 14.24% | 22-Feb-11 A | 2012-08-21 | Actual Labor Cost | 2011-02-01: 1122.45; 2011-03-01: 5163.27; 2011-04-01: 4714.29
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00501.Mechanicals.HVAC | 14.24% | 22-Feb-11 A | 2012-08-21 | Budgeted Labor Cost | 2011-02-01: 2200; 2011-03-01: 5060; 2011-04-01: 4620; 2011-05-01: 4620; 2011-06-01: 4840; 2011-07-01: 4400; 2011-08-01: 5060; 2011-09-01: 4620; 2011-10-01: 4620; 2011-11-01: 4620; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 4620; 2012-03-01: 4840; 2012-04-01: 4620; 2012-05-01: 4840; 2012-06-01: 4620; 2012-07-01: 3872
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00501.Mechanicals.HVAC | 14.24% | 22-Feb-11 A | 2012-08-21 | Actual Labor Units | 2011-02-01: 20; 2011-03-01: 94; 2011-04-01: 86
EC1290 | Fabricate and Deliver Heat Pump and Controls | EC00501.Mechanicals.HVAC | 14.24% | 22-Feb-11 A | 2012-08-21 | Budgeted Labor Units | 2011-02-01: 40; 2011-03-01: 92; 2011-04-01: 84; 2011-05-01: 84; 2011-06-01: 88; 2011-07-01: 80; 2011-08-01: 92; 2011-09-01: 84; 2011-10-01: 84; 2011-11-01: 84; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 84; 2012-03-01: 88; 2012-04-01: 84; 2012-05-01: 88; 2012-06-01: 84; 2012-07-01: 70
EC1500 | Install HVAC Ducts | EC00501.Mechanicals.HVAC | 0% | 2011-11-03 | 2011-12-05 | Actual Labor Cost
EC1500 | Install HVAC Ducts | EC00501.Mechanicals.HVAC | 0% | 2011-11-03 | 2011-12-05 | Budgeted Labor Cost | 2011-11-01: 6652.8; 2011-12-01: 739.2
EC1500 | Install HVAC Ducts | EC00501.Mechanicals.HVAC | 0% | 2011-11-03 | 2011-12-05 | Actual Labor Units
EC1500 | Install HVAC Ducts | EC00501.Mechanicals.HVAC | 0% | 2011-11-03 | 2011-12-05 | Budgeted Labor Units | 2011-11-01: 151; 2011-12-01: 17
EC1630 | Insulate Ducts | EC00501.Mechanicals.HVAC | 0% | 2012-01-26 | 2012-02-01 | Actual Labor Cost
EC1630 | Insulate Ducts | EC00501.Mechanicals.HVAC | 0% | 2012-01-26 | 2012-02-01 | Budgeted Labor Cost | 2012-01-01: 1302.4; 2012-02-01: 176
EC1630 | Insulate Ducts | EC00501.Mechanicals.HVAC | 0% | 2012-01-26 | 2012-02-01 | Actual Labor Units
EC1630 | Insulate Ducts | EC00501.Mechanicals.HVAC | 0% | 2012-01-26 | 2012-02-01 | Budgeted Labor Units | 2012-01-01: 30; 2012-02-01: 4
EC1650 | Set Heat Pump | EC00501.Mechanicals.HVAC | 0% | 2012-08-09 | 2012-08-23 | Actual Labor Cost
EC1650 | Set Heat Pump | EC00501.Mechanicals.HVAC | 0% | 2012-08-09 | 2012-08-23 | Budgeted Labor Cost | 2012-08-01: 5040
EC1650 | Set Heat Pump | EC00501.Mechanicals.HVAC | 0% | 2012-08-09 | 2012-08-23 | Actual Labor Units
EC1650 | Set Heat Pump | EC00501.Mechanicals.HVAC | 0% | 2012-08-09 | 2012-08-23 | Budgeted Labor Units | 2012-08-01: 84
EC1670 | Relocate HVAC Chiller | EC00501.Mechanicals.HVAC | 0% | 2012-08-23 | 2012-09-04 | Actual Labor Cost
EC1670 | Relocate HVAC Chiller | EC00501.Mechanicals.HVAC | 0% | 2012-08-23 | 2012-09-04 | Budgeted Labor Cost | 2012-08-01: 7920.85; 2012-09-01: 92.75
EC1670 | Relocate HVAC Chiller | EC00501.Mechanicals.HVAC | 0% | 2012-08-23 | 2012-09-04 | Actual Labor Units
EC1670 | Relocate HVAC Chiller | EC00501.Mechanicals.HVAC | 0% | 2012-08-23 | 2012-09-04 | Budgeted Labor Units | 2012-08-01: 116; 2012-09-01: 1
EC1680 | Startup and Test HVAC | EC00501.Mechanicals.HVAC | 0% | 2012-09-04 | 2012-09-06 | Actual Labor Cost
EC1680 | Startup and Test HVAC | EC00501.Mechanicals.HVAC | 0% | 2012-09-04 | 2012-09-06 | Budgeted Labor Cost | 2012-09-01: 2016
EC1680 | Startup and Test HVAC | EC00501.Mechanicals.HVAC | 0% | 2012-09-04 | 2012-09-06 | Actual Labor Units
EC1680 | Startup and Test HVAC | EC00501.Mechanicals.HVAC | 0% | 2012-09-04 | 2012-09-06 | Budgeted Labor Units | 2012-09-01: 34
EC1770 | Install AC Grills and Registers | EC00501.Mechanicals.HVAC | 0% | 2012-10-30 | 2012-11-06 | Actual Labor Cost
EC1770 | Install AC Grills and Registers | EC00501.Mechanicals.HVAC | 0% | 2012-10-30 | 2012-11-06 | Budgeted Labor Cost
EC1770 | Install AC Grills and Registers | EC00501.Mechanicals.HVAC | 0% | 2012-10-30 | 2012-11-06 | Actual Labor Units
EC1770 | Install AC Grills and Registers | EC00501.Mechanicals.HVAC | 0% | 2012-10-30 | 2012-11-06 | Budgeted Labor Units
EC1830 | Test and Balance HVAC Equipment | EC00501.Mechanicals.HVAC | 0% | 2013-01-03 | 2013-01-07 | Actual Labor Cost
EC1830 | Test and Balance HVAC Equipment | EC00501.Mechanicals.HVAC | 0% | 2013-01-03 | 2013-01-07 | Budgeted Labor Cost | 2013-01-01: 1008
EC1830 | Test and Balance HVAC Equipment | EC00501.Mechanicals.HVAC | 0% | 2013-01-03 | 2013-01-07 | Actual Labor Units
EC1830 | Test and Balance HVAC Equipment | EC00501.Mechanicals.HVAC | 0% | 2013-01-03 | 2013-01-07 | Budgeted Labor Units | 2013-01-01: 17
EC00501.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2011-09-20 | 2012-08-24 | Actual Labor Cost
EC00501.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2011-09-20 | 2012-08-24 | Budgeted Labor Cost | 2011-09-01: 4032; 2011-10-01: 10080; 2011-11-01: 3612; 2012-01-01: 2812; 2012-02-01: 15960; 2012-03-01: 5168
EC00501.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2011-09-20 | 2012-08-24 | Actual Labor Units
EC00501.Mechanicals.Systems Plumbing and Electrical |  |  | 0% | 2011-09-20 | 2012-08-24 | Budgeted Labor Units | 2011-09-01: 67; 2011-10-01: 168; 2011-11-01: 50; 2012-01-01: 30; 2012-02-01: 168; 2012-03-01: 54
EC1440 | Set Mechanical and Electrical Equipment | EC00501.Mechanicals.Systems | 0% | 2011-09-20 | 2011-11-03 | Actual Labor Cost
EC1440 | Set Mechanical and Electrical Equipment | EC00501.Mechanicals.Systems | 0% | 2011-09-20 | 2011-11-03 | Budgeted Labor Cost | 2011-09-01: 4032; 2011-10-01: 10080; 2011-11-01: 1008
EC1440 | Set Mechanical and Electrical Equipment | EC00501.Mechanicals.Systems | 0% | 2011-09-20 | 2011-11-03 | Actual Labor Units
EC1440 | Set Mechanical and Electrical Equipment | EC00501.Mechanicals.Systems | 0% | 2011-09-20 | 2011-11-03 | Budgeted Labor Units | 2011-09-01: 67; 2011-10-01: 168; 2011-11-01: 17
EC1510 | Rough-In Plumbing/Piping | EC00501.Mechanicals.Systems | 0% | 2011-11-09 | 2011-11-11 | Actual Labor Cost
EC1510 | Rough-In Plumbing/Piping | EC00501.Mechanicals.Systems | 0% | 2011-11-09 | 2011-11-11 | Budgeted Labor Cost | 2011-11-01: 2604
EC1510 | Rough-In Plumbing/Piping | EC00501.Mechanicals.Systems | 0% | 2011-11-09 | 2011-11-11 | Actual Labor Units
EC1510 | Rough-In Plumbing/Piping | EC00501.Mechanicals.Systems | 0% | 2011-11-09 | 2011-11-11 | Budgeted Labor Units | 2011-11-01: 34
EC1640 | Install Wiring and Cable | EC00501.Mechanicals.Systems | 0% | 2012-01-26 | 2012-03-09 | Actual Labor Cost
EC1640 | Install Wiring and Cable | EC00501.Mechanicals.Systems | 0% | 2012-01-26 | 2012-03-09 | Budgeted Labor Cost | 2012-01-01: 2812; 2012-02-01: 15960; 2012-03-01: 5168
EC1640 | Install Wiring and Cable | EC00501.Mechanicals.Systems | 0% | 2012-01-26 | 2012-03-09 | Actual Labor Units
EC1640 | Install Wiring and Cable | EC00501.Mechanicals.Systems | 0% | 2012-01-26 | 2012-03-09 | Budgeted Labor Units | 2012-01-01: 30; 2012-02-01: 168; 2012-03-01: 54
EC1660 | Connect Equipment | EC00501.Mechanicals.Systems | 0% | 2012-08-23 | 2012-08-24 | Actual Labor Cost
EC1660 | Connect Equipment | EC00501.Mechanicals.Systems | 0% | 2012-08-23 | 2012-08-24 | Budgeted Labor Cost
EC1660 | Connect Equipment | EC00501.Mechanicals.Systems | 0% | 2012-08-23 | 2012-08-24 | Actual Labor Units
EC1660 | Connect Equipment | EC00501.Mechanicals.Systems | 0% | 2012-08-23 | 2012-08-24 | Budgeted Labor Units
EC00501.Ex-Finish Exterior Finishes |  |  | 44.2% | 03-Dec-10 A | 2012-01-27 | Actual Labor Cost | 2010-12-01: 9600; 2011-01-01: 4125; 2011-02-01: 1279.35; 2011-03-01: 590.65
EC00501.Ex-Finish Exterior Finishes |  |  | 44.2% | 03-Dec-10 A | 2012-01-27 | Budgeted Labor Cost | 2010-12-01: 9024; 2011-01-01: 5676; 2011-02-01: 924; 2011-03-01: 924; 2011-12-01: 8248.8; 2012-01-01: 5124
EC00501.Ex-Finish Exterior Finishes |  |  | 44.2% | 03-Dec-10 A | 2012-01-27 | Actual Labor Units | 2010-12-01: 160; 2011-01-01: 75; 2011-02-01: 23; 2011-03-01: 11
EC00501.Ex-Finish Exterior Finishes |  |  | 44.2% | 03-Dec-10 A | 2012-01-27 | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 102; 2011-02-01: 17; 2011-03-01: 17; 2011-12-01: 190; 2012-01-01: 146
EC1590 | Close-In Phase Begins | EC00501.Ex-Finish | 0% | 2011-12-28 |  | Actual Labor Cost
EC1590 | Close-In Phase Begins | EC00501.Ex-Finish | 0% | 2011-12-28 |  | Budgeted Labor Cost
EC1590 | Close-In Phase Begins | EC00501.Ex-Finish | 0% | 2011-12-28 |  | Actual Labor Units
EC1590 | Close-In Phase Begins | EC00501.Ex-Finish | 0% | 2011-12-28 |  | Budgeted Labor Units
EC1620 | Building Enclosed | EC00501.Ex-Finish | 0% |  | 2012-01-26 | Actual Labor Cost
EC1620 | Building Enclosed | EC00501.Ex-Finish | 0% |  | 2012-01-26 | Budgeted Labor Cost
EC1620 | Building Enclosed | EC00501.Ex-Finish | 0% |  | 2012-01-26 | Actual Labor Units
EC1620 | Building Enclosed | EC00501.Ex-Finish | 0% |  | 2012-01-26 | Budgeted Labor Units
EC00501.Ex-Finish.Brick Brick |  |  | 60.43% | 03-Dec-10 A | 2011-12-29 | Actual Labor Cost | 2010-12-01: 9600; 2011-01-01: 4125; 2011-02-01: 1279.35; 2011-03-01: 590.65
EC00501.Ex-Finish.Brick Brick |  |  | 60.43% | 03-Dec-10 A | 2011-12-29 | Budgeted Labor Cost | 2010-12-01: 9024; 2011-01-01: 5676; 2011-02-01: 924; 2011-03-01: 924; 2011-12-01: 4116
EC00501.Ex-Finish.Brick Brick |  |  | 60.43% | 03-Dec-10 A | 2011-12-29 | Actual Labor Units | 2010-12-01: 160; 2011-01-01: 75; 2011-02-01: 23; 2011-03-01: 11
EC00501.Ex-Finish.Brick Brick |  |  | 60.43% | 03-Dec-10 A | 2011-12-29 | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 102; 2011-02-01: 17; 2011-03-01: 17; 2011-12-01: 118
EC1040 | Assemble Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A |  | Actual Labor Cost
EC1040 | Assemble Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A |  | Budgeted Labor Cost
EC1040 | Assemble Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A |  | Actual Labor Units
EC1040 | Assemble Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A |  | Budgeted Labor Units
EC1070 | Review and Approve Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A | 30-Dec-10 A | Actual Labor Cost | 2010-12-01: 9600
EC1070 | Review and Approve Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A | 30-Dec-10 A | Budgeted Labor Cost | 2010-12-01: 9024; 2011-01-01: 1056
EC1070 | Review and Approve Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A | 30-Dec-10 A | Actual Labor Units | 2010-12-01: 160
EC1070 | Review and Approve Brick Samples | EC00501.Ex-Finish.Brick | 100% | 03-Dec-10 A | 30-Dec-10 A | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 18
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00501.Ex-Finish.Brick | 100% | 05-Jan-11 A | 24-Jan-11 A | Actual Labor Cost | 2011-01-01: 2475
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00501.Ex-Finish.Brick | 100% | 05-Jan-11 A | 24-Jan-11 A | Budgeted Labor Cost | 2011-01-01: 2772
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00501.Ex-Finish.Brick | 100% | 05-Jan-11 A | 24-Jan-11 A | Actual Labor Units | 2011-01-01: 45
EC1180 | Prepare and Solicit Bids for Brick Exterior | EC00501.Ex-Finish.Brick | 100% | 05-Jan-11 A | 24-Jan-11 A | Budgeted Labor Units | 2011-01-01: 50
EC1220 | Review Bids for Brick | EC00501.Ex-Finish.Brick | 100% | 19-Jan-11 A | 07-Feb-11 A | Actual Labor Cost | 2011-01-01: 1650; 2011-02-01: 825
EC1220 | Review Bids for Brick | EC00501.Ex-Finish.Brick | 100% | 19-Jan-11 A | 07-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 1848; 2011-02-01: 924
EC1220 | Review Bids for Brick | EC00501.Ex-Finish.Brick | 100% | 19-Jan-11 A | 07-Feb-11 A | Actual Labor Units | 2011-01-01: 30; 2011-02-01: 15
EC1220 | Review Bids for Brick | EC00501.Ex-Finish.Brick | 100% | 19-Jan-11 A | 07-Feb-11 A | Budgeted Labor Units | 2011-01-01: 34; 2011-02-01: 17
EC1260 | Award Contract for Brick | EC00501.Ex-Finish.Brick | 100% | 23-Feb-11 A | 08-Mar-11 A | Actual Labor Cost | 2011-02-01: 454.35; 2011-03-01: 590.65
EC1260 | Award Contract for Brick | EC00501.Ex-Finish.Brick | 100% | 23-Feb-11 A | 08-Mar-11 A | Budgeted Labor Cost | 2011-03-01: 924
EC1260 | Award Contract for Brick | EC00501.Ex-Finish.Brick | 100% | 23-Feb-11 A | 08-Mar-11 A | Actual Labor Units | 2011-02-01: 8; 2011-03-01: 11
EC1260 | Award Contract for Brick | EC00501.Ex-Finish.Brick | 100% | 23-Feb-11 A | 08-Mar-11 A | Budgeted Labor Units | 2011-03-01: 17
EC1280 | Deliver Brick | EC00501.Ex-Finish.Brick | 100% | 14-Feb-11 A | 16-Feb-11 A | Actual Labor Cost
EC1280 | Deliver Brick | EC00501.Ex-Finish.Brick | 100% | 14-Feb-11 A | 16-Feb-11 A | Budgeted Labor Cost
EC1280 | Deliver Brick | EC00501.Ex-Finish.Brick | 100% | 14-Feb-11 A | 16-Feb-11 A | Actual Labor Units
EC1280 | Deliver Brick | EC00501.Ex-Finish.Brick | 100% | 14-Feb-11 A | 16-Feb-11 A | Budgeted Labor Units
EC1550 | Brick Exterior Walls | EC00501.Ex-Finish.Brick | 0% | 2011-12-07 | 2011-12-29 | Actual Labor Cost
EC1550 | Brick Exterior Walls | EC00501.Ex-Finish.Brick | 0% | 2011-12-07 | 2011-12-29 | Budgeted Labor Cost | 2011-12-01: 4116
EC1550 | Brick Exterior Walls | EC00501.Ex-Finish.Brick | 0% | 2011-12-07 | 2011-12-29 | Actual Labor Units
EC1550 | Brick Exterior Walls | EC00501.Ex-Finish.Brick | 0% | 2011-12-07 | 2011-12-29 | Budgeted Labor Units | 2011-12-01: 118
EC00501.Ex-Finish.Roof Roof |  |  | 0% | 2011-12-28 | 2012-01-27 | Actual Labor Cost
EC00501.Ex-Finish.Roof Roof |  |  | 0% | 2011-12-28 | 2012-01-27 | Budgeted Labor Cost | 2011-12-01: 756; 2012-01-01: 5124
EC00501.Ex-Finish.Roof Roof |  |  | 0% | 2011-12-28 | 2012-01-27 | Actual Labor Units
EC00501.Ex-Finish.Roof Roof |  |  | 0% | 2011-12-28 | 2012-01-27 | Budgeted Labor Units | 2011-12-01: 22; 2012-01-01: 146
EC1600 | Insulation and Built-up Roofing | EC00501.Ex-Finish.Roof | 0% | 2011-12-28 | 2012-01-27 | Actual Labor Cost
EC1600 | Insulation and Built-up Roofing | EC00501.Ex-Finish.Roof | 0% | 2011-12-28 | 2012-01-27 | Budgeted Labor Cost | 2011-12-01: 756; 2012-01-01: 5124
EC1600 | Insulation and Built-up Roofing | EC00501.Ex-Finish.Roof | 0% | 2011-12-28 | 2012-01-27 | Actual Labor Units
EC1600 | Insulation and Built-up Roofing | EC00501.Ex-Finish.Roof | 0% | 2011-12-28 | 2012-01-27 | Budgeted Labor Units | 2011-12-01: 22; 2012-01-01: 146
EC00501.Ex-Finish.Win Doors and Windows |  |  | 0% | 2011-12-14 | 2011-12-22 | Actual Labor Cost
EC00501.Ex-Finish.Win Doors and Windows |  |  | 0% | 2011-12-14 | 2011-12-22 | Budgeted Labor Cost | 2011-12-01: 3376.8
EC00501.Ex-Finish.Win Doors and Windows |  |  | 0% | 2011-12-14 | 2011-12-22 | Actual Labor Units
EC00501.Ex-Finish.Win Doors and Windows |  |  | 0% | 2011-12-14 | 2011-12-22 | Budgeted Labor Units | 2011-12-01: 50
EC1560 | Install Door and Window Frames | EC00501.Ex-Finish.Win | 0% | 2011-12-14 | 2011-12-16 | Actual Labor Cost
EC1560 | Install Door and Window Frames | EC00501.Ex-Finish.Win | 0% | 2011-12-14 | 2011-12-16 | Budgeted Labor Cost | 2011-12-01: 1125.6
EC1560 | Install Door and Window Frames | EC00501.Ex-Finish.Win | 0% | 2011-12-14 | 2011-12-16 | Actual Labor Units
EC1560 | Install Door and Window Frames | EC00501.Ex-Finish.Win | 0% | 2011-12-14 | 2011-12-16 | Budgeted Labor Units | 2011-12-01: 17
EC1580 | Install Exterior Doors and Windows | EC00501.Ex-Finish.Win | 0% | 2011-12-16 | 2011-12-22 | Actual Labor Cost
EC1580 | Install Exterior Doors and Windows | EC00501.Ex-Finish.Win | 0% | 2011-12-16 | 2011-12-22 | Budgeted Labor Cost | 2011-12-01: 2251.2
EC1580 | Install Exterior Doors and Windows | EC00501.Ex-Finish.Win | 0% | 2011-12-16 | 2011-12-22 | Actual Labor Units
EC1580 | Install Exterior Doors and Windows | EC00501.Ex-Finish.Win | 0% | 2011-12-16 | 2011-12-22 | Budgeted Labor Units | 2011-12-01: 34
EC00501.Int-Finish Interior Finishes |  |  | 19.57% | 03-Dec-10 A | 2013-01-11 | Actual Labor Cost | 2010-12-01: 8460; 2011-01-01: 6740; 2011-02-01: 4620; 2011-03-01: 5318.75; 2011-04-01: 4856.25
EC00501.Int-Finish Interior Finishes |  |  | 19.57% | 03-Dec-10 A | 2013-01-11 | Budgeted Labor Cost | 2010-12-01: 9024; 2011-01-01: 5632; 2011-02-01: 44; 2011-03-01: 8756; 2011-04-01: 4620; 2011-05-01: 4620; 2011-06-01: 4840; 2011-07-01: 4400; 2011-08-01: 5060; 2011-09-01: 4620; 2011-10-01: 4620; 2011-11-01: 4620; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 1892; 2012-09-01: 15435.32; 2012-10-01: 14398.25; 2012-11-01: 19013.75; 2012-12-01: 11256; 2013-01-01: 9051.08
EC00501.Int-Finish Interior Finishes |  |  | 19.57% | 03-Dec-10 A | 2013-01-11 | Actual Labor Units | 2010-12-01: 141; 2011-01-01: 119; 2011-02-01: 84; 2011-03-01: 97; 2011-04-01: 88
EC00501.Int-Finish Interior Finishes |  |  | 19.57% | 03-Dec-10 A | 2013-01-11 | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 101; 2011-02-01: 1; 2011-03-01: 159; 2011-04-01: 84; 2011-05-01: 84; 2011-06-01: 88; 2011-07-01: 80; 2011-08-01: 92; 2011-09-01: 84; 2011-10-01: 84; 2011-11-01: 84; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 34; 2012-09-01: 227; 2012-10-01: 205; 2012-11-01: 248; 2012-12-01: 202; 2013-01-01: 166
EC1700 | Drywall in Offices | EC00501.Int-Finish | 0% | 2012-09-05 | 2012-10-18 | Actual Labor Cost
EC1700 | Drywall in Offices | EC00501.Int-Finish | 0% | 2012-09-05 | 2012-10-18 | Budgeted Labor Cost | 2012-09-01: 9555.32; 2012-10-01: 7328.68
EC1700 | Drywall in Offices | EC00501.Int-Finish | 0% | 2012-09-05 | 2012-10-18 | Actual Labor Units
EC1700 | Drywall in Offices | EC00501.Int-Finish | 0% | 2012-09-05 | 2012-10-18 | Budgeted Labor Units | 2012-09-01: 143; 2012-10-01: 109
EC1820 | Touch-up and Clean-up | EC00501.Int-Finish | 0% | 2013-01-02 | 2013-01-04 | Actual Labor Cost
EC1820 | Touch-up and Clean-up | EC00501.Int-Finish | 0% | 2013-01-02 | 2013-01-04 | Budgeted Labor Cost | 2013-01-01: 4211.2
EC1820 | Touch-up and Clean-up | EC00501.Int-Finish | 0% | 2013-01-02 | 2013-01-04 | Actual Labor Units
EC1820 | Touch-up and Clean-up | EC00501.Int-Finish | 0% | 2013-01-02 | 2013-01-04 | Budgeted Labor Units | 2013-01-01: 78
EC1840 | Finishes Complete | EC00501.Int-Finish | 0% |  | 2013-01-07 | Actual Labor Cost
EC1840 | Finishes Complete | EC00501.Int-Finish | 0% |  | 2013-01-07 | Budgeted Labor Cost
EC1840 | Finishes Complete | EC00501.Int-Finish | 0% |  | 2013-01-07 | Actual Labor Units
EC1840 | Finishes Complete | EC00501.Int-Finish | 0% |  | 2013-01-07 | Budgeted Labor Units
EC1850 | Punch List | EC00501.Int-Finish | 0% | 2013-01-07 | 2013-01-11 | Actual Labor Cost
EC1850 | Punch List | EC00501.Int-Finish | 0% | 2013-01-07 | 2013-01-11 | Budgeted Labor Cost | 2013-01-01: 4211.2
EC1850 | Punch List | EC00501.Int-Finish | 0% | 2013-01-07 | 2013-01-11 | Actual Labor Units
EC1850 | Punch List | EC00501.Int-Finish | 0% | 2013-01-07 | 2013-01-11 | Budgeted Labor Units | 2013-01-01: 78
EC1860 | Building Addition Complete | EC00501.Int-Finish | 0% |  | 2013-01-11 | Actual Labor Cost
EC1860 | Building Addition Complete | EC00501.Int-Finish | 0% |  | 2013-01-11 | Budgeted Labor Cost
EC1860 | Building Addition Complete | EC00501.Int-Finish | 0% |  | 2013-01-11 | Actual Labor Units
EC1860 | Building Addition Complete | EC00501.Int-Finish | 0% |  | 2013-01-11 | Budgeted Labor Units
EC00501.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2012-10-30 | 2012-12-21 | Actual Labor Cost
EC00501.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2012-10-30 | 2012-12-21 | Budgeted Labor Cost | 2012-10-01: 2070.25; 2012-11-01: 7757.75; 2012-12-01: 1848
EC00501.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2012-10-30 | 2012-12-21 | Actual Labor Units
EC00501.Int-Finish.Fixtures Plumbing and Lighting Fixtures |  |  | 0% | 2012-10-30 | 2012-12-21 | Budgeted Labor Units | 2012-10-01: 21; 2012-11-01: 80; 2012-12-01: 34
EC1760 | Install Lighting Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-10-30 | 2012-11-08 | Actual Labor Cost
EC1760 | Install Lighting Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-10-30 | 2012-11-08 | Budgeted Labor Cost | 2012-10-01: 2070.25; 2012-11-01: 7757.75
EC1760 | Install Lighting Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-10-30 | 2012-11-08 | Actual Labor Units
EC1760 | Install Lighting Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-10-30 | 2012-11-08 | Budgeted Labor Units | 2012-10-01: 21; 2012-11-01: 80
EC1810 | Install Plumbing Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-12-17 | 2012-12-21 | Actual Labor Cost
EC1810 | Install Plumbing Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-12-17 | 2012-12-21 | Budgeted Labor Cost | 2012-12-01: 1848
EC1810 | Install Plumbing Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-12-17 | 2012-12-21 | Actual Labor Units
EC1810 | Install Plumbing Fixtures | EC00501.Int-Finish.Fixtures | 0% | 2012-12-17 | 2012-12-21 | Budgeted Labor Units | 2012-12-01: 34
EC00501.Int-Finish.Coverings Floor and Carpeting |  |  | 38.27% | 03-Dec-10 A | 2012-12-17 | Actual Labor Cost | 2010-12-01: 8460; 2011-01-01: 6740; 2011-02-01: 4620; 2011-03-01: 5318.75; 2011-04-01: 4856.25
EC00501.Int-Finish.Coverings Floor and Carpeting |  |  | 38.27% | 03-Dec-10 A | 2012-12-17 | Budgeted Labor Cost | 2010-12-01: 9024; 2011-01-01: 5632; 2011-02-01: 44; 2011-03-01: 8756; 2011-04-01: 4620; 2011-05-01: 4620; 2011-06-01: 4840; 2011-07-01: 4400; 2011-08-01: 5060; 2011-09-01: 4620; 2011-10-01: 4620; 2011-11-01: 4620; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 1892; 2012-12-01: 3780
EC00501.Int-Finish.Coverings Floor and Carpeting |  |  | 38.27% | 03-Dec-10 A | 2012-12-17 | Actual Labor Units | 2010-12-01: 141; 2011-01-01: 119; 2011-02-01: 84; 2011-03-01: 97; 2011-04-01: 88
EC00501.Int-Finish.Coverings Floor and Carpeting |  |  | 38.27% | 03-Dec-10 A | 2012-12-17 | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 101; 2011-02-01: 1; 2011-03-01: 159; 2011-04-01: 84; 2011-05-01: 84; 2011-06-01: 88; 2011-07-01: 80; 2011-08-01: 92; 2011-09-01: 84; 2011-10-01: 84; 2011-11-01: 84; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 34; 2012-12-01: 84
EC1060 | Assemble and Submit Flooring Samples | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A |  | Actual Labor Cost
EC1060 | Assemble and Submit Flooring Samples | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A |  | Budgeted Labor Cost
EC1060 | Assemble and Submit Flooring Samples | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A |  | Actual Labor Units
EC1060 | Assemble and Submit Flooring Samples | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A |  | Budgeted Labor Units
EC1080 | Review and Approve Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A | 10-Jan-11 A | Actual Labor Cost | 2010-12-01: 8460; 2011-01-01: 2340
EC1080 | Review and Approve Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A | 10-Jan-11 A | Budgeted Labor Cost | 2010-12-01: 9024; 2011-01-01: 1056
EC1080 | Review and Approve Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A | 10-Jan-11 A | Actual Labor Units | 2010-12-01: 141; 2011-01-01: 39
EC1080 | Review and Approve Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Dec-10 A | 10-Jan-11 A | Budgeted Labor Units | 2010-12-01: 150; 2011-01-01: 18
EC1170 | Prepare and Solicit Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Jan-11 A | 08-Feb-11 A | Actual Labor Cost | 2011-01-01: 4400; 2011-02-01: 1100
EC1170 | Prepare and Solicit Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Jan-11 A | 08-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 4576; 2011-02-01: 44
EC1170 | Prepare and Solicit Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Jan-11 A | 08-Feb-11 A | Actual Labor Units | 2011-01-01: 80; 2011-02-01: 20
EC1170 | Prepare and Solicit Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 03-Jan-11 A | 08-Feb-11 A | Budgeted Labor Units | 2011-01-01: 83; 2011-02-01: 1
EC1250 | Review Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 02-Feb-11 A | 18-Feb-11 A | Actual Labor Cost | 2011-02-01: 2640
EC1250 | Review Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 02-Feb-11 A | 18-Feb-11 A | Budgeted Labor Cost | 2011-03-01: 2772
EC1250 | Review Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 02-Feb-11 A | 18-Feb-11 A | Actual Labor Units | 2011-02-01: 48
EC1250 | Review Bids for Flooring | EC00501.Int-Finish.Coverings | 100% | 02-Feb-11 A | 18-Feb-11 A | Budgeted Labor Units | 2011-03-01: 50
EC1300 | Award Contract for Flooring | EC00501.Int-Finish.Coverings | 100% | 18-Feb-11 A | 25-Feb-11 A | Actual Labor Cost | 2011-02-01: 880
EC1300 | Award Contract for Flooring | EC00501.Int-Finish.Coverings | 100% | 18-Feb-11 A | 25-Feb-11 A | Budgeted Labor Cost | 2011-03-01: 924
EC1300 | Award Contract for Flooring | EC00501.Int-Finish.Coverings | 100% | 18-Feb-11 A | 25-Feb-11 A | Actual Labor Units | 2011-02-01: 16
EC1300 | Award Contract for Flooring | EC00501.Int-Finish.Coverings | 100% | 18-Feb-11 A | 25-Feb-11 A | Budgeted Labor Units | 2011-03-01: 17
EC1310 | Fabricate and Deliver Flooring | EC00501.Int-Finish.Coverings | 19.78% | 01-Mar-11 A | 2012-02-13 | Actual Labor Cost | 2011-03-01: 5318.75; 2011-04-01: 4856.25
EC1310 | Fabricate and Deliver Flooring | EC00501.Int-Finish.Coverings | 19.78% | 01-Mar-11 A | 2012-02-13 | Budgeted Labor Cost | 2011-03-01: 5060; 2011-04-01: 4620; 2011-05-01: 4620; 2011-06-01: 4840; 2011-07-01: 4400; 2011-08-01: 5060; 2011-09-01: 4620; 2011-10-01: 4620; 2011-11-01: 4620; 2011-12-01: 4620; 2012-01-01: 4620; 2012-02-01: 1892
EC1310 | Fabricate and Deliver Flooring | EC00501.Int-Finish.Coverings | 19.78% | 01-Mar-11 A | 2012-02-13 | Actual Labor Units | 2011-03-01: 97; 2011-04-01: 88
EC1310 | Fabricate and Deliver Flooring | EC00501.Int-Finish.Coverings | 19.78% | 01-Mar-11 A | 2012-02-13 | Budgeted Labor Units | 2011-03-01: 92; 2011-04-01: 84; 2011-05-01: 84; 2011-06-01: 88; 2011-07-01: 80; 2011-08-01: 92; 2011-09-01: 84; 2011-10-01: 84; 2011-11-01: 84; 2011-12-01: 84; 2012-01-01: 84; 2012-02-01: 34
EC1790 | Install Floor and Carpeting | EC00501.Int-Finish.Coverings | 0% | 2012-12-03 | 2012-12-17 | Actual Labor Cost
EC1790 | Install Floor and Carpeting | EC00501.Int-Finish.Coverings | 0% | 2012-12-03 | 2012-12-17 | Budgeted Labor Cost | 2012-12-01: 3780
EC1790 | Install Floor and Carpeting | EC00501.Int-Finish.Coverings | 0% | 2012-12-03 | 2012-12-17 | Actual Labor Units
EC1790 | Install Floor and Carpeting | EC00501.Int-Finish.Coverings | 0% | 2012-12-03 | 2012-12-17 | Budgeted Labor Units | 2012-12-01: 84
EC00501.Int-Finish.Carp Carpentry |  |  | 0% | 2012-10-18 | 2013-01-03 | Actual Labor Cost
EC00501.Int-Finish.Carp Carpentry |  |  | 0% | 2012-10-18 | 2013-01-03 | Budgeted Labor Cost | 2012-10-01: 4999.32; 2012-11-01: 11256; 2012-12-01: 5628; 2013-01-01: 628.68
EC00501.Int-Finish.Carp Carpentry |  |  | 0% | 2012-10-18 | 2013-01-03 | Actual Labor Units
EC00501.Int-Finish.Carp Carpentry |  |  | 0% | 2012-10-18 | 2013-01-03 | Budgeted Labor Units | 2012-10-01: 75; 2012-11-01: 168; 2012-12-01: 84; 2013-01-01: 9
EC1740 | Install Ceiling Grid | EC00501.Int-Finish.Carp | 0% | 2012-10-18 | 2012-12-04 | Actual Labor Cost
EC1740 | Install Ceiling Grid | EC00501.Int-Finish.Carp | 0% | 2012-10-18 | 2012-12-04 | Budgeted Labor Cost | 2012-10-01: 4999.32; 2012-11-01: 11256; 2012-12-01: 628.68
EC1740 | Install Ceiling Grid | EC00501.Int-Finish.Carp | 0% | 2012-10-18 | 2012-12-04 | Actual Labor Units
EC1740 | Install Ceiling Grid | EC00501.Int-Finish.Carp | 0% | 2012-10-18 | 2012-12-04 | Budgeted Labor Units | 2012-10-01: 75; 2012-11-01: 168; 2012-12-01: 9
EC1800 | Finish Carpentry and Millwork | EC00501.Int-Finish.Carp | 0% | 2012-12-17 | 2013-01-03 | Actual Labor Cost
EC1800 | Finish Carpentry and Millwork | EC00501.Int-Finish.Carp | 0% | 2012-12-17 | 2013-01-03 | Budgeted Labor Cost | 2012-12-01: 4999.32; 2013-01-01: 628.68
EC1800 | Finish Carpentry and Millwork | EC00501.Int-Finish.Carp | 0% | 2012-12-17 | 2013-01-03 | Actual Labor Units
EC1800 | Finish Carpentry and Millwork | EC00501.Int-Finish.Carp | 0% | 2012-12-17 | 2013-01-03 | Budgeted Labor Units | 2012-12-01: 75; 2013-01-01: 9
EC00501.Int-Finish.Paint Paint |  |  | 0% | 2012-09-14 | 2012-09-28 | Actual Labor Cost
EC00501.Int-Finish.Paint Paint |  |  | 0% | 2012-09-14 | 2012-09-28 | Budgeted Labor Cost | 2012-09-01: 5880
EC00501.Int-Finish.Paint Paint |  |  | 0% | 2012-09-14 | 2012-09-28 | Actual Labor Units
EC00501.Int-Finish.Paint Paint |  |  | 0% | 2012-09-14 | 2012-09-28 | Budgeted Labor Units | 2012-09-01: 84
EC1720 | Paint Building Interior | EC00501.Int-Finish.Paint | 0% | 2012-09-14 | 2012-09-28 | Actual Labor Cost
EC1720 | Paint Building Interior | EC00501.Int-Finish.Paint | 0% | 2012-09-14 | 2012-09-28 | Budgeted Labor Cost | 2012-09-01: 5880
EC1720 | Paint Building Interior | EC00501.Int-Finish.Paint | 0% | 2012-09-14 | 2012-09-28 | Actual Labor Units
EC1720 | Paint Building Interior | EC00501.Int-Finish.Paint | 0% | 2012-09-14 | 2012-09-28 | Budgeted Labor Units | 2012-09-01: 84
EC00610 Harbour Pointe Assisted Living Center |  |  | 14.09% | 01-Sep-10 A | 2014-09-24 | Actual Labor Cost | 2010-09-01: 123526.24; 2010-10-01: 137378.08; 2010-11-01: 135492.15; 2010-12-01: 122078.91; 2011-01-01: 41743.18; 2011-02-01: 28303.03; 2011-03-01: 30723.58; 2011-04-01: 31700.86
EC00610 Harbour Pointe Assisted Living Center |  |  | 14.09% | 01-Sep-10 A | 2014-09-24 | Budgeted Labor Cost | 119507.8 | 133787.8 | 132507.8 | 118827.8 | 49374.82 | 23588.57 | 29702.86 | 30186.67 | 75535.58 | 99661.6 | 103455.2 | 76525.48 | 104398.62 | 188906.74 | 392402.53 | 340192.93 | 311589.64 | 289169.93 | 233402.98 | 248850.96 | 259217.97 | 254348.85 | 220504.6 | 243797.31 | 275807.89 | 360658.87 | 300303.67 | 251087.56 | 206723.11 | 190117.93 | 123130.03 | 137931.06 | 86600.16 | 20890.25 | 20267.35 | 7261.17 | 2987.7 | 3108.11 | 2702.7 | 2837.84 | 3108.11 | 2702.7 | 2837.84 | 2972.97 | 2972.97 | 2837.84 | 3108.11 | 2837.84 | 2342.34
EC00610 Harbour Pointe Assisted Living Center |  |  | 14.09% | 01-Sep-10 A | 2014-09-24 | Actual Labor Units | 2010-09-01: 1304; 2010-10-01: 1551; 2010-11-01: 1559; 2010-12-01: 1545; 2011-01-01: 902; 2011-02-01: 624; 2011-03-01: 671; 2011-04-01: 699
EC00610 Harbour Pointe Assisted Living Center |  |  | 14.09% | 01-Sep-10 A | 2014-09-24 | Budgeted Labor Units | 1270 | 1526 | 1534 | 1502 | 863 | 510 | 660 | 672 | 1177 | 1439 | 1404 | 1283 | 1482 | 2244 | 4159 | 3798 | 3529 | 3397 | 2950 | 3336 | 3523 | 3440 | 2993 | 3344 | 3504 | 4493 | 3789 | 3245 | 2971 | 2671 | 1628 | 1949 | 1431 | 405 | 383 | 136 | 57 | 62 | 54 | 57 | 62 | 54 | 57 | 59 | 59 | 57 | 62 | 57 | 47
EC1010 | Building Pad Delivered by Owner | EC00610 | 100% | 01-Sep-10 A |  | Actual Labor Cost
EC1010 | Building Pad Delivered by Owner | EC00610 | 100% | 01-Sep-10 A |  | Budgeted Labor Cost
EC1010 | Building Pad Delivered by Owner | EC00610 | 100% | 01-Sep-10 A |  | Actual Labor Units
EC1010 | Building Pad Delivered by Owner | EC00610 | 100% | 01-Sep-10 A |  | Budgeted Labor Units
EC2430 | Substantial Completion - All TCO | EC00610 | 0% |  | 2014-09-24 | Actual Labor Cost
EC2430 | Substantial Completion - All TCO | EC00610 | 0% |  | 2014-09-24 | Budgeted Labor Cost
EC2430 | Substantial Completion - All TCO | EC00610 | 0% |  | 2014-09-24 | Actual Labor Units
EC2430 | Substantial Completion - All TCO | EC00610 | 0% |  | 2014-09-24 | Budgeted Labor Units
EC00610.1 Building 1 |  |  | 5.53% | 01-Sep-10 A | 2014-09-24 | Actual Labor Cost | 2010-09-01: 17618.64; 2010-10-01: 17618.64; 2010-11-01: 15732.71; 2010-12-01: 6790; 2011-01-01: 8053.68; 2011-02-01: 5148.09; 2011-03-01: 6881.45; 2011-04-01: 4731.77
EC00610.1 Building 1 |  |  | 5.53% | 01-Sep-10 A | 2014-09-24 | Budgeted Labor Cost | 16800 | 16800 | 15520 | 6160 | 6440 | 4480 | 6440 | 3826.67 | 5880 | 6160 | 5600 | 8040 | 39840 | 76960 | 78578.57 | 98675.42 | 96059.63 | 87769.26 | 90180.86 | 83507.64 | 78667.46 | 77677.75 | 80884.98 | 59986.4 | 47703.55 | 64686.8 | 51188.3 | 31835.35 | 27452.02 | 36276.29 | 36367.63 | 53455.35 | 42210.35 | 577.88
EC00610.1 Building 1 |  |  | 5.53% | 01-Sep-10 A | 2014-09-24 | Actual Labor Units | 2010-09-01: 176; 2010-10-01: 176; 2010-11-01: 185; 2010-12-01: 194; 2011-01-01: 230; 2011-02-01: 147; 2011-03-01: 197; 2011-04-01: 135
EC00610.1 Building 1 |  |  | 5.53% | 01-Sep-10 A | 2014-09-24 | Budgeted Labor Units | 168 | 168 | 176 | 176 | 184 | 128 | 184 | 109 | 168 | 176 | 160 | 197 | 459 | 781 | 902 | 1285 | 1281 | 1207 | 1239 | 1146 | 1114 | 1079 | 1069 | 933 | 755 | 1034 | 806 | 473 | 397 | 468 | 475 | 792 | 701 | 10
EC2440 | Complete Building 1 | EC00610.1 | 0% |  | 2014-09-24 | Actual Labor Cost
EC2440 | Complete Building 1 | EC00610.1 | 0% |  | 2014-09-24 | Budgeted Labor Cost
EC2440 | Complete Building 1 | EC00610.1 | 0% |  | 2014-09-24 | Actual Labor Units
EC2440 | Complete Building 1 | EC00610.1 | 0% |  | 2014-09-24 | Budgeted Labor Units
EC00610.1.1 Structure |  |  | 76.45% | 01-Sep-10 A | 2011-09-21 | Actual Labor Cost | 2010-09-01: 17618.64; 2010-10-01: 17618.64; 2010-11-01: 15732.71; 2010-12-01: 6790; 2011-01-01: 8053.68; 2011-02-01: 5148.09; 2011-03-01: 6881.45; 2011-04-01: 4731.77
EC00610.1.1 Structure |  |  | 76.45% | 01-Sep-10 A | 2011-09-21 | Budgeted Labor Cost | 2010-09-01: 16800; 2010-10-01: 16800; 2010-11-01: 15520; 2010-12-01: 6160; 2011-01-01: 6440; 2011-02-01: 4480; 2011-03-01: 6440; 2011-04-01: 3826.67; 2011-05-01: 5880; 2011-06-01: 6160; 2011-07-01: 5600; 2011-08-01: 6440; 2011-09-01: 3733.33
EC00610.1.1 Structure |  |  | 76.45% | 01-Sep-10 A | 2011-09-21 | Actual Labor Units | 2010-09-01: 176; 2010-10-01: 176; 2010-11-01: 185; 2010-12-01: 194; 2011-01-01: 230; 2011-02-01: 147; 2011-03-01: 197; 2011-04-01: 135
EC00610.1.1 Structure |  |  | 76.45% | 01-Sep-10 A | 2011-09-21 | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 176; 2010-12-01: 176; 2011-01-01: 184; 2011-02-01: 128; 2011-03-01: 184; 2011-04-01: 109; 2011-05-01: 168; 2011-06-01: 176; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 107
EC1090 | Building Pad Including UG Utils | EC00610.1.1 | 100% | 01-Sep-10 A | 23-Nov-10 A | Actual Labor Cost | 2010-09-01: 17618.64; 2010-10-01: 17618.64; 2010-11-01: 14262.71
EC1090 | Building Pad Including UG Utils | EC00610.1.1 | 100% | 01-Sep-10 A | 23-Nov-10 A | Budgeted Labor Cost | 2010-09-01: 16800; 2010-10-01: 16800; 2010-11-01: 14400
EC1090 | Building Pad Including UG Utils | EC00610.1.1 | 100% | 01-Sep-10 A | 23-Nov-10 A | Actual Labor Units | 2010-09-01: 176; 2010-10-01: 176; 2010-11-01: 143
EC1090 | Building Pad Including UG Utils | EC00610.1.1 | 100% | 01-Sep-10 A | 23-Nov-10 A | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 144
EC1140 | First Floor Masonry Structure | EC00610.1.1 | 100% | 24-Nov-10 A | 13-Dec-10 A | Actual Labor Cost | 2010-11-01: 1470; 2010-12-01: 2940
EC1140 | First Floor Masonry Structure | EC00610.1.1 | 100% | 24-Nov-10 A | 13-Dec-10 A | Budgeted Labor Cost | 2010-11-01: 1120; 2010-12-01: 3080
EC1140 | First Floor Masonry Structure | EC00610.1.1 | 100% | 24-Nov-10 A | 13-Dec-10 A | Actual Labor Units | 2010-11-01: 42; 2010-12-01: 84
EC1140 | First Floor Masonry Structure | EC00610.1.1 | 100% | 24-Nov-10 A | 13-Dec-10 A | Budgeted Labor Units | 2010-11-01: 32; 2010-12-01: 88
EC1170 | Second Floor Slab & Collar Beam | EC00610.1.1 | 100% | 15-Dec-10 A | 31-Jan-11 A | Actual Labor Cost | 2010-12-01: 3850; 2011-01-01: 7000
EC1170 | Second Floor Slab & Collar Beam | EC00610.1.1 | 100% | 15-Dec-10 A | 31-Jan-11 A | Budgeted Labor Cost | 2010-12-01: 3080; 2011-01-01: 5320
EC1170 | Second Floor Slab & Collar Beam | EC00610.1.1 | 100% | 15-Dec-10 A | 31-Jan-11 A | Actual Labor Units | 2010-12-01: 110; 2011-01-01: 200
EC1170 | Second Floor Slab & Collar Beam | EC00610.1.1 | 100% | 15-Dec-10 A | 31-Jan-11 A | Budgeted Labor Units | 2010-12-01: 88; 2011-01-01: 152
EC1190 | Second Floor Masonry Structure | EC00610.1.1 | 100% | 26-Jan-11 A | 22-Feb-11 A | Actual Labor Cost | 2011-01-01: 1053.68; 2011-02-01: 3951.32
EC1190 | Second Floor Masonry Structure | EC00610.1.1 | 100% | 26-Jan-11 A | 22-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 1120; 2011-02-01: 3080
EC1190 | Second Floor Masonry Structure | EC00610.1.1 | 100% | 26-Jan-11 A | 22-Feb-11 A | Actual Labor Units | 2011-01-01: 30; 2011-02-01: 113
EC1190 | Second Floor Masonry Structure | EC00610.1.1 | 100% | 26-Jan-11 A | 22-Feb-11 A | Budgeted Labor Units | 2011-01-01: 32; 2011-02-01: 88
EC1210 | Third Floor Slab & Collar Beam | EC00610.1.1 | 100% | 23-Feb-11 A | 07-Apr-11 A | Actual Labor Cost | 2011-02-01: 1196.77; 2011-03-01: 6881.45; 2011-04-01: 1196.77
EC1210 | Third Floor Slab & Collar Beam | EC00610.1.1 | 100% | 23-Feb-11 A | 07-Apr-11 A | Budgeted Labor Cost | 2011-02-01: 1400; 2011-03-01: 6440; 2011-04-01: 560
EC1210 | Third Floor Slab & Collar Beam | EC00610.1.1 | 100% | 23-Feb-11 A | 07-Apr-11 A | Actual Labor Units | 2011-02-01: 34; 2011-03-01: 197; 2011-04-01: 34
EC1210 | Third Floor Slab & Collar Beam | EC00610.1.1 | 100% | 23-Feb-11 A | 07-Apr-11 A | Budgeted Labor Units | 2011-02-01: 40; 2011-03-01: 184; 2011-04-01: 16
EC1240 | Third Floor Masonry Structure | EC00610.1.1 | 100% | 12-Apr-11 A | 2011-05-05 | Actual Labor Cost | 2011-04-01: 3535
EC1240 | Third Floor Masonry Structure | EC00610.1.1 | 100% | 12-Apr-11 A | 2011-05-05 | Budgeted Labor Cost | 2011-04-01: 3266.67; 2011-05-01: 933.33
EC1240 | Third Floor Masonry Structure | EC00610.1.1 | 100% | 12-Apr-11 A | 2011-05-05 | Actual Labor Units | 2011-04-01: 101
EC1240 | Third Floor Masonry Structure | EC00610.1.1 | 100% | 12-Apr-11 A | 2011-05-05 | Budgeted Labor Units | 2011-04-01: 93; 2011-05-01: 27
EC1250 | Fourth Floor Slab & Collar Beam | EC00610.1.1 | 27.59% | 2011-05-05 | 2011-06-17 | Actual Labor Cost
EC1250 | Fourth Floor Slab & Collar Beam | EC00610.1.1 | 27.59% | 2011-05-05 | 2011-06-17 | Budgeted Labor Cost | 2011-05-01: 4946.67; 2011-06-01: 3453.33
EC1250 | Fourth Floor Slab & Collar Beam | EC00610.1.1 | 27.59% | 2011-05-05 | 2011-06-17 | Actual Labor Units
EC1250 | Fourth Floor Slab & Collar Beam | EC00610.1.1 | 27.59% | 2011-05-05 | 2011-06-17 | Budgeted Labor Units | 2011-05-01: 141; 2011-06-01: 99
EC1300 | Fourth Floor Masonry Structure | EC00610.1.1 | 0% | 2011-06-17 | 2011-07-11 | Actual Labor Cost
EC1300 | Fourth Floor Masonry Structure | EC00610.1.1 | 0% | 2011-06-17 | 2011-07-11 | Budgeted Labor Cost | 2011-06-01: 2706.67; 2011-07-01: 1493.33
EC1300 | Fourth Floor Masonry Structure | EC00610.1.1 | 0% | 2011-06-17 | 2011-07-11 | Actual Labor Units
EC1300 | Fourth Floor Masonry Structure | EC00610.1.1 | 0% | 2011-06-17 | 2011-07-11 | Budgeted Labor Units | 2011-06-01: 77; 2011-07-01: 43
EC1310 | Roof Slab | EC00610.1.1 | 0% | 2011-07-11 | 2011-08-22 | Actual Labor Cost
EC1310 | Roof Slab | EC00610.1.1 | 0% | 2011-07-11 | 2011-08-22 | Budgeted Labor Cost | 2011-07-01: 4106.67; 2011-08-01: 4293.33
EC1310 | Roof Slab | EC00610.1.1 | 0% | 2011-07-11 | 2011-08-22 | Actual Labor Units
EC1310 | Roof Slab | EC00610.1.1 | 0% | 2011-07-11 | 2011-08-22 | Budgeted Labor Units | 2011-07-01: 117; 2011-08-01: 123
EC1340 | Stair and Elevator Masonry Structure | EC00610.1.1 | 0% | 2011-08-22 | 2011-08-30 | Actual Labor Cost
EC1340 | Stair and Elevator Masonry Structure | EC00610.1.1 | 0% | 2011-08-22 | 2011-08-30 | Budgeted Labor Cost | 2011-08-01: 1680
EC1340 | Stair and Elevator Masonry Structure | EC00610.1.1 | 0% | 2011-08-22 | 2011-08-30 | Actual Labor Units
EC1340 | Stair and Elevator Masonry Structure | EC00610.1.1 | 0% | 2011-08-22 | 2011-08-30 | Budgeted Labor Units | 2011-08-01: 48
EC1350 | Roof Slab/Collar Beam | EC00610.1.1 | 0% | 2011-08-30 | 2011-09-21 | Actual Labor Cost
EC1350 | Roof Slab/Collar Beam | EC00610.1.1 | 0% | 2011-08-30 | 2011-09-21 | Budgeted Labor Cost | 2011-08-01: 466.67; 2011-09-01: 3733.33
EC1350 | Roof Slab/Collar Beam | EC00610.1.1 | 0% | 2011-08-30 | 2011-09-21 | Actual Labor Units
EC1350 | Roof Slab/Collar Beam | EC00610.1.1 | 0% | 2011-08-30 | 2011-09-21 | Budgeted Labor Units | 2011-08-01: 13; 2011-09-01: 107
EC00610.1.2 Roof |  |  | 0% | 2011-09-21 | 2012-01-25 | Actual Labor Cost
EC00610.1.2 Roof |  |  | 0% | 2011-09-21 | 2012-01-25 | Budgeted Labor Cost | 2011-09-01: 15946.67; 2011-10-01: 43680; 2011-11-01: 26373.33; 2011-12-01: 25200; 2012-01-01: 10600
EC00610.1.2 Roof |  |  | 0% | 2011-09-21 | 2012-01-25 | Actual Labor Units
EC00610.1.2 Roof |  |  | 0% | 2011-09-21 | 2012-01-25 | Budgeted Labor Units | 2011-09-01: 184; 2011-10-01: 504; 2011-11-01: 347; 2011-12-01: 336; 2012-01-01: 141
EC1390 | Place Roof Trusses and Sheathing | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Actual Labor Cost
EC1390 | Place Roof Trusses and Sheathing | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Budgeted Labor Cost | 2011-09-01: 11346.67; 2011-10-01: 31080; 2011-11-01: 1973.33
EC1390 | Place Roof Trusses and Sheathing | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Actual Labor Units
EC1390 | Place Roof Trusses and Sheathing | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Budgeted Labor Units | 2011-09-01: 123; 2011-10-01: 336; 2011-11-01: 21
EC1400 | Place Mechanical Equipment Supports | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Actual Labor Cost
EC1400 | Place Mechanical Equipment Supports | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Budgeted Labor Cost | 2011-09-01: 4600; 2011-10-01: 12600; 2011-11-01: 800
EC1400 | Place Mechanical Equipment Supports | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Actual Labor Units
EC1400 | Place Mechanical Equipment Supports | EC00610.1.2 | 0% | 2011-09-21 | 2011-11-02 | Budgeted Labor Units | 2011-09-01: 61; 2011-10-01: 168; 2011-11-01: 11
EC1530 | Built-Up Asphalt Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-04 | Actual Labor Cost
EC1530 | Built-Up Asphalt Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-04 | Budgeted Labor Cost | 2011-11-01: 11800; 2011-12-01: 12600; 2012-01-01: 800
EC1530 | Built-Up Asphalt Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-04 | Actual Labor Units
EC1530 | Built-Up Asphalt Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-04 | Budgeted Labor Units | 2011-11-01: 157; 2011-12-01: 168; 2012-01-01: 11
EC1540 | Felt and Tile Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-25 | Actual Labor Cost
EC1540 | Felt and Tile Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-25 | Budgeted Labor Cost | 2011-11-01: 11800; 2011-12-01: 12600; 2012-01-01: 9800
EC1540 | Felt and Tile Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-25 | Actual Labor Units
EC1540 | Felt and Tile Roofing | EC00610.1.2 | 0% | 2011-11-02 | 2012-01-25 | Budgeted Labor Units | 2011-11-01: 157; 2011-12-01: 168; 2012-01-01: 131
EC1780 | Roof Complete | EC00610.1.2 | 0% |  | 2012-01-25 | Actual Labor Cost
EC1780 | Roof Complete | EC00610.1.2 | 0% |  | 2012-01-25 | Budgeted Labor Cost
EC1780 | Roof Complete | EC00610.1.2 | 0% |  | 2012-01-25 | Actual Labor Units
EC1780 | Roof Complete | EC00610.1.2 | 0% |  | 2012-01-25 | Budgeted Labor Units
EC00610.1.3 Envelope |  |  | 0% | 2011-08-30 | 2012-08-03 | Actual Labor Cost
EC00610.1.3 Envelope |  |  | 0% | 2011-08-30 | 2012-08-03 | Budgeted Labor Cost | 2011-08-01: 1600; 2011-09-01: 20160; 2011-10-01: 33280; 2011-11-01: 38400; 2011-12-01: 34880; 2012-01-01: 33600; 2012-02-01: 20160; 2012-03-01: 21120; 2012-04-01: 20160; 2012-05-01: 16693.33; 2012-06-01: 34586.67; 2012-07-01: 28160; 2012-08-01: 2240
EC00610.1.3 Envelope |  |  | 0% | 2011-08-30 | 2012-08-03 | Actual Labor Units
EC00610.1.3 Envelope |  |  | 0% | 2011-08-30 | 2012-08-03 | Budgeted Labor Units | 2011-08-01: 13; 2011-09-01: 168; 2011-10-01: 277; 2011-11-01: 320; 2011-12-01: 291; 2012-01-01: 280; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 168; 2012-05-01: 141; 2012-06-01: 336; 2012-07-01: 235; 2012-08-01: 19
EC1360 | Mobilize Scaffolding | EC00610.1.3 | 0% | 2011-08-30 | 2011-09-21 | Actual Labor Cost
EC1360 | Mobilize Scaffolding | EC00610.1.3 | 0% | 2011-08-30 | 2011-09-21 | Budgeted Labor Cost | 2011-08-01: 1600; 2011-09-01: 12800
EC1360 | Mobilize Scaffolding | EC00610.1.3 | 0% | 2011-08-30 | 2011-09-21 | Actual Labor Units
EC1360 | Mobilize Scaffolding | EC00610.1.3 | 0% | 2011-08-30 | 2011-09-21 | Budgeted Labor Units | 2011-08-01: 13; 2011-09-01: 107
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.1.3 | 0% | 2011-09-21 | 2011-10-25 | Actual Labor Cost
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.1.3 | 0% | 2011-09-21 | 2011-10-25 | Budgeted Labor Cost | 2011-09-01: 7360; 2011-10-01: 15680
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.1.3 | 0% | 2011-09-21 | 2011-10-25 | Actual Labor Units
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.1.3 | 0% | 2011-09-21 | 2011-10-25 | Budgeted Labor Units | 2011-09-01: 61; 2011-10-01: 131
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.1.3 | 0% | 2011-10-18 | 2011-11-21 | Actual Labor Cost
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.1.3 | 0% | 2011-10-18 | 2011-11-21 | Budgeted Labor Cost | 2011-10-01: 9280; 2011-11-01: 13760
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.1.3 | 0% | 2011-10-18 | 2011-11-21 | Actual Labor Units
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.1.3 | 0% | 2011-10-18 | 2011-11-21 | Budgeted Labor Units | 2011-10-01: 77; 2011-11-01: 115
EC1490 | Install Backing & Cauld Windows Floor1 | EC00610.1.3 | 0% | 2011-10-19 | 2011-11-04 | Actual Labor Cost
EC1490 | Install Backing & Cauld Windows Floor1 | EC00610.1.3 | 0% | 2011-10-19 | 2011-11-04 | Budgeted Labor Cost | 2011-10-01: 8320; 2011-11-01: 3200
EC1490 | Install Backing & Cauld Windows Floor1 | EC00610.1.3 | 0% | 2011-10-19 | 2011-11-04 | Actual Labor Units
EC1490 | Install Backing & Cauld Windows Floor1 | EC00610.1.3 | 0% | 2011-10-19 | 2011-11-04 | Budgeted Labor Units | 2011-10-01: 69; 2011-11-01: 27
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.1.3 | 0% | 2011-11-14 | 2011-12-14 | Actual Labor Cost
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.1.3 | 0% | 2011-11-14 | 2011-12-14 | Budgeted Labor Cost | 2011-11-01: 11200; 2011-12-01: 8960
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.1.3 | 0% | 2011-11-14 | 2011-12-14 | Actual Labor Units
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.1.3 | 0% | 2011-11-14 | 2011-12-14 | Budgeted Labor Units | 2011-11-01: 93; 2011-12-01: 75
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00610.1.3 | 0% | 2011-11-15 | 2011-12-02 | Actual Labor Cost
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00610.1.3 | 0% | 2011-11-15 | 2011-12-02 | Budgeted Labor Cost | 2011-11-01: 10240; 2011-12-01: 1280
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00610.1.3 | 0% | 2011-11-15 | 2011-12-02 | Actual Labor Units
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00610.1.3 | 0% | 2011-11-15 | 2011-12-02 | Budgeted Labor Units | 2011-11-01: 85; 2011-12-01: 11
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.1.3 | 0% | 2011-12-07 | 2012-01-17 | Actual Labor Cost
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.1.3 | 0% | 2011-12-07 | 2012-01-17 | Budgeted Labor Cost | 2011-12-01: 16000; 2012-01-01: 9920
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.1.3 | 0% | 2011-12-07 | 2012-01-17 | Actual Labor Units
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.1.3 | 0% | 2011-12-07 | 2012-01-17 | Budgeted Labor Units | 2011-12-01: 133; 2012-01-01: 83
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00610.1.3 | 0% | 2011-12-08 | 2011-12-21 | Actual Labor Cost
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00610.1.3 | 0% | 2011-12-08 | 2011-12-21 | Budgeted Labor Cost | 2011-12-01: 8640
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00610.1.3 | 0% | 2011-12-08 | 2011-12-21 | Actual Labor Units
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00610.1.3 | 0% | 2011-12-08 | 2011-12-21 | Budgeted Labor Units | 2011-12-01: 72
EC1580 | Stucco Bands | EC00610.1.3 | 0% | 2012-01-13 | 2012-01-31 | Actual Labor Cost
EC1580 | Stucco Bands | EC00610.1.3 | 0% | 2012-01-13 | 2012-01-31 | Budgeted Labor Cost | 2012-01-01: 11520
EC1580 | Stucco Bands | EC00610.1.3 | 0% | 2012-01-13 | 2012-01-31 | Actual Labor Units
EC1580 | Stucco Bands | EC00610.1.3 | 0% | 2012-01-13 | 2012-01-31 | Budgeted Labor Units | 2012-01-01: 96
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00610.1.3 | 0% | 2012-01-11 | 2012-01-27 | Actual Labor Cost
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00610.1.3 | 0% | 2012-01-11 | 2012-01-27 | Budgeted Labor Cost | 2012-01-01: 11520
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00610.1.3 | 0% | 2012-01-11 | 2012-01-27 | Actual Labor Units
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00610.1.3 | 0% | 2012-01-11 | 2012-01-27 | Budgeted Labor Units | 2012-01-01: 96
EC1660 | Stucco Grey | EC00610.1.3 | 0% | 2012-01-31 | 2012-03-05 | Actual Labor Cost
EC1660 | Stucco Grey | EC00610.1.3 | 0% | 2012-01-31 | 2012-03-05 | Budgeted Labor Cost | 2012-01-01: 640; 2012-02-01: 20160; 2012-03-01: 2240
EC1660 | Stucco Grey | EC00610.1.3 | 0% | 2012-01-31 | 2012-03-05 | Actual Labor Units
EC1660 | Stucco Grey | EC00610.1.3 | 0% | 2012-01-31 | 2012-03-05 | Budgeted Labor Units | 2012-01-01: 5; 2012-02-01: 168; 2012-03-01: 19
EC1690 | Stucco Finish Coat | EC00610.1.3 | 0% | 2012-03-05 | 2012-04-16 | Actual Labor Cost
EC1690 | Stucco Finish Coat | EC00610.1.3 | 0% | 2012-03-05 | 2012-04-16 | Budgeted Labor Cost | 2012-03-01: 18880; 2012-04-01: 9920
EC1690 | Stucco Finish Coat | EC00610.1.3 | 0% | 2012-03-05 | 2012-04-16 | Actual Labor Units
EC1690 | Stucco Finish Coat | EC00610.1.3 | 0% | 2012-03-05 | 2012-04-16 | Budgeted Labor Units | 2012-03-01: 157; 2012-04-01: 83
EC1840 | Caulk | EC00610.1.3 | 0% | 2012-04-16 | 2012-05-02 | Actual Labor Cost
EC1840 | Caulk | EC00610.1.3 | 0% | 2012-04-16 | 2012-05-02 | Budgeted Labor Cost | 2012-04-01: 10240; 2012-05-01: 1280
EC1840 | Caulk | EC00610.1.3 | 0% | 2012-04-16 | 2012-05-02 | Actual Labor Units
EC1840 | Caulk | EC00610.1.3 | 0% | 2012-04-16 | 2012-05-02 | Budgeted Labor Units | 2012-04-01: 85; 2012-05-01: 11
EC1900 | Stucco Band Trim | EC00610.1.3 | 0% | 2012-05-02 | 2012-05-23 | Actual Labor Cost
EC1900 | Stucco Band Trim | EC00610.1.3 | 0% | 2012-05-02 | 2012-05-23 | Budgeted Labor Cost | 2012-05-01: 14400
EC1900 | Stucco Band Trim | EC00610.1.3 | 0% | 2012-05-02 | 2012-05-23 | Actual Labor Units
EC1900 | Stucco Band Trim | EC00610.1.3 | 0% | 2012-05-02 | 2012-05-23 | Budgeted Labor Units | 2012-05-01: 120
EC1980 | Paint Exterior | EC00610.1.3 | 0% | 2012-05-31 | 2012-06-21 | Actual Labor Cost
EC1980 | Paint Exterior | EC00610.1.3 | 0% | 2012-05-31 | 2012-06-21 | Budgeted Labor Cost | 2012-05-01: 373.33; 2012-06-01: 8026.67
EC1980 | Paint Exterior | EC00610.1.3 | 0% | 2012-05-31 | 2012-06-21 | Actual Labor Units
EC1980 | Paint Exterior | EC00610.1.3 | 0% | 2012-05-31 | 2012-06-21 | Budgeted Labor Units | 2012-05-01: 5; 2012-06-01: 115
EC1990 | Install Railings | EC00610.1.3 | 0% | 2012-05-31 | 2012-08-03 | Actual Labor Cost
EC1990 | Install Railings | EC00610.1.3 | 0% | 2012-05-31 | 2012-08-03 | Budgeted Labor Cost | 2012-05-01: 640; 2012-06-01: 20160; 2012-07-01: 20160; 2012-08-01: 2240
EC1990 | Install Railings | EC00610.1.3 | 0% | 2012-05-31 | 2012-08-03 | Actual Labor Units
EC1990 | Install Railings | EC00610.1.3 | 0% | 2012-05-31 | 2012-08-03 | Budgeted Labor Units | 2012-05-01: 5; 2012-06-01: 168; 2012-07-01: 168; 2012-08-01: 19
EC2110 | Demobilize Scaffolding | EC00610.1.3 | 0% | 2012-06-21 | 2012-07-13 | Actual Labor Cost
EC2110 | Demobilize Scaffolding | EC00610.1.3 | 0% | 2012-06-21 | 2012-07-13 | Budgeted Labor Cost | 2012-06-01: 6400; 2012-07-01: 8000
EC2110 | Demobilize Scaffolding | EC00610.1.3 | 0% | 2012-06-21 | 2012-07-13 | Actual Labor Units
EC2110 | Demobilize Scaffolding | EC00610.1.3 | 0% | 2012-06-21 | 2012-07-13 | Budgeted Labor Units | 2012-06-01: 53; 2012-07-01: 67
EC2140 | Shell Complete | EC00610.1.3 | 0% |  | 2012-08-03 | Actual Labor Cost
EC2140 | Shell Complete | EC00610.1.3 | 0% |  | 2012-08-03 | Budgeted Labor Cost
EC2140 | Shell Complete | EC00610.1.3 | 0% |  | 2012-08-03 | Actual Labor Units
EC2140 | Shell Complete | EC00610.1.3 | 0% |  | 2012-08-03 | Budgeted Labor Units
EC00610.1.4 Interior Finishes |  |  | 0% | 2011-11-02 | 2013-06-03 | Actual Labor Cost
EC00610.1.4 Interior Finishes |  |  | 0% | 2011-11-02 | 2013-06-03 | Budgeted Labor Cost | 2011-11-01: 13805.24; 2011-12-01: 38595.42; 2012-01-01: 51859.63; 2012-02-01: 67609.26; 2012-03-01: 69060.86; 2012-04-01: 63347.64; 2012-05-01: 61974.13; 2012-06-01: 42260.57; 2012-07-01: 42260.57; 2012-08-01: 46285.39; 2012-09-01: 38235.75; 2012-10-01: 53225.78; 2012-11-01: 40723.9; 2012-12-01: 21869.25; 2013-01-01: 16489.31; 2013-02-01: 14830.19; 2013-03-01: 15571.7; 2013-04-01: 34975.35; 2013-05-01: 36890.35; 2013-06-01: 577.88
EC00610.1.4 Interior Finishes |  |  | 0% | 2011-11-02 | 2013-06-03 | Actual Labor Units
EC00610.1.4 Interior Finishes |  |  | 0% | 2011-11-02 | 2013-06-03 | Budgeted Labor Units | 2011-11-01: 235; 2011-12-01: 658; 2012-01-01: 859; 2012-02-01: 1039; 2012-03-01: 1063; 2012-04-01: 978; 2012-05-01: 972; 2012-06-01: 735; 2012-07-01: 735; 2012-08-01: 805; 2012-09-01: 665; 2012-10-01: 925; 2012-11-01: 706; 2012-12-01: 378; 2013-01-01: 293; 2013-02-01: 264; 2013-03-01: 277; 2013-04-01: 616; 2013-05-01: 650; 2013-06-01: 10
EC1550 | Unit Finishes Building North - Floor 1 | EC00610.1.4 | 0% | 2011-11-02 | 2012-10-19 | Actual Labor Cost
EC1550 | Unit Finishes Building North - Floor 1 | EC00610.1.4 | 0% | 2011-11-02 | 2012-10-19 | Budgeted Labor Cost | 2011-11-01: 5619.17; 2011-12-01: 6000.13; 2012-01-01: 6000.13; 2012-02-01: 5979.64; 2012-03-01: 5609.76; 2012-04-01: 5354.77; 2012-05-01: 5609.76; 2012-06-01: 5354.77; 2012-07-01: 5354.77; 2012-08-01: 5864.74; 2012-09-01: 4844.79; 2012-10-01: 3654.84
EC1550 | Unit Finishes Building North - Floor 1 | EC00610.1.4 | 0% | 2011-11-02 | 2012-10-19 | Actual Labor Units
EC1550 | Unit Finishes Building North - Floor 1 | EC00610.1.4 | 0% | 2011-11-02 | 2012-10-19 | Budgeted Labor Units | 2011-11-01: 96; 2011-12-01: 102; 2012-01-01: 102; 2012-02-01: 102; 2012-03-01: 98; 2012-04-01: 93; 2012-05-01: 98; 2012-06-01: 93; 2012-07-01: 93; 2012-08-01: 102; 2012-09-01: 84; 2012-10-01: 64
EC1630 | Unit Finishes Building South - Floor 1 | EC00610.1.4 | 0% | 2011-11-09 | 2012-10-31 | Actual Labor Cost
EC1630 | Unit Finishes Building South - Floor 1 | EC00610.1.4 | 0% | 2011-11-09 | 2012-10-31 | Budgeted Labor Cost | 2011-11-01: 4140.08; 2011-12-01: 5927.84; 2012-01-01: 5927.84; 2012-02-01: 5927.84; 2012-03-01: 5704.1; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 5290.25; 2012-08-01: 5794.09; 2012-09-01: 4786.42; 2012-10-01: 5626.14
EC1630 | Unit Finishes Building South - Floor 1 | EC00610.1.4 | 0% | 2011-11-09 | 2012-10-31 | Actual Labor Units
EC1630 | Unit Finishes Building South - Floor 1 | EC00610.1.4 | 0% | 2011-11-09 | 2012-10-31 | Budgeted Labor Units | 2011-11-01: 71; 2011-12-01: 101; 2012-01-01: 101; 2012-02-01: 101; 2012-03-01: 99; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 98
EC1670 | Unit Finishes Building North - Floor 2 | EC00610.1.4 | 0% | 2011-11-16 | 2012-11-07 | Actual Labor Cost
EC1670 | Unit Finishes Building North - Floor 2 | EC00610.1.4 | 0% | 2011-11-16 | 2012-11-07 | Budgeted Labor Cost | 2011-11-01: 2728.69; 2011-12-01: 5927.84; 2012-01-01: 5927.84; 2012-02-01: 5927.84; 2012-03-01: 5855.9; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 5290.25; 2012-08-01: 5794.09; 2012-09-01: 4786.42; 2012-10-01: 5794.09; 2012-11-01: 1091.64
EC1670 | Unit Finishes Building North - Floor 2 | EC00610.1.4 | 0% | 2011-11-16 | 2012-11-07 | Actual Labor Units
EC1670 | Unit Finishes Building North - Floor 2 | EC00610.1.4 | 0% | 2011-11-16 | 2012-11-07 | Budgeted Labor Units | 2011-11-01: 47; 2011-12-01: 101; 2012-01-01: 101; 2012-02-01: 101; 2012-03-01: 101; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 101; 2012-11-01: 19
EC1700 | Unit Finishes Building South - Floor 2 | EC00610.1.4 | 0% | 2011-11-23 | 2012-11-14 | Actual Labor Cost
EC1700 | Unit Finishes Building South - Floor 2 | EC00610.1.4 | 0% | 2011-11-23 | 2012-11-14 | Budgeted Labor Cost | 2011-11-01: 1317.3; 2011-12-01: 5927.84; 2012-01-01: 5927.84; 2012-02-01: 5927.84; 2012-03-01: 6007.71; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 5290.25; 2012-08-01: 5794.09; 2012-09-01: 4786.42; 2012-10-01: 5794.09; 2012-11-01: 2351.23
EC1700 | Unit Finishes Building South - Floor 2 | EC00610.1.4 | 0% | 2011-11-23 | 2012-11-14 | Actual Labor Units
EC1700 | Unit Finishes Building South - Floor 2 | EC00610.1.4 | 0% | 2011-11-23 | 2012-11-14 | Budgeted Labor Units | 2011-11-01: 22; 2011-12-01: 101; 2012-01-01: 101; 2012-02-01: 101; 2012-03-01: 103; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 101; 2012-11-01: 41
EC1790 | Unit Finishes Building North - Floor 3 | EC00610.1.4 | 0% | 2011-12-01 | 2012-11-21 | Actual Labor Cost
EC1790 | Unit Finishes Building North - Floor 3 | EC00610.1.4 | 0% | 2011-12-01 | 2012-11-21 | Budgeted Labor Cost | 2011-12-01: 5833.75; 2012-01-01: 5927.84; 2012-02-01: 5927.84; 2012-03-01: 6159.52; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 5290.25; 2012-08-01: 5794.09; 2012-09-01: 4786.42; 2012-10-01: 5794.09; 2012-11-01: 3610.81
EC1790 | Unit Finishes Building North - Floor 3 | EC00610.1.4 | 0% | 2011-12-01 | 2012-11-21 | Actual Labor Units
EC1790 | Unit Finishes Building North - Floor 3 | EC00610.1.4 | 0% | 2011-12-01 | 2012-11-21 | Budgeted Labor Units | 2011-12-01: 100; 2012-01-01: 101; 2012-02-01: 101; 2012-03-01: 105; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 101; 2012-11-01: 63
EC1820 | Building 2 Elevators Complete | EC00610.1.4 | 0% | 2012-01-25 | 2012-05-25 | Actual Labor Cost
EC1820 | Building 2 Elevators Complete | EC00610.1.4 | 0% | 2012-01-25 | 2012-05-25 | Budgeted Labor Cost | 2012-01-01: 4505.75; 2012-02-01: 20275.86; 2012-03-01: 21241.38; 2012-04-01: 20275.86; 2012-05-01: 17701.15
EC1820 | Building 2 Elevators Complete | EC00610.1.4 | 0% | 2012-01-25 | 2012-05-25 | Actual Labor Units
EC1820 | Building 2 Elevators Complete | EC00610.1.4 | 0% | 2012-01-25 | 2012-05-25 | Budgeted Labor Units | 2012-01-01: 51; 2012-02-01: 232; 2012-03-01: 243; 2012-04-01: 232; 2012-05-01: 202
EC1850 | Unit Finishes Building South - Floor 3 | EC00610.1.4 | 0% | 2011-12-08 | 2012-11-29 | Actual Labor Cost
EC1850 | Unit Finishes Building South - Floor 3 | EC00610.1.4 | 0% | 2011-12-08 | 2012-11-29 | Budgeted Labor Cost | 2011-12-01: 4422.36; 2012-01-01: 5927.84; 2012-02-01: 5927.84; 2012-03-01: 6210.12; 2012-04-01: 5391.46; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 5290.25; 2012-08-01: 5794.09; 2012-09-01: 4786.42; 2012-10-01: 5794.09; 2012-11-01: 4870.39
EC1850 | Unit Finishes Building South - Floor 3 | EC00610.1.4 | 0% | 2011-12-08 | 2012-11-29 | Actual Labor Units
EC1850 | Unit Finishes Building South - Floor 3 | EC00610.1.4 | 0% | 2011-12-08 | 2012-11-29 | Budgeted Labor Units | 2011-12-01: 75; 2012-01-01: 101; 2012-02-01: 101; 2012-03-01: 106; 2012-04-01: 93; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 101; 2012-11-01: 85
EC1910 | Unit Finishes Building North - Floor 4 | EC00610.1.4 | 0% | 2011-12-15 | 2012-12-11 | Actual Labor Cost
EC1910 | Unit Finishes Building North - Floor 4 | EC00610.1.4 | 0% | 2011-12-15 | 2012-12-11 | Budgeted Labor Cost | 2011-12-01: 2975.12; 2012-01-01: 5857.27; 2012-02-01: 5857.27; 2012-03-01: 6136.19; 2012-04-01: 5507.27; 2012-05-01: 5476.19; 2012-06-01: 5227.27; 2012-07-01: 5227.27; 2012-08-01: 5725.11; 2012-09-01: 4729.44; 2012-10-01: 5725.11; 2012-11-01: 5227.27; 2012-12-01: 1576.48
EC1910 | Unit Finishes Building North - Floor 4 | EC00610.1.4 | 0% | 2011-12-15 | 2012-12-11 | Actual Labor Units
EC1910 | Unit Finishes Building North - Floor 4 | EC00610.1.4 | 0% | 2011-12-15 | 2012-12-11 | Budgeted Labor Units | 2011-12-01: 51; 2012-01-01: 100; 2012-02-01: 100; 2012-03-01: 105; 2012-04-01: 95; 2012-05-01: 95; 2012-06-01: 91; 2012-07-01: 91; 2012-08-01: 100; 2012-09-01: 82; 2012-10-01: 100; 2012-11-01: 91; 2012-12-01: 27
EC1950 | Unit Finishes Building South - Floor 4 | EC00610.1.4 | 0% | 2011-12-22 | 2012-12-18 | Actual Labor Cost
EC1950 | Unit Finishes Building South - Floor 4 | EC00610.1.4 | 0% | 2011-12-22 | 2012-12-18 | Budgeted Labor Cost | 2011-12-01: 1580.53; 2012-01-01: 5857.27; 2012-02-01: 5857.27; 2012-03-01: 6136.19; 2012-04-01: 5657.27; 2012-05-01: 5476.19; 2012-06-01: 5227.27; 2012-07-01: 5227.27; 2012-08-01: 5725.11; 2012-09-01: 4729.44; 2012-10-01: 5725.11; 2012-11-01: 5227.27; 2012-12-01: 2821.07
EC1950 | Unit Finishes Building South - Floor 4 | EC00610.1.4 | 0% | 2011-12-22 | 2012-12-18 | Actual Labor Units
EC1950 | Unit Finishes Building South - Floor 4 | EC00610.1.4 | 0% | 2011-12-22 | 2012-12-18 | Budgeted Labor Units | 2011-12-01: 27; 2012-01-01: 100; 2012-02-01: 100; 2012-03-01: 105; 2012-04-01: 97; 2012-05-01: 95; 2012-06-01: 91; 2012-07-01: 91; 2012-08-01: 100; 2012-09-01: 82; 2012-10-01: 100; 2012-11-01: 91; 2012-12-01: 49
EC2240 | Tenant Finishes for Clubhouse Areas | EC00610.1.4 | 0% | 2012-10-17 | 2013-06-03 | Actual Labor Cost
EC2240 | Tenant Finishes for Clubhouse Areas | EC00610.1.4 | 0% | 2012-10-17 | 2013-06-03 | Budgeted Labor Cost | 2012-10-01: 9318.24; 2012-11-01: 18345.28; 2012-12-01: 17471.7; 2013-01-01: 16489.31; 2013-02-01: 14830.19; 2013-03-01: 15571.7; 2013-04-01: 16313.21; 2013-05-01: 16313.21; 2013-06-01: 247.17
EC2240 | Tenant Finishes for Clubhouse Areas | EC00610.1.4 | 0% | 2012-10-17 | 2013-06-03 | Actual Labor Units
EC2240 | Tenant Finishes for Clubhouse Areas | EC00610.1.4 | 0% | 2012-10-17 | 2013-06-03 | Budgeted Labor Units | 2012-10-01: 161; 2012-11-01: 317; 2012-12-01: 302; 2013-01-01: 293; 2013-02-01: 264; 2013-03-01: 277; 2013-04-01: 291; 2013-05-01: 291; 2013-06-01: 4
EC2370 | Final Inspections and Punchlist | EC00610.1.4 | 0% | 2013-04-03 | 2013-06-03 | Actual Labor Cost
EC2370 | Final Inspections and Punchlist | EC00610.1.4 | 0% | 2013-04-03 | 2013-06-03 | Budgeted Labor Cost | 2013-04-01: 18662.14; 2013-05-01: 20577.14; 2013-06-01: 330.71
EC2370 | Final Inspections and Punchlist | EC00610.1.4 | 0% | 2013-04-03 | 2013-06-03 | Actual Labor Units
EC2370 | Final Inspections and Punchlist | EC00610.1.4 | 0% | 2013-04-03 | 2013-06-03 | Budgeted Labor Units | 2013-04-01: 325; 2013-05-01: 359; 2013-06-01: 6
EC00610.1.5 Pool & Courtyard |  |  | 0% | 2012-06-28 | 2013-05-09 | Actual Labor Cost
EC00610.1.5 Pool & Courtyard |  |  | 0% | 2012-06-28 | 2013-05-09 | Budgeted Labor Cost | 2012-06-01: 830.51; 2012-07-01: 10464.41; 2012-08-01: 11461.02; 2012-09-01: 9467.8; 2012-10-01: 11461.02; 2012-11-01: 10464.41; 2012-12-01: 9966.1; 2013-01-01: 10962.71; 2013-02-01: 21446.1; 2013-03-01: 20795.93; 2013-04-01: 18480; 2013-05-01: 5320
EC00610.1.5 Pool & Courtyard |  |  | 0% | 2012-06-28 | 2013-05-09 | Actual Labor Units
EC00610.1.5 Pool & Courtyard |  |  | 0% | 2012-06-28 | 2013-05-09 | Budgeted Labor Units | 2012-06-01: 8; 2012-07-01: 100; 2012-08-01: 109; 2012-09-01: 90; 2012-10-01: 109; 2012-11-01: 100; 2012-12-01: 95; 2013-01-01: 104; 2013-02-01: 204; 2013-03-01: 198; 2013-04-01: 176; 2013-05-01: 51
EC2080 | Pool & Deck | EC00610.1.5 | 0% | 2012-06-28 | 2013-03-11 | Actual Labor Cost
EC2080 | Pool & Deck | EC00610.1.5 | 0% | 2012-06-28 | 2013-03-11 | Budgeted Labor Cost | 2012-06-01: 830.51; 2012-07-01: 10464.41; 2012-08-01: 11461.02; 2012-09-01: 9467.8; 2012-10-01: 11461.02; 2012-11-01: 10464.41; 2012-12-01: 9966.1; 2013-01-01: 10962.71; 2013-02-01: 9966.1; 2013-03-01: 3155.93
EC2080 | Pool & Deck | EC00610.1.5 | 0% | 2012-06-28 | 2013-03-11 | Actual Labor Units
EC2080 | Pool & Deck | EC00610.1.5 | 0% | 2012-06-28 | 2013-03-11 | Budgeted Labor Units | 2012-06-01: 8; 2012-07-01: 100; 2012-08-01: 109; 2012-09-01: 90; 2012-10-01: 109; 2012-11-01: 100; 2012-12-01: 95; 2013-01-01: 104; 2013-02-01: 95; 2013-03-01: 30
EC2270 | Pergola and Amenities | EC00610.1.5 | 0% | 2013-02-11 | 2013-05-09 | Actual Labor Cost
EC2270 | Pergola and Amenities | EC00610.1.5 | 0% | 2013-02-11 | 2013-05-09 | Budgeted Labor Cost | 2013-02-01: 11480; 2013-03-01: 17640; 2013-04-01: 18480; 2013-05-01: 5320
EC2270 | Pergola and Amenities | EC00610.1.5 | 0% | 2013-02-11 | 2013-05-09 | Actual Labor Units
EC2270 | Pergola and Amenities | EC00610.1.5 | 0% | 2013-02-11 | 2013-05-09 | Budgeted Labor Units | 2013-02-01: 109; 2013-03-01: 168; 2013-04-01: 176; 2013-05-01: 51
EC00610.2 Building 2 |  |  | 6.92% | 29-Sep-10 A | 2013-09-05 | Actual Labor Cost | 2010-09-01: 2385.25; 2010-10-01: 25045.08; 2010-11-01: 25045.08; 2010-12-01: 22251.06; 2011-01-01: 7635.4; 2011-02-01: 6079.18; 2011-03-01: 5529.81; 2011-04-01: 5449.14
EC00610.2 Building 2 |  |  | 6.92% | 29-Sep-10 A | 2013-09-05 | Budgeted Labor Cost | 2400 | 25200 | 25200 | 20880 | 6440 | 4480 | 6440 | 5880 | 11480 | 12320 | 11200 | 12880 | 11760 | 47088 | 178069.95 | 105763.5 | 79776 | 75399.04 | 104024.02 | 130991.56 | 144562.94 | 138919.34 | 114901.19 | 121707.61 | 113048.34 | 164320.07 | 128911.37 | 88490.04 | 79643.09 | 67889.64 | 33002.4 | 24814.04 | 22423.37 | 15447.5 | 14916 | 2090 | 285
EC00610.2 Building 2 |  |  | 6.92% | 29-Sep-10 A | 2013-09-05 | Actual Labor Units | 2010-09-01: 32; 2010-10-01: 334; 2010-11-01: 334; 2010-12-01: 327; 2011-01-01: 218; 2011-02-01: 174; 2011-03-01: 158; 2011-04-01: 156
EC00610.2 Building 2 |  |  | 6.92% | 29-Sep-10 A | 2013-09-05 | Budgeted Labor Units | 32 | 336 | 336 | 304 | 184 | 128 | 184 | 168 | 328 | 352 | 320 | 368 | 336 | 656 | 1856 | 1112 | 848 | 780 | 1225 | 1774 | 1973 | 1894 | 1609 | 1703 | 1505 | 2049 | 1695 | 1334 | 1429 | 1222 | 617 | 480 | 446 | 287 | 264 | 22 | 3
EC2420 | Complete Building 2 | EC00610.2 | 0% |  | 2013-08-01 | Actual Labor Cost
EC2420 | Complete Building 2 | EC00610.2 | 0% |  | 2013-08-01 | Budgeted Labor Cost
EC2420 | Complete Building 2 | EC00610.2 | 0% |  | 2013-08-01 | Actual Labor Units
EC2420 | Complete Building 2 | EC00610.2 | 0% |  | 2013-08-01 | Budgeted Labor Units
EC00610.2.1 Structure |  |  | 74.48% | 29-Sep-10 A | 2011-10-25 | Actual Labor Cost | 2010-09-01: 2385.25; 2010-10-01: 25045.08; 2010-11-01: 25045.08; 2010-12-01: 22251.06; 2011-01-01: 7635.4; 2011-02-01: 6079.18; 2011-03-01: 5529.81; 2011-04-01: 5449.14
EC00610.2.1 Structure |  |  | 74.48% | 29-Sep-10 A | 2011-10-25 | Budgeted Labor Cost | 2010-09-01: 2400; 2010-10-01: 25200; 2010-11-01: 25200; 2010-12-01: 20880; 2011-01-01: 6440; 2011-02-01: 4480; 2011-03-01: 6440; 2011-04-01: 5880; 2011-05-01: 11480; 2011-06-01: 12320; 2011-07-01: 11200; 2011-08-01: 12880; 2011-09-01: 11760; 2011-10-01: 9520
EC00610.2.1 Structure |  |  | 74.48% | 29-Sep-10 A | 2011-10-25 | Actual Labor Units | 2010-09-01: 32; 2010-10-01: 334; 2010-11-01: 334; 2010-12-01: 327; 2011-01-01: 218; 2011-02-01: 174; 2011-03-01: 158; 2011-04-01: 156
EC00610.2.1 Structure |  |  | 74.48% | 29-Sep-10 A | 2011-10-25 | Budgeted Labor Units | 2010-09-01: 32; 2010-10-01: 336; 2010-11-01: 336; 2010-12-01: 304; 2011-01-01: 184; 2011-02-01: 128; 2011-03-01: 184; 2011-04-01: 168; 2011-05-01: 328; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 368; 2011-09-01: 336; 2011-10-01: 272
EC1150 | Building Slab Incl. UG Utils | EC00610.2.1 | 100% | 29-Sep-10 A | 27-Dec-10 A | Actual Labor Cost | 2010-09-01: 2385.25; 2010-10-01: 25045.08; 2010-11-01: 25045.08; 2010-12-01: 20274.59
EC1150 | Building Slab Incl. UG Utils | EC00610.2.1 | 100% | 29-Sep-10 A | 27-Dec-10 A | Budgeted Labor Cost | 2010-09-01: 2400; 2010-10-01: 25200; 2010-11-01: 25200; 2010-12-01: 19200
EC1150 | Building Slab Incl. UG Utils | EC00610.2.1 | 100% | 29-Sep-10 A | 27-Dec-10 A | Actual Labor Units | 2010-09-01: 32; 2010-10-01: 334; 2010-11-01: 334; 2010-12-01: 270
EC1150 | Building Slab Incl. UG Utils | EC00610.2.1 | 100% | 29-Sep-10 A | 27-Dec-10 A | Budgeted Labor Units | 2010-09-01: 32; 2010-10-01: 336; 2010-11-01: 336; 2010-12-01: 256
EC1220 | First Floor Masonry Structure | EC00610.2.1 | 100% | 22-Dec-10 A | 18-Jan-11 A | Actual Labor Cost | 2010-12-01: 1976.47; 2011-01-01: 3623.53
EC1220 | First Floor Masonry Structure | EC00610.2.1 | 100% | 22-Dec-10 A | 18-Jan-11 A | Budgeted Labor Cost | 2010-12-01: 1680; 2011-01-01: 2520
EC1220 | First Floor Masonry Structure | EC00610.2.1 | 100% | 22-Dec-10 A | 18-Jan-11 A | Actual Labor Units | 2010-12-01: 56; 2011-01-01: 104
EC1220 | First Floor Masonry Structure | EC00610.2.1 | 100% | 22-Dec-10 A | 18-Jan-11 A | Budgeted Labor Units | 2010-12-01: 48; 2011-01-01: 72
EC1230 | Second Floor Slab & Collar Beam | EC00610.2.1 | 100% | 12-Jan-11 A | 25-Feb-11 A | Actual Labor Cost | 2011-01-01: 4011.88; 2011-02-01: 5158.13
EC1230 | Second Floor Slab & Collar Beam | EC00610.2.1 | 100% | 12-Jan-11 A | 25-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 3920; 2011-02-01: 4480
EC1230 | Second Floor Slab & Collar Beam | EC00610.2.1 | 100% | 12-Jan-11 A | 25-Feb-11 A | Actual Labor Units | 2011-01-01: 115; 2011-02-01: 147
EC1230 | Second Floor Slab & Collar Beam | EC00610.2.1 | 100% | 12-Jan-11 A | 25-Feb-11 A | Budgeted Labor Units | 2011-01-01: 112; 2011-02-01: 128
EC1260 | Second Floor Masonry Structure | EC00610.2.1 | 100% | 23-Feb-11 A | 22-Mar-11 A | Actual Labor Cost | 2011-02-01: 921.05; 2011-03-01: 3453.95
EC1260 | Second Floor Masonry Structure | EC00610.2.1 | 100% | 23-Feb-11 A | 22-Mar-11 A | Budgeted Labor Cost | 2011-03-01: 4200
EC1260 | Second Floor Masonry Structure | EC00610.2.1 | 100% | 23-Feb-11 A | 22-Mar-11 A | Actual Labor Units | 2011-02-01: 26; 2011-03-01: 99
EC1260 | Second Floor Masonry Structure | EC00610.2.1 | 100% | 23-Feb-11 A | 22-Mar-11 A | Budgeted Labor Units | 2011-03-01: 120
EC1290 | Third Floor Slab & Collar Beam | EC00610.2.1 | 100% | 22-Mar-11 A | 2011-05-03 | Actual Labor Cost | 2011-03-01: 2075.86; 2011-04-01: 5449.14
EC1290 | Third Floor Slab & Collar Beam | EC00610.2.1 | 100% | 22-Mar-11 A | 2011-05-03 | Budgeted Labor Cost | 2011-03-01: 2240; 2011-04-01: 5880; 2011-05-01: 280
EC1290 | Third Floor Slab & Collar Beam | EC00610.2.1 | 100% | 22-Mar-11 A | 2011-05-03 | Actual Labor Units | 2011-03-01: 59; 2011-04-01: 156
EC1290 | Third Floor Slab & Collar Beam | EC00610.2.1 | 100% | 22-Mar-11 A | 2011-05-03 | Budgeted Labor Units | 2011-03-01: 64; 2011-04-01: 168; 2011-05-01: 8
EC1320 | Third Floor Masonry Structure | EC00610.2.1 | 20% | 2011-05-03 | 2011-05-23 | Actual Labor Cost
EC1320 | Third Floor Masonry Structure | EC00610.2.1 | 20% | 2011-05-03 | 2011-05-23 | Budgeted Labor Cost | 2011-05-01: 8400
EC1320 | Third Floor Masonry Structure | EC00610.2.1 | 20% | 2011-05-03 | 2011-05-23 | Actual Labor Units
EC1320 | Third Floor Masonry Structure | EC00610.2.1 | 20% | 2011-05-03 | 2011-05-23 | Budgeted Labor Units | 2011-05-01: 240
EC1330 | Fourth Floor Slab & Collar Beam | EC00610.2.1 | 0% | 2011-05-24 | 2011-07-06 | Actual Labor Cost
EC1330 | Fourth Floor Slab & Collar Beam | EC00610.2.1 | 0% | 2011-05-24 | 2011-07-06 | Budgeted Labor Cost | 2011-05-01: 2800; 2011-06-01: 12320; 2011-07-01: 1680
EC1330 | Fourth Floor Slab & Collar Beam | EC00610.2.1 | 0% | 2011-05-24 | 2011-07-06 | Actual Labor Units
EC1330 | Fourth Floor Slab & Collar Beam | EC00610.2.1 | 0% | 2011-05-24 | 2011-07-06 | Budgeted Labor Units | 2011-05-01: 80; 2011-06-01: 352; 2011-07-01: 48
EC1380 | Fourth Floor Masonry Structure | EC00610.2.1 | 0% | 2011-07-07 | 2011-07-27 | Actual Labor Cost
EC1380 | Fourth Floor Masonry Structure | EC00610.2.1 | 0% | 2011-07-07 | 2011-07-27 | Budgeted Labor Cost | 2011-07-01: 8400
EC1380 | Fourth Floor Masonry Structure | EC00610.2.1 | 0% | 2011-07-07 | 2011-07-27 | Actual Labor Units
EC1380 | Fourth Floor Masonry Structure | EC00610.2.1 | 0% | 2011-07-07 | 2011-07-27 | Budgeted Labor Units | 2011-07-01: 240
EC1480 | Roof Slab | EC00610.2.1 | 0% | 2011-07-28 | 2011-09-02 | Actual Labor Cost
EC1480 | Roof Slab | EC00610.2.1 | 0% | 2011-07-28 | 2011-09-02 | Budgeted Labor Cost | 2011-07-01: 1120; 2011-08-01: 12880; 2011-09-01: 1120
EC1480 | Roof Slab | EC00610.2.1 | 0% | 2011-07-28 | 2011-09-02 | Actual Labor Units
EC1480 | Roof Slab | EC00610.2.1 | 0% | 2011-07-28 | 2011-09-02 | Budgeted Labor Units | 2011-07-01: 32; 2011-08-01: 368; 2011-09-01: 32
EC1620 | Stair and Elevator Masonry Structure | EC00610.2.1 | 0% | 2011-09-06 | 2011-09-13 | Actual Labor Cost
EC1620 | Stair and Elevator Masonry Structure | EC00610.2.1 | 0% | 2011-09-06 | 2011-09-13 | Budgeted Labor Cost | 2011-09-01: 3360
EC1620 | Stair and Elevator Masonry Structure | EC00610.2.1 | 0% | 2011-09-06 | 2011-09-13 | Actual Labor Units
EC1620 | Stair and Elevator Masonry Structure | EC00610.2.1 | 0% | 2011-09-06 | 2011-09-13 | Budgeted Labor Units | 2011-09-01: 96
EC1640 | Roof Slab/Collar Beam | EC00610.2.1 | 0% | 2011-09-14 | 2011-10-25 | Actual Labor Cost
EC1640 | Roof Slab/Collar Beam | EC00610.2.1 | 0% | 2011-09-14 | 2011-10-25 | Budgeted Labor Cost | 2011-09-01: 7280; 2011-10-01: 9520
EC1640 | Roof Slab/Collar Beam | EC00610.2.1 | 0% | 2011-09-14 | 2011-10-25 | Actual Labor Units
EC1640 | Roof Slab/Collar Beam | EC00610.2.1 | 0% | 2011-09-14 | 2011-10-25 | Budgeted Labor Units | 2011-09-01: 208; 2011-10-01: 272
EC00610.2.2 Roof |  |  | 0% | 2011-10-26 | 2012-02-28 | Actual Labor Cost
EC00610.2.2 Roof |  |  | 0% | 2011-10-26 | 2012-02-28 | Budgeted Labor Cost | 2011-10-01: 16640; 2011-11-01: 87360; 2011-12-01: 40027.5; 2012-01-01: 25200; 2012-02-01: 14972.5
EC00610.2.2 Roof |  |  | 0% | 2011-10-26 | 2012-02-28 | Actual Labor Units
EC00610.2.2 Roof |  |  | 0% | 2011-10-26 | 2012-02-28 | Budgeted Labor Units | 2011-10-01: 192; 2011-11-01: 1008; 2011-12-01: 496; 2012-01-01: 336; 2012-02-01: 200
EC1710 | Place Roof Trusses and Sheathing | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Actual Labor Cost
EC1710 | Place Roof Trusses and Sheathing | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Budgeted Labor Cost | 2011-10-01: 11840; 2011-11-01: 62160; 2011-12-01: 14800
EC1710 | Place Roof Trusses and Sheathing | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Actual Labor Units
EC1710 | Place Roof Trusses and Sheathing | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Budgeted Labor Units | 2011-10-01: 128; 2011-11-01: 672; 2011-12-01: 160
EC1720 | Place Mechanical Equipment Supports | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Actual Labor Cost
EC1720 | Place Mechanical Equipment Supports | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Budgeted Labor Cost | 2011-10-01: 4800; 2011-11-01: 25200; 2011-12-01: 6000
EC1720 | Place Mechanical Equipment Supports | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Actual Labor Units
EC1720 | Place Mechanical Equipment Supports | EC00610.2.2 | 0% | 2011-10-26 | 2011-12-07 | Budgeted Labor Units | 2011-10-01: 64; 2011-11-01: 336; 2011-12-01: 80
EC1860 | Built-Up Asphalt Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-07 | Actual Labor Cost
EC1860 | Built-Up Asphalt Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-07 | Budgeted Labor Cost | 2011-12-01: 9613.75; 2012-01-01: 12600; 2012-02-01: 2986.25
EC1860 | Built-Up Asphalt Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-07 | Actual Labor Units
EC1860 | Built-Up Asphalt Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-07 | Budgeted Labor Units | 2011-12-01: 128; 2012-01-01: 168; 2012-02-01: 40
EC1870 | Felt and Tile Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-28 | Actual Labor Cost
EC1870 | Felt and Tile Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-28 | Budgeted Labor Cost | 2011-12-01: 9613.75; 2012-01-01: 12600; 2012-02-01: 11986.25
EC1870 | Felt and Tile Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-28 | Actual Labor Units
EC1870 | Felt and Tile Roofing | EC00610.2.2 | 0% | 2011-12-07 | 2012-02-28 | Budgeted Labor Units | 2011-12-01: 128; 2012-01-01: 168; 2012-02-01: 160
EC2020 | Roof Complete | EC00610.2.2 | 0% |  | 2012-02-28 | Actual Labor Cost
EC2020 | Roof Complete | EC00610.2.2 | 0% |  | 2012-02-28 | Budgeted Labor Cost
EC2020 | Roof Complete | EC00610.2.2 | 0% |  | 2012-02-28 | Actual Labor Units
EC2020 | Roof Complete | EC00610.2.2 | 0% |  | 2012-02-28 | Budgeted Labor Units
EC00610.2.3 Envelope |  |  | 0% | 2011-10-26 | 2012-12-28 | Actual Labor Cost
EC00610.2.3 Envelope |  |  | 0% | 2011-10-26 | 2012-12-28 | Budgeted Labor Cost | 2011-10-01: 20928; 2011-11-01: 90709.95; 2011-12-01: 65736; 2012-01-01: 54576; 2012-02-01: 57456; 2012-03-01: 51778.05; 2012-04-01: 40320; 2012-05-01: 42240; 2012-06-01: 40320; 2012-07-01: 40320; 2012-08-01: 44160; 2012-09-01: 49920; 2012-10-01: 88320; 2012-11-01: 59520; 2012-12-01: 22080
EC00610.2.3 Envelope |  |  | 0% | 2011-10-26 | 2012-12-28 | Actual Labor Units
EC00610.2.3 Envelope |  |  | 0% | 2011-10-26 | 2012-12-28 | Budgeted Labor Units | 2011-10-01: 192; 2011-11-01: 848; 2011-12-01: 616; 2012-01-01: 512; 2012-02-01: 536; 2012-03-01: 456; 2012-04-01: 336; 2012-05-01: 352; 2012-06-01: 336; 2012-07-01: 336; 2012-08-01: 368; 2012-09-01: 416; 2012-10-01: 736; 2012-11-01: 496; 2012-12-01: 184
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.2.3 | 0% | 2011-10-26 | 2011-12-07 | Actual Labor Cost
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.2.3 | 0% | 2011-10-26 | 2011-12-07 | Budgeted Labor Cost | 2011-10-01: 13248; 2011-11-01: 69552; 2011-12-01: 16560
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.2.3 | 0% | 2011-10-26 | 2011-12-07 | Actual Labor Units
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00610.2.3 | 0% | 2011-10-26 | 2011-12-07 | Budgeted Labor Units | 2011-10-01: 128; 2011-11-01: 672; 2011-12-01: 160
EC1740 | Mobilize Scaffolding | EC00610.2.3 | 0% | 2011-10-26 | 2011-11-15 | Actual Labor Cost
EC1740 | Mobilize Scaffolding | EC00610.2.3 | 0% | 2011-10-26 | 2011-11-15 | Budgeted Labor Cost | 2011-10-01: 7680; 2011-11-01: 21120
EC1740 | Mobilize Scaffolding | EC00610.2.3 | 0% | 2011-10-26 | 2011-11-15 | Actual Labor Units
EC1740 | Mobilize Scaffolding | EC00610.2.3 | 0% | 2011-10-26 | 2011-11-15 | Budgeted Labor Units | 2011-10-01: 64; 2011-11-01: 176
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.2.3 | 0% | 2011-11-30 | 2012-01-10 | Actual Labor Cost
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.2.3 | 0% | 2011-11-30 | 2012-01-10 | Budgeted Labor Cost | 2011-11-01: 37.95; 2011-12-01: 34776; 2012-01-01: 9898.05
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.2.3 | 0% | 2011-11-30 | 2012-01-10 | Actual Labor Units
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00610.2.3 | 0% | 2011-11-30 | 2012-01-10 | Budgeted Labor Units | 2011-11-01: 0; 2011-12-01: 336; 2012-01-01: 96
EC1830 | Install Backing & Cauld Windows Floor1 | EC00610.2.3 | 0% | 2011-12-01 | 2011-12-22 | Actual Labor Cost
EC1830 | Install Backing & Cauld Windows Floor1 | EC00610.2.3 | 0% | 2011-12-01 | 2011-12-22 | Budgeted Labor Cost | 2011-12-01: 14400
EC1830 | Install Backing & Cauld Windows Floor1 | EC00610.2.3 | 0% | 2011-12-01 | 2011-12-22 | Actual Labor Units
EC1830 | Install Backing & Cauld Windows Floor1 | EC00610.2.3 | 0% | 2011-12-01 | 2011-12-22 | Budgeted Labor Units | 2011-12-01: 120
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.2.3 | 0% | 2012-01-03 | 2012-02-09 | Actual Labor Cost
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.2.3 | 0% | 2012-01-03 | 2012-02-09 | Budgeted Labor Cost | 2012-01-01: 33157.95; 2012-02-01: 11554.05
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.2.3 | 0% | 2012-01-03 | 2012-02-09 | Actual Labor Units
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00610.2.3 | 0% | 2012-01-03 | 2012-02-09 | Budgeted Labor Units | 2012-01-01: 320; 2012-02-01: 112
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00610.2.3 | 0% | 2012-01-04 | 2012-01-20 | Actual Labor Cost
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00610.2.3 | 0% | 2012-01-04 | 2012-01-20 | Budgeted Labor Cost | 2012-01-01: 11520
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00610.2.3 | 0% | 2012-01-04 | 2012-01-20 | Actual Labor Units
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00610.2.3 | 0% | 2012-01-04 | 2012-01-20 | Budgeted Labor Units | 2012-01-01: 96
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.2.3 | 0% | 2012-02-02 | 2012-03-15 | Actual Labor Cost
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.2.3 | 0% | 2012-02-02 | 2012-03-15 | Budgeted Labor Cost | 2012-02-01: 31501.95; 2012-03-01: 18178.05
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.2.3 | 0% | 2012-02-02 | 2012-03-15 | Actual Labor Units
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00610.2.3 | 0% | 2012-02-02 | 2012-03-15 | Budgeted Labor Units | 2012-02-01: 304; 2012-03-01: 176
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00610.2.3 | 0% | 2012-02-03 | 2012-02-24 | Actual Labor Cost
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00610.2.3 | 0% | 2012-02-03 | 2012-02-24 | Budgeted Labor Cost | 2012-02-01: 14400
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00610.2.3 | 0% | 2012-02-03 | 2012-02-24 | Actual Labor Units
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00610.2.3 | 0% | 2012-02-03 | 2012-02-24 | Budgeted Labor Units | 2012-02-01: 120
EC1940 | Stucco Bands | EC00610.2.3 | 0% | 2012-03-19 | 2012-04-06 | Actual Labor Cost
EC1940 | Stucco Bands | EC00610.2.3 | 0% | 2012-03-19 | 2012-04-06 | Budgeted Labor Cost | 2012-03-01: 19200; 2012-04-01: 9600
EC1940 | Stucco Bands | EC00610.2.3 | 0% | 2012-03-19 | 2012-04-06 | Actual Labor Units
EC1940 | Stucco Bands | EC00610.2.3 | 0% | 2012-03-19 | 2012-04-06 | Budgeted Labor Units | 2012-03-01: 160; 2012-04-01: 80
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00610.2.3 | 0% | 2012-03-09 | 2012-03-30 | Actual Labor Cost
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00610.2.3 | 0% | 2012-03-09 | 2012-03-30 | Budgeted Labor Cost | 2012-03-01: 14400
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00610.2.3 | 0% | 2012-03-09 | 2012-03-30 | Actual Labor Units
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00610.2.3 | 0% | 2012-03-09 | 2012-03-30 | Budgeted Labor Units | 2012-03-01: 120
EC1970 | Stucco Grey | EC00610.2.3 | 0% | 2012-04-09 | 2012-05-18 | Actual Labor Cost
EC1970 | Stucco Grey | EC00610.2.3 | 0% | 2012-04-09 | 2012-05-18 | Budgeted Labor Cost | 2012-04-01: 30720; 2012-05-01: 26880
EC1970 | Stucco Grey | EC00610.2.3 | 0% | 2012-04-09 | 2012-05-18 | Actual Labor Units
EC1970 | Stucco Grey | EC00610.2.3 | 0% | 2012-04-09 | 2012-05-18 | Budgeted Labor Units | 2012-04-01: 256; 2012-05-01: 224
EC2050 | Stucco Finish Coat | EC00610.2.3 | 0% | 2012-05-21 | 2012-07-02 | Actual Labor Cost
EC2050 | Stucco Finish Coat | EC00610.2.3 | 0% | 2012-05-21 | 2012-07-02 | Budgeted Labor Cost | 2012-05-01: 15360; 2012-06-01: 40320; 2012-07-01: 1920
EC2050 | Stucco Finish Coat | EC00610.2.3 | 0% | 2012-05-21 | 2012-07-02 | Actual Labor Units
EC2050 | Stucco Finish Coat | EC00610.2.3 | 0% | 2012-05-21 | 2012-07-02 | Budgeted Labor Units | 2012-05-01: 128; 2012-06-01: 336; 2012-07-01: 16
EC2130 | Caulk | EC00610.2.3 | 0% | 2012-07-03 | 2012-07-24 | Actual Labor Cost
EC2130 | Caulk | EC00610.2.3 | 0% | 2012-07-03 | 2012-07-24 | Budgeted Labor Cost | 2012-07-01: 28800
EC2130 | Caulk | EC00610.2.3 | 0% | 2012-07-03 | 2012-07-24 | Actual Labor Units
EC2130 | Caulk | EC00610.2.3 | 0% | 2012-07-03 | 2012-07-24 | Budgeted Labor Units | 2012-07-01: 240
EC2160 | Stucco Band Trim | EC00610.2.3 | 0% | 2012-07-25 | 2012-09-05 | Actual Labor Cost
EC2160 | Stucco Band Trim | EC00610.2.3 | 0% | 2012-07-25 | 2012-09-05 | Budgeted Labor Cost | 2012-07-01: 9600; 2012-08-01: 44160; 2012-09-01: 3840
EC2160 | Stucco Band Trim | EC00610.2.3 | 0% | 2012-07-25 | 2012-09-05 | Actual Labor Units
EC2160 | Stucco Band Trim | EC00610.2.3 | 0% | 2012-07-25 | 2012-09-05 | Budgeted Labor Units | 2012-07-01: 80; 2012-08-01: 368; 2012-09-01: 32
EC2220 | Paint Exterior | EC00610.2.3 | 0% | 2012-09-13 | 2012-12-06 | Actual Labor Cost
EC2220 | Paint Exterior | EC00610.2.3 | 0% | 2012-09-13 | 2012-12-06 | Budgeted Labor Cost | 2012-09-01: 23040; 2012-10-01: 44160; 2012-11-01: 40320; 2012-12-01: 7680
EC2220 | Paint Exterior | EC00610.2.3 | 0% | 2012-09-13 | 2012-12-06 | Actual Labor Units
EC2220 | Paint Exterior | EC00610.2.3 | 0% | 2012-09-13 | 2012-12-06 | Budgeted Labor Units | 2012-09-01: 192; 2012-10-01: 368; 2012-11-01: 336; 2012-12-01: 64
EC2230 | Install Railings | EC00610.2.3 | 0% | 2012-09-13 | 2012-11-14 | Actual Labor Cost
EC2230 | Install Railings | EC00610.2.3 | 0% | 2012-09-13 | 2012-11-14 | Budgeted Labor Cost | 2012-09-01: 23040; 2012-10-01: 44160; 2012-11-01: 19200
EC2230 | Install Railings | EC00610.2.3 | 0% | 2012-09-13 | 2012-11-14 | Actual Labor Units
EC2230 | Install Railings | EC00610.2.3 | 0% | 2012-09-13 | 2012-11-14 | Budgeted Labor Units | 2012-09-01: 192; 2012-10-01: 368; 2012-11-01: 160
EC2300 | Demobilize Scaffolding | EC00610.2.3 | 0% | 2012-12-06 | 2012-12-28 | Actual Labor Cost
EC2300 | Demobilize Scaffolding | EC00610.2.3 | 0% | 2012-12-06 | 2012-12-28 | Budgeted Labor Cost | 2012-12-01: 14400
EC2300 | Demobilize Scaffolding | EC00610.2.3 | 0% | 2012-12-06 | 2012-12-28 | Actual Labor Units
EC2300 | Demobilize Scaffolding | EC00610.2.3 | 0% | 2012-12-06 | 2012-12-28 | Budgeted Labor Units | 2012-12-01: 120
EC2320 | Shell Complete | EC00610.2.3 | 0% |  | 2012-12-28 | Actual Labor Cost
EC2320 | Shell Complete | EC00610.2.3 | 0% |  | 2012-12-28 | Budgeted Labor Cost
EC2320 | Shell Complete | EC00610.2.3 | 0% |  | 2012-12-28 | Actual Labor Units
EC2320 | Shell Complete | EC00610.2.3 | 0% |  | 2012-12-28 | Budgeted Labor Units
EC00610.2.4 Interior Finishes |  |  | 0% | 2012-02-21 | 2013-09-05 | Actual Labor Cost
EC00610.2.4 Interior Finishes |  |  | 0% | 2012-02-21 | 2013-09-05 | Budgeted Labor Cost | 2012-02-01: 2970.54; 2012-03-01: 52245.97; 2012-04-01: 90671.56; 2012-05-01: 102322.94; 2012-06-01: 98599.34; 2012-07-01: 74581.19; 2012-08-01: 77547.61; 2012-09-01: 63128.34; 2012-10-01: 76000.07; 2012-11-01: 69391.37; 2012-12-01: 66087.02; 2013-01-01: 72695.72; 2013-02-01: 61573.85; 2013-03-01: 26370.82; 2013-04-01: 17866.67; 2013-05-01: 15476; 2013-06-01: 13560; 2013-07-01: 14916; 2013-08-01: 2090; 2013-09-01: 285
EC00610.2.4 Interior Finishes |  |  | 0% | 2012-02-21 | 2013-09-05 | Actual Labor Units
EC00610.2.4 Interior Finishes |  |  | 0% | 2012-02-21 | 2013-09-05 | Budgeted Labor Units | 2012-02-01: 45; 2012-03-01: 769; 2012-04-01: 1438; 2012-05-01: 1621; 2012-06-01: 1558; 2012-07-01: 1273; 2012-08-01: 1335; 2012-09-01: 1089; 2012-10-01: 1313; 2012-11-01: 1199; 2012-12-01: 1142; 2013-01-01: 1256; 2013-02-01: 1064; 2013-03-01: 451; 2013-04-01: 307; 2013-05-01: 272; 2013-06-01: 240; 2013-07-01: 264; 2013-08-01: 22; 2013-09-01: 3
EC2000 | Unit Finishes Building North - Floor 1 | EC00610.2.4 | 0% | 2012-02-21 | 2013-02-15 | Actual Labor Cost
EC2000 | Unit Finishes Building North - Floor 1 | EC00610.2.4 | 0% | 2012-02-21 | 2013-02-15 | Budgeted Labor Cost | 2012-02-01: 1695.02; 2012-03-01: 6191.43; 2012-04-01: 5910; 2012-05-01: 6191.43; 2012-06-01: 5642.57; 2012-07-01: 5210; 2012-08-01: 5706.19; 2012-09-01: 4713.81; 2012-10-01: 5706.19; 2012-11-01: 5210; 2012-12-01: 4961.9; 2013-01-01: 5458.1; 2013-02-01: 2723.36
EC2000 | Unit Finishes Building North - Floor 1 | EC00610.2.4 | 0% | 2012-02-21 | 2013-02-15 | Actual Labor Units
EC2000 | Unit Finishes Building North - Floor 1 | EC00610.2.4 | 0% | 2012-02-21 | 2013-02-15 | Budgeted Labor Units | 2012-02-01: 29; 2012-03-01: 105; 2012-04-01: 100; 2012-05-01: 105; 2012-06-01: 96; 2012-07-01: 90; 2012-08-01: 99; 2012-09-01: 81; 2012-10-01: 99; 2012-11-01: 90; 2012-12-01: 86; 2013-01-01: 94; 2013-02-01: 47
EC2030 | Unit Finishes Building South - Floor 1 | EC00610.2.4 | 0% | 2012-02-28 | 2013-02-22 | Actual Labor Cost
EC2030 | Unit Finishes Building South - Floor 1 | EC00610.2.4 | 0% | 2012-02-28 | 2013-02-22 | Budgeted Labor Cost | 2012-02-01: 287.88; 2012-03-01: 6191.43; 2012-04-01: 5910; 2012-05-01: 6191.43; 2012-06-01: 5809.24; 2012-07-01: 5210; 2012-08-01: 5706.19; 2012-09-01: 4713.81; 2012-10-01: 5706.19; 2012-11-01: 5210; 2012-12-01: 4961.9; 2013-01-01: 5458.1; 2013-02-01: 3963.84
EC2030 | Unit Finishes Building South - Floor 1 | EC00610.2.4 | 0% | 2012-02-28 | 2013-02-22 | Actual Labor Units
EC2030 | Unit Finishes Building South - Floor 1 | EC00610.2.4 | 0% | 2012-02-28 | 2013-02-22 | Budgeted Labor Units | 2012-02-01: 5; 2012-03-01: 105; 2012-04-01: 100; 2012-05-01: 105; 2012-06-01: 99; 2012-07-01: 90; 2012-08-01: 99; 2012-09-01: 81; 2012-10-01: 99; 2012-11-01: 90; 2012-12-01: 86; 2013-01-01: 94; 2013-02-01: 68
EC2040 | Building 1 Elevators Complete | EC00610.2.4 | 0% | 2012-02-28 | 2012-06-29 | Actual Labor Cost
EC2040 | Building 1 Elevators Complete | EC00610.2.4 | 0% | 2012-02-28 | 2012-06-29 | Budgeted Labor Cost | 2012-02-01: 987.64; 2012-03-01: 21241.38; 2012-04-01: 20275.86; 2012-05-01: 21241.38; 2012-06-01: 20253.74
EC2040 | Building 1 Elevators Complete | EC00610.2.4 | 0% | 2012-02-28 | 2012-06-29 | Actual Labor Units
EC2040 | Building 1 Elevators Complete | EC00610.2.4 | 0% | 2012-02-28 | 2012-06-29 | Budgeted Labor Units | 2012-02-01: 11; 2012-03-01: 243; 2012-04-01: 232; 2012-05-01: 243; 2012-06-01: 231
EC2070 | Unit Finishes Building North - Floor 2 | EC00610.2.4 | 0% | 2012-03-06 | 2013-02-21 | Actual Labor Cost
EC2070 | Unit Finishes Building North - Floor 2 | EC00610.2.4 | 0% | 2012-03-06 | 2013-02-21 | Budgeted Labor Cost | 2012-03-01: 5195.88; 2012-04-01: 6054.15; 2012-05-01: 6342.44; 2012-06-01: 6053.36; 2012-07-01: 5337.07; 2012-08-01: 5845.37; 2012-09-01: 4828.78; 2012-10-01: 5845.37; 2012-11-01: 5337.07; 2012-12-01: 5082.93; 2013-01-01: 5591.22; 2013-02-01: 3806.37
EC2070 | Unit Finishes Building North - Floor 2 | EC00610.2.4 | 0% | 2012-03-06 | 2013-02-21 | Actual Labor Units
EC2070 | Unit Finishes Building North - Floor 2 | EC00610.2.4 | 0% | 2012-03-06 | 2013-02-21 | Budgeted Labor Units | 2012-03-01: 88; 2012-04-01: 102; 2012-05-01: 107; 2012-06-01: 102; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 101; 2012-11-01: 92; 2012-12-01: 88; 2013-01-01: 97; 2013-02-01: 66
EC2120 | Unit Finishes Building South - Floor 2 | EC00610.2.4 | 0% | 2012-03-14 | 2013-02-28 | Actual Labor Cost
EC2120 | Unit Finishes Building South - Floor 2 | EC00610.2.4 | 0% | 2012-03-14 | 2013-02-28 | Budgeted Labor Cost | 2012-03-01: 7495.61; 2012-04-01: 12108.29; 2012-05-01: 12684.88; 2012-06-01: 12108.29; 2012-07-01: 11015.61; 2012-08-01: 11690.73; 2012-09-01: 9657.56; 2012-10-01: 11690.73; 2012-11-01: 10674.15; 2012-12-01: 10165.85; 2013-01-01: 11182.44; 2013-02-01: 10165.85
EC2120 | Unit Finishes Building South - Floor 2 | EC00610.2.4 | 0% | 2012-03-14 | 2013-02-28 | Actual Labor Units
EC2120 | Unit Finishes Building South - Floor 2 | EC00610.2.4 | 0% | 2012-03-14 | 2013-02-28 | Budgeted Labor Units | 2012-03-01: 127; 2012-04-01: 205; 2012-05-01: 215; 2012-06-01: 205; 2012-07-01: 189; 2012-08-01: 202; 2012-09-01: 167; 2012-10-01: 202; 2012-11-01: 184; 2012-12-01: 176; 2013-01-01: 193; 2013-02-01: 176
EC2150 | Unit Finishes Building North - Floor 3 | EC00610.2.4 | 0% | 2012-03-21 | 2013-03-07 | Actual Labor Cost
EC2150 | Unit Finishes Building North - Floor 3 | EC00610.2.4 | 0% | 2012-03-21 | 2013-03-07 | Budgeted Labor Cost | 2012-03-01: 4339.51; 2012-04-01: 11391.22; 2012-05-01: 12650.73; 2012-06-01: 12108.29; 2012-07-01: 11732.68; 2012-08-01: 12339.51; 2012-09-01: 9657.56; 2012-10-01: 11690.73; 2012-11-01: 10674.15; 2012-12-01: 10165.85; 2013-01-01: 11182.44; 2013-02-01: 10165.85; 2013-03-01: 2541.46
EC2150 | Unit Finishes Building North - Floor 3 | EC00610.2.4 | 0% | 2012-03-21 | 2013-03-07 | Actual Labor Units
EC2150 | Unit Finishes Building North - Floor 3 | EC00610.2.4 | 0% | 2012-03-21 | 2013-03-07 | Budgeted Labor Units | 2012-03-01: 74; 2012-04-01: 195; 2012-05-01: 214; 2012-06-01: 205; 2012-07-01: 200; 2012-08-01: 211; 2012-09-01: 167; 2012-10-01: 202; 2012-11-01: 184; 2012-12-01: 176; 2013-01-01: 193; 2013-02-01: 176; 2013-03-01: 44
EC2170 | Unit Finishes Building South - Floor 3 | EC00610.2.4 | 0% | 2012-03-28 | 2013-04-25 | Actual Labor Cost
EC2170 | Unit Finishes Building South - Floor 3 | EC00610.2.4 | 0% | 2012-03-28 | 2013-04-25 | Budgeted Labor Cost | 2012-03-01: 1590.73; 2012-04-01: 11135.12; 2012-05-01: 12406.83; 2012-06-01: 12108.29; 2012-07-01: 11698.54; 2012-08-01: 11690.73; 2012-09-01: 9657.56; 2012-10-01: 11690.73; 2012-11-01: 10674.15; 2012-12-01: 10165.85; 2013-01-01: 11182.44; 2013-02-01: 10165.85; 2013-03-01: 5592.68; 2013-04-01: 880.49
EC2170 | Unit Finishes Building South - Floor 3 | EC00610.2.4 | 0% | 2012-03-28 | 2013-04-25 | Actual Labor Units
EC2170 | Unit Finishes Building South - Floor 3 | EC00610.2.4 | 0% | 2012-03-28 | 2013-04-25 | Budgeted Labor Units | 2012-03-01: 28; 2012-04-01: 195; 2012-05-01: 212; 2012-06-01: 205; 2012-07-01: 199; 2012-08-01: 202; 2012-09-01: 167; 2012-10-01: 202; 2012-11-01: 184; 2012-12-01: 176; 2013-01-01: 193; 2013-02-01: 176; 2013-03-01: 93; 2013-04-01: 9
EC2200 | Unit Finishes Building North - Floor 4 | EC00610.2.4 | 0% | 2012-04-04 | 2013-04-29 | Actual Labor Cost
EC2200 | Unit Finishes Building North - Floor 4 | EC00610.2.4 | 0% | 2012-04-04 | 2013-04-29 | Budgeted Labor Cost | 2012-04-01: 10199.01; 2012-05-01: 12325.43; 2012-06-01: 12257.78; 2012-07-01: 12119.51; 2012-08-01: 11835.06; 2012-09-01: 9776.79; 2012-10-01: 11835.06; 2012-11-01: 10805.93; 2012-12-01: 10291.36; 2013-01-01: 11320.49; 2013-02-01: 10291.36; 2013-03-01: 6597.03; 2013-04-01: 985.18
EC2200 | Unit Finishes Building North - Floor 4 | EC00610.2.4 | 0% | 2012-04-04 | 2013-04-29 | Actual Labor Units
EC2200 | Unit Finishes Building North - Floor 4 | EC00610.2.4 | 0% | 2012-04-04 | 2013-04-29 | Budgeted Labor Units | 2012-04-01: 178; 2012-05-01: 212; 2012-06-01: 207; 2012-07-01: 205; 2012-08-01: 204; 2012-09-01: 169; 2012-10-01: 204; 2012-11-01: 187; 2012-12-01: 178; 2013-01-01: 196; 2013-02-01: 178; 2013-03-01: 111; 2013-04-01: 10
EC2210 | Unit Finishes Building South - Floor 4 | EC00610.2.4 | 0% | 2012-04-11 | 2013-03-25 | Actual Labor Cost
EC2210 | Unit Finishes Building South - Floor 4 | EC00610.2.4 | 0% | 2012-04-11 | 2013-03-25 | Budgeted Labor Cost | 2012-04-01: 7687.9; 2012-05-01: 12288.4; 2012-06-01: 12257.78; 2012-07-01: 12257.78; 2012-08-01: 12733.83; 2012-09-01: 10122.47; 2012-10-01: 11835.06; 2012-11-01: 10805.93; 2012-12-01: 10291.36; 2013-01-01: 11320.49; 2013-02-01: 10291.36; 2013-03-01: 8747.65
EC2210 | Unit Finishes Building South - Floor 4 | EC00610.2.4 | 0% | 2012-04-11 | 2013-03-25 | Actual Labor Units
EC2210 | Unit Finishes Building South - Floor 4 | EC00610.2.4 | 0% | 2012-04-11 | 2013-03-25 | Budgeted Labor Units | 2012-04-01: 131; 2012-05-01: 209; 2012-06-01: 207; 2012-07-01: 207; 2012-08-01: 217; 2012-09-01: 174; 2012-10-01: 204; 2012-11-01: 187; 2012-12-01: 178; 2013-01-01: 196; 2013-02-01: 178; 2013-03-01: 151
EC2410 | Final Inspections and Punchlist | EC00610.2.4 | 0% | 2013-03-26 | 2013-09-05 | Actual Labor Cost
EC2410 | Final Inspections and Punchlist | EC00610.2.4 | 0% | 2013-03-26 | 2013-09-05 | Budgeted Labor Cost | 2013-03-01: 2892; 2013-04-01: 16001; 2013-05-01: 15476; 2013-06-01: 13560; 2013-07-01: 14916; 2013-08-01: 2090; 2013-09-01: 285
EC2410 | Final Inspections and Punchlist | EC00610.2.4 | 0% | 2013-03-26 | 2013-09-05 | Actual Labor Units
EC2410 | Final Inspections and Punchlist | EC00610.2.4 | 0% | 2013-03-26 | 2013-09-05 | Budgeted Labor Units | 2013-03-01: 52; 2013-04-01: 287; 2013-05-01: 272; 2013-06-01: 240; 2013-07-01: 264; 2013-08-01: 22; 2013-09-01: 3
EC00610.2.5 Courtyard |  |  | 0% | 2012-12-28 | 2013-06-10 | Actual Labor Cost
EC00610.2.5 Courtyard |  |  | 0% | 2012-12-28 | 2013-06-10 | Budgeted Labor Cost | 2012-12-01: 323.03; 2013-01-01: 6947.37; 2013-02-01: 6315.79; 2013-03-01: 6631.58; 2013-04-01: 6947.37; 2013-05-01: 6947.37; 2013-06-01: 1887.5
EC00610.2.5 Courtyard |  |  | 0% | 2012-12-28 | 2013-06-10 | Actual Labor Units
EC00610.2.5 Courtyard |  |  | 0% | 2012-12-28 | 2013-06-10 | Budgeted Labor Units | 2012-12-01: 8; 2013-01-01: 174; 2013-02-01: 158; 2013-03-01: 166; 2013-04-01: 174; 2013-05-01: 174; 2013-06-01: 47
EC2330 | Courtyard Walks and Amenities | EC00610.2.5 | 0% | 2012-12-28 | 2013-06-10 | Actual Labor Cost
EC2330 | Courtyard Walks and Amenities | EC00610.2.5 | 0% | 2012-12-28 | 2013-06-10 | Budgeted Labor Cost | 2012-12-01: 323.03; 2013-01-01: 6947.37; 2013-02-01: 6315.79; 2013-03-01: 6631.58; 2013-04-01: 6947.37; 2013-05-01: 6947.37; 2013-06-01: 1887.5
EC2330 | Courtyard Walks and Amenities | EC00610.2.5 | 0% | 2012-12-28 | 2013-06-10 | Actual Labor Units
EC2330 | Courtyard Walks and Amenities | EC00610.2.5 | 0% | 2012-12-28 | 2013-06-10 | Budgeted Labor Units | 2012-12-01: 8; 2013-01-01: 174; 2013-02-01: 158; 2013-03-01: 166; 2013-04-01: 174; 2013-05-01: 174; 2013-06-01: 47
EC00610.5 Garage 1 |  |  | 0% | 2011-06-22 | 2013-05-06 | Actual Labor Cost
EC00610.5 Garage 1 |  |  | 0% | 2011-06-22 | 2013-05-06 | Budgeted Labor Cost | 2011-06-01: 7810.17; 2011-07-01: 26033.9; 2011-08-01: 29938.98; 2011-09-01: 27335.59; 2011-10-01: 25383.05; 2011-11-01: 20501.69; 2011-12-01: 20501.69; 2012-01-01: 20501.69; 2012-02-01: 20501.69; 2012-03-01: 10836.78; 2012-04-01: 10351.76; 2012-05-01: 10844.71; 2012-06-01: 10351.76; 2012-07-01: 10351.76; 2012-08-01: 13839.29; 2012-09-01: 20900; 2012-10-01: 25300; 2012-11-01: 23100; 2012-12-01: 37218.33; 2013-01-01: 18700; 2013-02-01: 16000; 2013-03-01: 16800; 2013-04-01: 36781.67; 2013-05-01: 3200
EC00610.5 Garage 1 |  |  | 0% | 2011-06-22 | 2013-05-06 | Actual Labor Units
EC00610.5 Garage 1 |  |  | 0% | 2011-06-22 | 2013-05-06 | Budgeted Labor Units | 2011-06-01: 108; 2011-07-01: 347; 2011-08-01: 399; 2011-09-01: 364; 2011-10-01: 343; 2011-11-01: 273; 2011-12-01: 273; 2012-01-01: 273; 2012-02-01: 273; 2012-03-01: 142; 2012-04-01: 128; 2012-05-01: 134; 2012-06-01: 128; 2012-07-01: 128; 2012-08-01: 172; 2012-09-01: 253; 2012-10-01: 307; 2012-11-01: 280; 2012-12-01: 470; 2013-01-01: 248; 2013-02-01: 213; 2013-03-01: 224; 2013-04-01: 501; 2013-05-01: 64
EC1420 | Start Garage | EC00610.5 | 0% | 2011-06-27 |  | Actual Labor Cost
EC1420 | Start Garage | EC00610.5 | 0% | 2011-06-27 |  | Budgeted Labor Cost
EC1420 | Start Garage | EC00610.5 | 0% | 2011-06-27 |  | Actual Labor Units
EC1420 | Start Garage | EC00610.5 | 0% | 2011-06-27 |  | Budgeted Labor Units
EC1430 | Shop Drawings, Review & Approval | EC00610.5 | 0% | 2011-06-22 | 2011-10-27 | Actual Labor Cost
EC1430 | Shop Drawings, Review & Approval | EC00610.5 | 0% | 2011-06-22 | 2011-10-27 | Budgeted Labor Cost | 2011-06-01: 7810.17; 2011-07-01: 26033.9; 2011-08-01: 29938.98; 2011-09-01: 27335.59; 2011-10-01: 23430.51
EC1430 | Shop Drawings, Review & Approval | EC00610.5 | 0% | 2011-06-22 | 2011-10-27 | Actual Labor Units
EC1430 | Shop Drawings, Review & Approval | EC00610.5 | 0% | 2011-06-22 | 2011-10-27 | Budgeted Labor Units | 2011-06-01: 108; 2011-07-01: 347; 2011-08-01: 399; 2011-09-01: 364; 2011-10-01: 317
EC1810 | Fab & Delivery | EC00610.5 | 0% | 2011-10-28 | 2012-03-06 | Actual Labor Cost
EC1810 | Fab & Delivery | EC00610.5 | 0% | 2011-10-28 | 2012-03-06 | Budgeted Labor Cost | 2011-10-01: 1952.54; 2011-11-01: 20501.69; 2011-12-01: 20501.69; 2012-01-01: 20501.69; 2012-02-01: 20501.69; 2012-03-01: 1952.54
EC1810 | Fab & Delivery | EC00610.5 | 0% | 2011-10-28 | 2012-03-06 | Actual Labor Units
EC1810 | Fab & Delivery | EC00610.5 | 0% | 2011-10-28 | 2012-03-06 | Budgeted Labor Units | 2011-10-01: 26; 2011-11-01: 273; 2011-12-01: 273; 2012-01-01: 273; 2012-02-01: 273; 2012-03-01: 33
EC2090 | Erect Precast Structure | EC00610.5 | 0% | 2012-03-06 | 2012-08-23 | Actual Labor Cost
EC2090 | Erect Precast Structure | EC00610.5 | 0% | 2012-03-06 | 2012-08-23 | Budgeted Labor Cost | 2012-03-01: 8884.24; 2012-04-01: 10351.76; 2012-05-01: 10844.71; 2012-06-01: 10351.76; 2012-07-01: 10351.76; 2012-08-01: 7239.29
EC2090 | Erect Precast Structure | EC00610.5 | 0% | 2012-03-06 | 2012-08-23 | Actual Labor Units
EC2090 | Erect Precast Structure | EC00610.5 | 0% | 2012-03-06 | 2012-08-23 | Budgeted Labor Units | 2012-03-01: 110; 2012-04-01: 128; 2012-05-01: 134; 2012-06-01: 128; 2012-07-01: 128; 2012-08-01: 92
EC2280 | Fire Protection and Lighting | EC00610.5 | 0% | 2012-08-24 | 2013-01-02 | Actual Labor Cost
EC2280 | Fire Protection and Lighting | EC00610.5 | 0% | 2012-08-24 | 2013-01-02 | Budgeted Labor Cost | 2012-08-01: 6600; 2012-09-01: 20900; 2012-10-01: 25300; 2012-11-01: 23100; 2012-12-01: 22000; 2013-01-01: 1100
EC2280 | Fire Protection and Lighting | EC00610.5 | 0% | 2012-08-24 | 2013-01-02 | Actual Labor Units
EC2280 | Fire Protection and Lighting | EC00610.5 | 0% | 2012-08-24 | 2013-01-02 | Budgeted Labor Units | 2012-08-01: 80; 2012-09-01: 253; 2012-10-01: 307; 2012-11-01: 280; 2012-12-01: 267; 2013-01-01: 13
EC2310 | Finishes, Barrier Cables & Striping | EC00610.5 | 0% | 2012-12-03 | 2013-04-10 | Actual Labor Cost
EC2310 | Finishes, Barrier Cables & Striping | EC00610.5 | 0% | 2012-12-03 | 2013-04-10 | Budgeted Labor Cost | 2012-12-01: 15218.33; 2013-01-01: 17600; 2013-02-01: 16000; 2013-03-01: 16800; 2013-04-01: 6381.67
EC2310 | Finishes, Barrier Cables & Striping | EC00610.5 | 0% | 2012-12-03 | 2013-04-10 | Actual Labor Units
EC2310 | Finishes, Barrier Cables & Striping | EC00610.5 | 0% | 2012-12-03 | 2013-04-10 | Budgeted Labor Units | 2012-12-01: 203; 2013-01-01: 235; 2013-02-01: 213; 2013-03-01: 224; 2013-04-01: 85
EC2380 | Punchlist Garage | EC00610.5 | 0% | 2013-04-11 | 2013-05-06 | Actual Labor Cost
EC2380 | Punchlist Garage | EC00610.5 | 0% | 2013-04-11 | 2013-05-06 | Budgeted Labor Cost | 2013-04-01: 30400; 2013-05-01: 3200
EC2380 | Punchlist Garage | EC00610.5 | 0% | 2013-04-11 | 2013-05-06 | Actual Labor Units
EC2380 | Punchlist Garage | EC00610.5 | 0% | 2013-04-11 | 2013-05-06 | Budgeted Labor Units | 2013-04-01: 416; 2013-05-01: 64
EC2390 | Complete Garage 1 | EC00610.5 | 0% |  | 2013-04-29 | Actual Labor Cost
EC2390 | Complete Garage 1 | EC00610.5 | 0% |  | 2013-04-29 | Budgeted Labor Cost
EC2390 | Complete Garage 1 | EC00610.5 | 0% |  | 2013-04-29 | Actual Labor Units
EC2390 | Complete Garage 1 | EC00610.5 | 0% |  | 2013-04-29 | Budgeted Labor Units
EC2400 | Complete Garage | EC00610.5 | 0% |  | 2013-04-29 | Actual Labor Cost
EC2400 | Complete Garage | EC00610.5 | 0% |  | 2013-04-29 | Budgeted Labor Cost
EC2400 | Complete Garage | EC00610.5 | 0% |  | 2013-04-29 | Actual Labor Units
EC2400 | Complete Garage | EC00610.5 | 0% |  | 2013-04-29 | Budgeted Labor Units
EC00610.6 Garage 2 |  |  | 33.13% | 01-Sep-10 A | 2012-09-26 | Actual Labor Cost | 2010-09-01: 13767.93; 2010-10-01: 13767.93; 2010-11-01: 13767.93; 2010-12-01: 13767.93; 2011-01-01: 11993.16; 2011-02-01: 10576.92; 2011-03-01: 12163.46; 2011-04-01: 11105.77
EC00610.6 Garage 2 |  |  | 33.13% | 01-Sep-10 A | 2012-09-26 | Budgeted Labor Cost | 2010-09-01: 13667.8; 2010-10-01: 13667.8; 2010-11-01: 13667.8; 2010-12-01: 13667.8; 2011-01-01: 11723.39; 2011-02-01: 9600; 2011-03-01: 11040; 2011-04-01: 10080; 2011-05-01: 16918.44; 2011-06-01: 20571.43; 2011-07-01: 18701.3; 2011-08-01: 21506.49; 2011-09-01: 19636.36; 2011-10-01: 14315.68; 2011-11-01: 23692.31; 2011-12-01: 23692.31; 2012-01-01: 23692.31; 2012-02-01: 43539.93; 2012-03-01: 27347.98; 2012-04-01: 24000; 2012-05-01: 25142.86; 2012-06-01: 27400; 2012-07-01: 14366.67; 2012-08-01: 13800; 2012-09-01: 6300
EC00610.6 Garage 2 |  |  | 33.13% | 01-Sep-10 A | 2012-09-26 | Actual Labor Units | 2010-09-01: 185; 2010-10-01: 185; 2010-11-01: 185; 2010-12-01: 185; 2011-01-01: 160; 2011-02-01: 141; 2011-03-01: 162; 2011-04-01: 148
EC00610.6 Garage 2 |  |  | 33.13% | 01-Sep-10 A | 2012-09-26 | Budgeted Labor Units | 2010-09-01: 182; 2010-10-01: 182; 2010-11-01: 182; 2010-12-01: 182; 2011-01-01: 161; 2011-02-01: 128; 2011-03-01: 147; 2011-04-01: 134; 2011-05-01: 226; 2011-06-01: 274; 2011-07-01: 249; 2011-08-01: 287; 2011-09-01: 262; 2011-10-01: 208; 2011-11-01: 287; 2011-12-01: 287; 2012-01-01: 287; 2012-02-01: 528; 2012-03-01: 332; 2012-04-01: 288; 2012-05-01: 302; 2012-06-01: 339; 2012-07-01: 187; 2012-08-01: 184; 2012-09-01: 78
EC1020 | Start Garage | EC00610.6 | 100% | 01-Sep-10 A |  | Actual Labor Cost
EC1020 | Start Garage | EC00610.6 | 100% | 01-Sep-10 A |  | Budgeted Labor Cost
EC1020 | Start Garage | EC00610.6 | 100% | 01-Sep-10 A |  | Actual Labor Units
EC1020 | Start Garage | EC00610.6 | 100% | 01-Sep-10 A |  | Budgeted Labor Units
EC1030 | Shop Drawings, Review and Approval | EC00610.6 | 100% | 01-Sep-10 A | 12-Jan-11 A | Actual Labor Cost | 2010-09-01: 13767.93; 2010-10-01: 13767.93; 2010-11-01: 13767.93; 2010-12-01: 13767.93; 2011-01-01: 4589.31
EC1030 | Shop Drawings, Review and Approval | EC00610.6 | 100% | 01-Sep-10 A | 12-Jan-11 A | Budgeted Labor Cost | 2010-09-01: 13667.8; 2010-10-01: 13667.8; 2010-11-01: 13667.8; 2010-12-01: 13667.8; 2011-01-01: 2603.39
EC1030 | Shop Drawings, Review and Approval | EC00610.6 | 100% | 01-Sep-10 A | 12-Jan-11 A | Actual Labor Units | 2010-09-01: 185; 2010-10-01: 185; 2010-11-01: 185; 2010-12-01: 185; 2011-01-01: 62
EC1030 | Shop Drawings, Review and Approval | EC00610.6 | 100% | 01-Sep-10 A | 12-Jan-11 A | Budgeted Labor Units | 2010-09-01: 182; 2010-10-01: 182; 2010-11-01: 182; 2010-12-01: 182; 2011-01-01: 39
EC1180 | Fab & Delivery | EC00610.6 | 92.22% | 12-Jan-11 A | 2011-05-10 | Actual Labor Cost | 2011-01-01: 7403.85; 2011-02-01: 10576.92; 2011-03-01: 12163.46; 2011-04-01: 11105.77
EC1180 | Fab & Delivery | EC00610.6 | 92.22% | 12-Jan-11 A | 2011-05-10 | Budgeted Labor Cost | 2011-01-01: 9120; 2011-02-01: 9600; 2011-03-01: 11040; 2011-04-01: 10080; 2011-05-01: 3360
EC1180 | Fab & Delivery | EC00610.6 | 92.22% | 12-Jan-11 A | 2011-05-10 | Actual Labor Units | 2011-01-01: 99; 2011-02-01: 141; 2011-03-01: 162; 2011-04-01: 148
EC1180 | Fab & Delivery | EC00610.6 | 92.22% | 12-Jan-11 A | 2011-05-10 | Budgeted Labor Units | 2011-01-01: 122; 2011-02-01: 128; 2011-03-01: 147; 2011-04-01: 134; 2011-05-01: 45
EC1280 | Erect Precast Structure | EC00610.6 | 0% | 2011-05-10 | 2011-10-28 | Actual Labor Cost
EC1280 | Erect Precast Structure | EC00610.6 | 0% | 2011-05-10 | 2011-10-28 | Budgeted Labor Cost | 2011-05-01: 13558.44; 2011-06-01: 20571.43; 2011-07-01: 18701.3; 2011-08-01: 21506.49; 2011-09-01: 19636.36; 2011-10-01: 12623.38
EC1280 | Erect Precast Structure | EC00610.6 | 0% | 2011-05-10 | 2011-10-28 | Actual Labor Units
EC1280 | Erect Precast Structure | EC00610.6 | 0% | 2011-05-10 | 2011-10-28 | Budgeted Labor Units | 2011-05-01: 181; 2011-06-01: 274; 2011-07-01: 249; 2011-08-01: 287; 2011-09-01: 262; 2011-10-01: 187
EC1590 | Fire Protection and Lighting | EC00610.6 | 0% | 2011-10-28 | 2012-03-07 | Actual Labor Cost
EC1590 | Fire Protection and Lighting | EC00610.6 | 0% | 2011-10-28 | 2012-03-07 | Budgeted Labor Cost | 2011-10-01: 1692.31; 2011-11-01: 23692.31; 2011-12-01: 23692.31; 2012-01-01: 23692.31; 2012-02-01: 23692.31; 2012-03-01: 2205.13
EC1590 | Fire Protection and Lighting | EC00610.6 | 0% | 2011-10-28 | 2012-03-07 | Actual Labor Units
EC1590 | Fire Protection and Lighting | EC00610.6 | 0% | 2011-10-28 | 2012-03-07 | Budgeted Labor Units | 2011-10-01: 21; 2011-11-01: 287; 2011-12-01: 287; 2012-01-01: 287; 2012-02-01: 287; 2012-03-01: 31
EC1680 | Finishes and Striping | EC00610.6 | 0% | 2012-02-03 | 2012-07-06 | Actual Labor Cost
EC1680 | Finishes and Striping | EC00610.6 | 0% | 2012-02-03 | 2012-07-06 | Budgeted Labor Cost | 2012-02-01: 19847.62; 2012-03-01: 25142.86; 2012-04-01: 24000; 2012-05-01: 25142.86; 2012-06-01: 24000; 2012-07-01: 1866.67
EC1680 | Finishes and Striping | EC00610.6 | 0% | 2012-02-03 | 2012-07-06 | Actual Labor Units
EC1680 | Finishes and Striping | EC00610.6 | 0% | 2012-02-03 | 2012-07-06 | Budgeted Labor Units | 2012-02-01: 241; 2012-03-01: 302; 2012-04-01: 288; 2012-05-01: 302; 2012-06-01: 288; 2012-07-01: 20
EC2060 | Punch List Garage | EC00610.6 | 0% | 2012-06-19 | 2012-09-26 | Actual Labor Cost
EC2060 | Punch List Garage | EC00610.6 | 0% | 2012-06-19 | 2012-09-26 | Budgeted Labor Cost | 2012-06-01: 3400; 2012-07-01: 12500; 2012-08-01: 13800; 2012-09-01: 6300
EC2060 | Punch List Garage | EC00610.6 | 0% | 2012-06-19 | 2012-09-26 | Actual Labor Units
EC2060 | Punch List Garage | EC00610.6 | 0% | 2012-06-19 | 2012-09-26 | Budgeted Labor Units | 2012-06-01: 51; 2012-07-01: 167; 2012-08-01: 184; 2012-09-01: 78
EC2180 | Complete Garage 2 | EC00610.6 | 0% |  | 2012-09-26 | Actual Labor Cost
EC2180 | Complete Garage 2 | EC00610.6 | 0% |  | 2012-09-26 | Budgeted Labor Cost
EC2180 | Complete Garage 2 | EC00610.6 | 0% |  | 2012-09-26 | Actual Labor Units
EC2180 | Complete Garage 2 | EC00610.6 | 0% |  | 2012-09-26 | Budgeted Labor Units
EC2190 | Complete Garage | EC00610.6 | 0% |  | 2012-09-26 | Actual Labor Cost
EC2190 | Complete Garage | EC00610.6 | 0% |  | 2012-09-26 | Budgeted Labor Cost
EC2190 | Complete Garage | EC00610.6 | 0% |  | 2012-09-26 | Actual Labor Units
EC2190 | Complete Garage | EC00610.6 | 0% |  | 2012-09-26 | Budgeted Labor Units
EC00610.7 Roads, Utilities & Pavers |  |  | 35.26% | 01-Sep-10 A | 2013-05-17 | Actual Labor Cost | 2010-09-01: 89754.42; 2010-10-01: 80946.42; 2010-11-01: 80946.42; 2010-12-01: 79269.92; 2011-01-01: 14060.94; 2011-02-01: 6498.84; 2011-03-01: 6148.86; 2011-04-01: 5614.18
EC00610.7 Roads, Utilities & Pavers |  |  | 35.26% | 01-Sep-10 A | 2013-05-17 | Budgeted Labor Cost | 2010-09-01: 86640; 2010-10-01: 78120; 2010-11-01: 78120; 2010-12-01: 78120; 2011-01-01: 24771.43; 2011-02-01: 5028.57; 2011-03-01: 5782.86; 2011-04-01: 5280; 2011-05-01: 34537.14; 2011-06-01: 45760; 2011-07-01: 41600; 2011-08-01: 4160; 2011-09-01: 5826.67; 2011-10-01: 25160; 2011-11-01: 91560; 2011-12-01: 91560; 2012-01-01: 91560; 2012-02-01: 61960; 2012-03-01: 1013.33; 2012-08-01: 34464; 2012-09-01: 87856; 2012-10-01: 106352; 2012-11-01: 97104; 2012-12-01: 93543.83; 2013-01-01: 80928; 2013-02-01: 69952; 2013-03-01: 36960; 2013-04-01: 22880; 2013-05-01: 13496.17
EC00610.7 Roads, Utilities & Pavers |  |  | 35.26% | 01-Sep-10 A | 2013-05-17 | Actual Labor Units | 2010-09-01: 911; 2010-10-01: 856; 2010-11-01: 856; 2010-12-01: 839; 2011-01-01: 294; 2011-02-01: 162; 2011-03-01: 154; 2011-04-01: 140
EC00610.7 Roads, Utilities & Pavers |  |  | 35.26% | 01-Sep-10 A | 2013-05-17 | Budgeted Labor Units | 2010-09-01: 888; 2010-10-01: 840; 2010-11-01: 840; 2010-12-01: 840; 2011-01-01: 334; 2011-02-01: 126; 2011-03-01: 145; 2011-04-01: 132; 2011-05-01: 287; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 32; 2011-09-01: 61; 2011-10-01: 256; 2011-11-01: 840; 2011-12-01: 840; 2012-01-01: 840; 2012-02-01: 608; 2012-03-01: 11; 2012-08-01: 352; 2012-09-01: 912; 2012-10-01: 1104; 2012-11-01: 1008; 2012-12-01: 968; 2013-01-01: 896; 2013-02-01: 768; 2013-03-01: 312; 2013-04-01: 176; 2013-05-01: 104
EC1000 | Curbing | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Actual Labor Cost | 2010-09-01: 22880; 2010-10-01: 22880; 2010-11-01: 22880; 2010-12-01: 22880
EC1000 | Curbing | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Budgeted Labor Cost | 2010-09-01: 21840; 2010-10-01: 21840; 2010-11-01: 21840; 2010-12-01: 21840; 2011-01-01: 6240
EC1000 | Curbing | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Actual Labor Units | 2010-09-01: 176; 2010-10-01: 176; 2010-11-01: 176; 2010-12-01: 176
EC1000 | Curbing | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 168; 2010-12-01: 168; 2011-01-01: 48
EC1040 | Electric to Building 4 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 10-Jan-11 A | Actual Labor Cost | 2010-09-01: 16811.8; 2010-10-01: 16811.8; 2010-11-01: 16811.8; 2010-12-01: 16811.8; 2011-01-01: 4002.81
EC1040 | Electric to Building 4 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 10-Jan-11 A | Budgeted Labor Cost | 2010-09-01: 15960; 2010-10-01: 15960; 2010-11-01: 15960; 2010-12-01: 15960; 2011-01-01: 4560
EC1040 | Electric to Building 4 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 10-Jan-11 A | Actual Labor Units | 2010-09-01: 177; 2010-10-01: 177; 2010-11-01: 177; 2010-12-01: 177; 2011-01-01: 42
EC1040 | Electric to Building 4 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 10-Jan-11 A | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 168; 2010-12-01: 168; 2011-01-01: 48
EC1050 | Electric to Building 3 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Actual Labor Cost | 2010-09-01: 16344.58; 2010-10-01: 16344.58; 2010-11-01: 16344.58; 2010-12-01: 15566.27
EC1050 | Electric to Building 3 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Budgeted Labor Cost | 2010-09-01: 15960; 2010-10-01: 15960; 2010-11-01: 15960; 2010-12-01: 15960; 2011-01-01: 2280
EC1050 | Electric to Building 3 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Actual Labor Units | 2010-09-01: 172; 2010-10-01: 172; 2010-11-01: 172; 2010-12-01: 164
EC1050 | Electric to Building 3 Power Vault | EC00610.7 | 100% | 01-Sep-10 A | 30-Dec-10 A | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 168; 2010-12-01: 168; 2011-01-01: 24
EC1100 | Storm Drainage Site Work | EC00610.7 | 100% | 01-Sep-10 A | 29-Dec-10 A | Actual Labor Cost | 2010-09-01: 18862.05; 2010-10-01: 18862.05; 2010-11-01: 18862.05; 2010-12-01: 17963.86
EC1100 | Storm Drainage Site Work | EC00610.7 | 100% | 01-Sep-10 A | 29-Dec-10 A | Budgeted Labor Cost | 2010-09-01: 17640; 2010-10-01: 17640; 2010-11-01: 17640; 2010-12-01: 17640; 2011-01-01: 5040
EC1100 | Storm Drainage Site Work | EC00610.7 | 100% | 01-Sep-10 A | 29-Dec-10 A | Actual Labor Units | 2010-09-01: 180; 2010-10-01: 180; 2010-11-01: 180; 2010-12-01: 171
EC1100 | Storm Drainage Site Work | EC00610.7 | 100% | 01-Sep-10 A | 29-Dec-10 A | Budgeted Labor Units | 2010-09-01: 168; 2010-10-01: 168; 2010-11-01: 168; 2010-12-01: 168; 2011-01-01: 48
EC1110 | Site Electrical Work & Temp Power | EC00610.7 | 100% | 01-Sep-10 A | 21-Sep-10 A | Actual Labor Cost | 2010-09-01: 11400
EC1110 | Site Electrical Work & Temp Power | EC00610.7 | 100% | 01-Sep-10 A | 21-Sep-10 A | Budgeted Labor Cost | 2010-09-01: 11400
EC1110 | Site Electrical Work & Temp Power | EC00610.7 | 100% | 01-Sep-10 A | 21-Sep-10 A | Actual Labor Units | 2010-09-01: 120
EC1110 | Site Electrical Work & Temp Power | EC00610.7 | 100% | 01-Sep-10 A | 21-Sep-10 A | Budgeted Labor Units | 2010-09-01: 120
EC1130 | Walkways | EC00610.7 | 100% | 15-Sep-10 A | 04-Feb-11 A | Actual Labor Cost | 2010-09-01: 3456; 2010-10-01: 6048; 2010-11-01: 6048; 2010-12-01: 6048; 2011-01-01: 6048; 2011-02-01: 1152
EC1130 | Walkways | EC00610.7 | 100% | 15-Sep-10 A | 04-Feb-11 A | Budgeted Labor Cost | 2010-09-01: 3840; 2010-10-01: 6720; 2010-11-01: 6720; 2010-12-01: 6720; 2011-01-01: 2880
EC1130 | Walkways | EC00610.7 | 100% | 15-Sep-10 A | 04-Feb-11 A | Actual Labor Units | 2010-09-01: 86; 2010-10-01: 151; 2010-11-01: 151; 2010-12-01: 151; 2011-01-01: 151; 2011-02-01: 29
EC1130 | Walkways | EC00610.7 | 100% | 15-Sep-10 A | 04-Feb-11 A | Budgeted Labor Units | 2010-09-01: 96; 2010-10-01: 168; 2010-11-01: 168; 2010-12-01: 168; 2011-01-01: 72
EC1200 | Roadway Pavers | EC00610.7 | 94.05% | 11-Jan-11 A | 2011-05-09 | Actual Labor Cost | 2011-01-01: 4010.13; 2011-02-01: 5346.84; 2011-03-01: 6148.86; 2011-04-01: 5614.18
EC1200 | Roadway Pavers | EC00610.7 | 94.05% | 11-Jan-11 A | 2011-05-09 | Budgeted Labor Cost | 2011-01-01: 3771.43; 2011-02-01: 5028.57; 2011-03-01: 5782.86; 2011-04-01: 5280; 2011-05-01: 1257.14
EC1200 | Roadway Pavers | EC00610.7 | 94.05% | 11-Jan-11 A | 2011-05-09 | Actual Labor Units | 2011-01-01: 100; 2011-02-01: 134; 2011-03-01: 154; 2011-04-01: 140
EC1200 | Roadway Pavers | EC00610.7 | 94.05% | 11-Jan-11 A | 2011-05-09 | Budgeted Labor Units | 2011-01-01: 94; 2011-02-01: 126; 2011-03-01: 145; 2011-04-01: 132; 2011-05-01: 31
EC1270 | Finish Paving, Striping and Signs | EC00610.7 | 0% | 2011-05-09 | 2011-08-02 | Actual Labor Cost
EC1270 | Finish Paving, Striping and Signs | EC00610.7 | 0% | 2011-05-09 | 2011-08-02 | Budgeted Labor Cost | 2011-05-01: 33280; 2011-06-01: 45760; 2011-07-01: 41600; 2011-08-01: 4160
EC1270 | Finish Paving, Striping and Signs | EC00610.7 | 0% | 2011-05-09 | 2011-08-02 | Actual Labor Units
EC1270 | Finish Paving, Striping and Signs | EC00610.7 | 0% | 2011-05-09 | 2011-08-02 | Budgeted Labor Units | 2011-05-01: 256; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 32
EC1440 | Electric to Building 2 Power Vault | EC00610.7 | 0% | 2011-09-21 | 2012-03-02 | Actual Labor Cost
EC1440 | Electric to Building 2 Power Vault | EC00610.7 | 0% | 2011-09-21 | 2012-03-02 | Budgeted Labor Cost | 2011-09-01: 5826.67; 2011-10-01: 15960; 2011-11-01: 15960; 2011-12-01: 15960; 2012-01-01: 15960; 2012-02-01: 15960; 2012-03-01: 1013.33
EC1440 | Electric to Building 2 Power Vault | EC00610.7 | 0% | 2011-09-21 | 2012-03-02 | Actual Labor Units
EC1440 | Electric to Building 2 Power Vault | EC00610.7 | 0% | 2011-09-21 | 2012-03-02 | Budgeted Labor Units | 2011-09-01: 61; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 11
EC1610 | Curbs & Paving | EC00610.7 | 0% | 2011-10-28 | 2012-02-10 | Actual Labor Cost
EC1610 | Curbs & Paving | EC00610.7 | 0% | 2011-10-28 | 2012-02-10 | Budgeted Labor Cost | 2011-10-01: 3120; 2011-11-01: 43680; 2011-12-01: 43680; 2012-01-01: 43680; 2012-02-01: 15600
EC1610 | Curbs & Paving | EC00610.7 | 0% | 2011-10-28 | 2012-02-10 | Actual Labor Units
EC1610 | Curbs & Paving | EC00610.7 | 0% | 2011-10-28 | 2012-02-10 | Budgeted Labor Units | 2011-10-01: 24; 2011-11-01: 336; 2011-12-01: 336; 2012-01-01: 336; 2012-02-01: 120
EC1750 | Electric to Building 1 Power Vault | EC00610.7 | 0% | 2011-10-26 | 2012-02-28 | Actual Labor Cost
EC1750 | Electric to Building 1 Power Vault | EC00610.7 | 0% | 2011-10-26 | 2012-02-28 | Budgeted Labor Cost | 2011-10-01: 6080; 2011-11-01: 31920; 2011-12-01: 31920; 2012-01-01: 31920; 2012-02-01: 30400
EC1750 | Electric to Building 1 Power Vault | EC00610.7 | 0% | 2011-10-26 | 2012-02-28 | Actual Labor Units
EC1750 | Electric to Building 1 Power Vault | EC00610.7 | 0% | 2011-10-26 | 2012-02-28 | Budgeted Labor Units | 2011-10-01: 64; 2011-11-01: 336; 2011-12-01: 336; 2012-01-01: 336; 2012-02-01: 320
EC2250 | Fountain/Water Feature | EC00610.7 | 0% | 2012-08-20 | 2013-03-13 | Actual Labor Cost
EC2250 | Fountain/Water Feature | EC00610.7 | 0% | 2012-08-20 | 2013-03-13 | Budgeted Labor Cost | 2012-08-01: 16800; 2012-09-01: 31920; 2012-10-01: 38640; 2012-11-01: 35280; 2012-12-01: 33600; 2013-01-01: 36960; 2013-02-01: 33600; 2013-03-01: 15120
EC2250 | Fountain/Water Feature | EC00610.7 | 0% | 2012-08-20 | 2013-03-13 | Actual Labor Units
EC2250 | Fountain/Water Feature | EC00610.7 | 0% | 2012-08-20 | 2013-03-13 | Budgeted Labor Units | 2012-08-01: 160; 2012-09-01: 304; 2012-10-01: 368; 2012-11-01: 336; 2012-12-01: 320; 2013-01-01: 352; 2013-02-01: 320; 2013-03-01: 144
EC2260 | Entry Feature/Sign Wall | EC00610.7 | 0% | 2012-08-24 | 2013-02-26 | Actual Labor Cost
EC2260 | Entry Feature/Sign Wall | EC00610.7 | 0% | 2012-08-24 | 2013-02-26 | Budgeted Labor Cost | 2012-08-01: 5184; 2012-09-01: 16416; 2012-10-01: 19872; 2012-11-01: 18144; 2012-12-01: 17280; 2013-01-01: 19008; 2013-02-01: 15552
EC2260 | Entry Feature/Sign Wall | EC00610.7 | 0% | 2012-08-24 | 2013-02-26 | Actual Labor Units
EC2260 | Entry Feature/Sign Wall | EC00610.7 | 0% | 2012-08-24 | 2013-02-26 | Budgeted Labor Units | 2012-08-01: 96; 2012-09-01: 304; 2012-10-01: 368; 2012-11-01: 336; 2012-12-01: 320; 2013-01-01: 352; 2013-02-01: 288
EC2290 | Curbs & Paving | EC00610.7 | 0% | 2012-08-24 | 2013-01-02 | Actual Labor Cost
EC2290 | Curbs & Paving | EC00610.7 | 0% | 2012-08-24 | 2013-01-02 | Budgeted Labor Cost | 2012-08-01: 12480; 2012-09-01: 39520; 2012-10-01: 47840; 2012-11-01: 43680; 2012-12-01: 41600; 2013-01-01: 2080
EC2290 | Curbs & Paving | EC00610.7 | 0% | 2012-08-24 | 2013-01-02 | Actual Labor Units
EC2290 | Curbs & Paving | EC00610.7 | 0% | 2012-08-24 | 2013-01-02 | Budgeted Labor Units | 2012-08-01: 96; 2012-09-01: 304; 2012-10-01: 368; 2012-11-01: 336; 2012-12-01: 320; 2013-01-01: 16
EC2340 | Curbs & Paving | EC00610.7 | 0% | 2012-12-28 | 2013-05-17 | Actual Labor Cost
EC2340 | Curbs & Paving | EC00610.7 | 0% | 2012-12-28 | 2013-05-17 | Budgeted Labor Cost | 2012-12-01: 1063.83; 2013-01-01: 22880; 2013-02-01: 20800; 2013-03-01: 21840; 2013-04-01: 22880; 2013-05-01: 13496.17
EC2340 | Curbs & Paving | EC00610.7 | 0% | 2012-12-28 | 2013-05-17 | Actual Labor Units
EC2340 | Curbs & Paving | EC00610.7 | 0% | 2012-12-28 | 2013-05-17 | Budgeted Labor Units | 2012-12-01: 8; 2013-01-01: 176; 2013-02-01: 160; 2013-03-01: 168; 2013-04-01: 176; 2013-05-01: 104
EC00610.8 Landscape & Irrigation |  |  | 5.59% | 08-Apr-11 A | 2014-09-24 | Actual Labor Cost | 2011-04-01: 4800
EC00610.8 Landscape & Irrigation |  |  | 5.59% | 08-Apr-11 A | 2014-09-24 | Budgeted Labor Cost | 2011-04-01: 5120; 2011-05-01: 6720; 2011-06-01: 7040; 2011-07-01: 320; 2013-05-01: 5270.27; 2013-06-01: 4864.86; 2013-07-01: 5351.35; 2013-08-01: 5171.17; 2013-09-01: 2702.7; 2013-10-01: 3108.11; 2013-11-01: 2702.7; 2013-12-01: 2837.84; 2014-01-01: 3108.11; 2014-02-01: 2702.7; 2014-03-01: 2837.84; 2014-04-01: 2972.97; 2014-05-01: 2972.97; 2014-06-01: 2837.84; 2014-07-01: 3108.11; 2014-08-01: 2837.84; 2014-09-01: 2342.34
EC00610.8 Landscape & Irrigation |  |  | 5.59% | 08-Apr-11 A | 2014-09-24 | Actual Labor Units | 2011-04-01: 120
EC00610.8 Landscape & Irrigation |  |  | 5.59% | 08-Apr-11 A | 2014-09-24 | Budgeted Labor Units | 2011-04-01: 128; 2011-05-01: 168; 2011-06-01: 176; 2011-07-01: 8; 2013-05-01: 117; 2013-06-01: 108; 2013-07-01: 119; 2013-08-01: 114; 2013-09-01: 54; 2013-10-01: 62; 2013-11-01: 54; 2013-12-01: 57; 2014-01-01: 62; 2014-02-01: 54; 2014-03-01: 57; 2014-04-01: 59; 2014-05-01: 59; 2014-06-01: 57; 2014-07-01: 62; 2014-08-01: 57; 2014-09-01: 47
EC1600 | Site Cleanup | EC00610.8 | 22.41% | 08-Apr-11 A | 2011-07-05 | Actual Labor Cost | 2011-04-01: 4800
EC1600 | Site Cleanup | EC00610.8 | 22.41% | 08-Apr-11 A | 2011-07-05 | Budgeted Labor Cost | 2011-04-01: 5120; 2011-05-01: 6720; 2011-06-01: 7040; 2011-07-01: 320
EC1600 | Site Cleanup | EC00610.8 | 22.41% | 08-Apr-11 A | 2011-07-05 | Actual Labor Units | 2011-04-01: 120
EC1600 | Site Cleanup | EC00610.8 | 22.41% | 08-Apr-11 A | 2011-07-05 | Budgeted Labor Units | 2011-04-01: 128; 2011-05-01: 168; 2011-06-01: 176; 2011-07-01: 8
EC2360 | Landscape & Irrigation | EC00610.8 | 0% | 2013-05-01 | 2014-09-24 | Actual Labor Cost
EC2360 | Landscape & Irrigation | EC00610.8 | 0% | 2013-05-01 | 2014-09-24 | Budgeted Labor Cost | 2013-05-01: 5270.27; 2013-06-01: 4864.86; 2013-07-01: 5351.35; 2013-08-01: 5171.17; 2013-09-01: 2702.7; 2013-10-01: 3108.11; 2013-11-01: 2702.7; 2013-12-01: 2837.84; 2014-01-01: 3108.11; 2014-02-01: 2702.7; 2014-03-01: 2837.84; 2014-04-01: 2972.97; 2014-05-01: 2972.97; 2014-06-01: 2837.84; 2014-07-01: 3108.11; 2014-08-01: 2837.84; 2014-09-01: 2342.34
EC2360 | Landscape & Irrigation | EC00610.8 | 0% | 2013-05-01 | 2014-09-24 | Actual Labor Units
EC2360 | Landscape & Irrigation | EC00610.8 | 0% | 2013-05-01 | 2014-09-24 | Budgeted Labor Units | 2013-05-01: 117; 2013-06-01: 108; 2013-07-01: 119; 2013-08-01: 114; 2013-09-01: 54; 2013-10-01: 62; 2013-11-01: 54; 2013-12-01: 57; 2014-01-01: 62; 2014-02-01: 54; 2014-03-01: 57; 2014-04-01: 59; 2014-05-01: 59; 2014-06-01: 57; 2014-07-01: 62; 2014-08-01: 57; 2014-09-01: 47
EC00620 Juniper Nursing Home |  |  | 12.8% | 01-Nov-10 A | 2014-01-08 | Actual Labor Cost | 2010-11-01: 123629.08; 2010-12-01: 128520.44; 2011-01-01: 115693.98; 2011-02-01: 55366.84; 2011-03-01: 25886.1; 2011-04-01: 33148.9
EC00620 Juniper Nursing Home |  |  | 12.8% | 01-Nov-10 A | 2014-01-08 | Budgeted Labor Cost |  |  | 114067.8 | 120107.8 | 111282.8 | 49293.84 | 29282.86 | 32965 | 38325.87 | 110571.73 | 121535.2 | 136306.14 | 208834.54 | 426493.17 | 438680.95 | 347273.01 | 240236.77 | 193349.77 | 206130.87 | 211480.44 | 189019 | 302783.9 | 320896 | 301449.51 | 238928.92 | 263644.58 | 172031.22 | 100773.49 | 19993.06 | 11407.03 | 4880.31 | 2972.97 | 2972.97 | 2702.7 | 2972.97 | 2972.97 | 2702.7 | 3108.11 | 2702.7 | 2837.84 | 756.76
EC00620 Juniper Nursing Home |  |  | 12.8% | 01-Nov-10 A | 2014-01-08 | Actual Labor Units | 2010-11-01: 1312; 2010-12-01: 1478; 2011-01-01: 1433; 2011-02-01: 814; 2011-03-01: 551; 2011-04-01: 775
EC00620 Juniper Nursing Home |  |  | 12.8% | 01-Nov-10 A | 2014-01-08 | Budgeted Labor Units |  |  | 1206 | 1382 | 1379 | 710 | 648 | 769 | 904 | 1770 | 1876 | 1944 | 2566 | 4658 | 4929 | 4012 | 2988 | 2621 | 2855 | 2774 | 2574 | 3703 | 3885 | 3695 | 3059 | 3401 | 2230 | 1528 | 417 | 222 | 93 | 59 | 59 | 54 | 59 | 59 | 54 | 62 | 54 | 57 | 15
EC1010 | Building Pad Delivered by Owner | EC00620 | 100% | 01-Nov-10 A |  | Actual Labor Cost
EC1010 | Building Pad Delivered by Owner | EC00620 | 100% | 01-Nov-10 A |  | Budgeted Labor Cost
EC1010 | Building Pad Delivered by Owner | EC00620 | 100% | 01-Nov-10 A |  | Actual Labor Units
EC1010 | Building Pad Delivered by Owner | EC00620 | 100% | 01-Nov-10 A |  | Budgeted Labor Units
EC1080 | Curbing | EC00620 | 100% | 02-Nov-10 A |  | Actual Labor Cost
EC1080 | Curbing | EC00620 | 100% | 02-Nov-10 A |  | Budgeted Labor Cost
EC1080 | Curbing | EC00620 | 100% | 02-Nov-10 A |  | Actual Labor Units
EC1080 | Curbing | EC00620 | 100% | 02-Nov-10 A |  | Budgeted Labor Units
EC2430 | Substantial Completion - All TCO | EC00620 | 0% |  | 2014-01-08 | Actual Labor Cost
EC2430 | Substantial Completion - All TCO | EC00620 | 0% |  | 2014-01-08 | Budgeted Labor Cost
EC2430 | Substantial Completion - All TCO | EC00620 | 0% |  | 2014-01-08 | Actual Labor Units
EC2430 | Substantial Completion - All TCO | EC00620 | 0% |  | 2014-01-08 | Budgeted Labor Units
EC00620.1 Building 1 |  |  | 5.3% | 02-Nov-10 A | 2014-01-08 | Actual Labor Cost | 2010-11-01: 17777.78; 2010-12-01: 18666.67; 2011-01-01: 8120.2; 2011-02-01: 5620.35; 2011-03-01: 6108.15; 2011-04-01: 5651.85
EC00620.1 Building 1 |  |  | 5.3% | 02-Nov-10 A | 2014-01-08 | Budgeted Labor Cost | 2010-11-01: 16000; 2010-12-01: 16800; 2011-01-01: 10255; 2011-02-01: 5425; 2011-03-01: 6440; 2011-04-01: 5880; 2011-05-01: 10640; 2011-06-01: 12320; 2011-07-01: 11200; 2011-08-01: 48372; 2011-09-01: 118182.59; 2011-10-01: 113217.64; 2011-11-01: 119469.94; 2011-12-01: 93970.87; 2012-01-01: 92191.89; 2012-02-01: 89114.72; 2012-03-01: 87244.98; 2012-04-01: 94591.64; 2012-05-01: 71740.57; 2012-06-01: 68479.64; 2012-07-01: 77735.78; 2012-08-01: 59108.61; 2012-09-01: 46233.27; 2012-10-01: 67803.53; 2012-11-01: 60517.27; 2012-12-01: 31673.05; 2013-01-01: 1900.38
EC00620.1 Building 1 |  |  | 5.3% | 02-Nov-10 A | 2014-01-08 | Actual Labor Units | 2010-11-01: 178; 2010-12-01: 187; 2011-01-01: 166; 2011-02-01: 161; 2011-03-01: 175; 2011-04-01: 161
EC00620.1 Building 1 |  |  | 5.3% | 02-Nov-10 A | 2014-01-08 | Budgeted Labor Units | 2010-11-01: 160; 2010-12-01: 168; 2011-01-01: 189; 2011-02-01: 155; 2011-03-01: 184; 2011-04-01: 168; 2011-05-01: 304; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 675; 2011-09-01: 1267; 2011-10-01: 1353; 2011-11-01: 1595; 2011-12-01: 1315; 2012-01-01: 1287; 2012-02-01: 1243; 2012-03-01: 1245; 2012-04-01: 1244; 2012-05-01: 1075; 2012-06-01: 1026; 2012-07-01: 1185; 2012-08-01: 846; 2012-09-01: 557; 2012-10-01: 787; 2012-11-01: 800; 2012-12-01: 564; 2013-01-01: 34
EC2440 | Complete Building 1 | EC00620.1 | 0% |  | 2014-01-08 | Actual Labor Cost
EC2440 | Complete Building 1 | EC00620.1 | 0% |  | 2014-01-08 | Budgeted Labor Cost
EC2440 | Complete Building 1 | EC00620.1 | 0% |  | 2014-01-08 | Actual Labor Units
EC2440 | Complete Building 1 | EC00620.1 | 0% |  | 2014-01-08 | Budgeted Labor Units
EC00620.1.1 Structure |  |  | 73.22% | 02-Nov-10 A | 2011-08-24 | Actual Labor Cost | 2010-11-01: 17777.78; 2010-12-01: 18666.67; 2011-01-01: 8120.2; 2011-02-01: 5620.35; 2011-03-01: 6108.15; 2011-04-01: 5651.85
EC00620.1.1 Structure |  |  | 73.22% | 02-Nov-10 A | 2011-08-24 | Budgeted Labor Cost | 2010-11-01: 16000; 2010-12-01: 16800; 2011-01-01: 10255; 2011-02-01: 5425; 2011-03-01: 6440; 2011-04-01: 5880; 2011-05-01: 10640; 2011-06-01: 12320; 2011-07-01: 11200; 2011-08-01: 9968
EC00620.1.1 Structure |  |  | 73.22% | 02-Nov-10 A | 2011-08-24 | Actual Labor Units | 2010-11-01: 178; 2010-12-01: 187; 2011-01-01: 166; 2011-02-01: 161; 2011-03-01: 175; 2011-04-01: 161
EC00620.1.1 Structure |  |  | 73.22% | 02-Nov-10 A | 2011-08-24 | Budgeted Labor Units | 2010-11-01: 160; 2010-12-01: 168; 2011-01-01: 189; 2011-02-01: 155; 2011-03-01: 184; 2011-04-01: 168; 2011-05-01: 304; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 285
EC1090 | Building Pad Including UG Utils | EC00620.1.1 | 100% | 02-Nov-10 A | 07-Jan-11 A | Actual Labor Cost | 2010-11-01: 17777.78; 2010-12-01: 18666.67; 2011-01-01: 3555.56
EC1090 | Building Pad Including UG Utils | EC00620.1.1 | 100% | 02-Nov-10 A | 07-Jan-11 A | Budgeted Labor Cost | 2010-11-01: 16000; 2010-12-01: 16800; 2011-01-01: 5600
EC1090 | Building Pad Including UG Utils | EC00620.1.1 | 100% | 02-Nov-10 A | 07-Jan-11 A | Actual Labor Units | 2010-11-01: 178; 2010-12-01: 187; 2011-01-01: 36
EC1090 | Building Pad Including UG Utils | EC00620.1.1 | 100% | 02-Nov-10 A | 07-Jan-11 A | Budgeted Labor Units | 2010-11-01: 160; 2010-12-01: 168; 2011-01-01: 56
EC1140 | First Floor Masonry Structure | EC00620.1.1 | 100% | 06-Jan-11 A | 26-Jan-11 A | Actual Labor Cost | 2011-01-01: 3150
EC1140 | First Floor Masonry Structure | EC00620.1.1 | 100% | 06-Jan-11 A | 26-Jan-11 A | Budgeted Labor Cost | 2011-01-01: 3360
EC1140 | First Floor Masonry Structure | EC00620.1.1 | 100% | 06-Jan-11 A | 26-Jan-11 A | Actual Labor Units | 2011-01-01: 90
EC1140 | First Floor Masonry Structure | EC00620.1.1 | 100% | 06-Jan-11 A | 26-Jan-11 A | Budgeted Labor Units | 2011-01-01: 96
EC1170 | Second Floor Slab & Collar Beam | EC00620.1.1 | 100% | 25-Jan-11 A | 25-Feb-11 A | Actual Labor Cost | 2011-01-01: 1414.65; 2011-02-01: 5620.35
EC1170 | Second Floor Slab & Collar Beam | EC00620.1.1 | 100% | 25-Jan-11 A | 25-Feb-11 A | Budgeted Labor Cost | 2011-01-01: 1295; 2011-02-01: 5425
EC1170 | Second Floor Slab & Collar Beam | EC00620.1.1 | 100% | 25-Jan-11 A | 25-Feb-11 A | Actual Labor Units | 2011-01-01: 40; 2011-02-01: 161
EC1170 | Second Floor Slab & Collar Beam | EC00620.1.1 | 100% | 25-Jan-11 A | 25-Feb-11 A | Budgeted Labor Units | 2011-01-01: 37; 2011-02-01: 155
EC1190 | Second Floor Masonry Structure | EC00620.1.1 | 100% | 02-Mar-11 A | 18-Mar-11 A | Actual Labor Cost | 2011-03-01: 2940
EC1190 | Second Floor Masonry Structure | EC00620.1.1 | 100% | 02-Mar-11 A | 18-Mar-11 A | Budgeted Labor Cost | 2011-03-01: 3360
EC1190 | Second Floor Masonry Structure | EC00620.1.1 | 100% | 02-Mar-11 A | 18-Mar-11 A | Actual Labor Units | 2011-03-01: 84
EC1190 | Second Floor Masonry Structure | EC00620.1.1 | 100% | 02-Mar-11 A | 18-Mar-11 A | Budgeted Labor Units | 2011-03-01: 96
EC1210 | Third Floor Slab & Collar Beam | EC00620.1.1 | 100% | 15-Mar-11 A | 21-Apr-11 A | Actual Labor Cost | 2011-03-01: 3168.15; 2011-04-01: 3411.85
EC1210 | Third Floor Slab & Collar Beam | EC00620.1.1 | 100% | 15-Mar-11 A | 21-Apr-11 A | Budgeted Labor Cost | 2011-03-01: 3080; 2011-04-01: 3640
EC1210 | Third Floor Slab & Collar Beam | EC00620.1.1 | 100% | 15-Mar-11 A | 21-Apr-11 A | Actual Labor Units | 2011-03-01: 91; 2011-04-01: 97
EC1210 | Third Floor Slab & Collar Beam | EC00620.1.1 | 100% | 15-Mar-11 A | 21-Apr-11 A | Budgeted Labor Units | 2011-03-01: 88; 2011-04-01: 104
EC1240 | Third Floor Masonry Structure | EC00620.1.1 | 75% | 20-Apr-11 A | 2011-05-06 | Actual Labor Cost | 2011-04-01: 2240
EC1240 | Third Floor Masonry Structure | EC00620.1.1 | 75% | 20-Apr-11 A | 2011-05-06 | Budgeted Labor Cost | 2011-04-01: 2240; 2011-05-01: 1120
EC1240 | Third Floor Masonry Structure | EC00620.1.1 | 75% | 20-Apr-11 A | 2011-05-06 | Actual Labor Units | 2011-04-01: 64
EC1240 | Third Floor Masonry Structure | EC00620.1.1 | 75% | 20-Apr-11 A | 2011-05-06 | Budgeted Labor Units | 2011-04-01: 64; 2011-05-01: 32
EC1250 | Fourth Floor Slab & Collar Beam | EC00620.1.1 | 0% | 2011-05-06 | 2011-06-10 | Actual Labor Cost
EC1250 | Fourth Floor Slab & Collar Beam | EC00620.1.1 | 0% | 2011-05-06 | 2011-06-10 | Budgeted Labor Cost | 2011-05-01: 9520; 2011-06-01: 3920
EC1250 | Fourth Floor Slab & Collar Beam | EC00620.1.1 | 0% | 2011-05-06 | 2011-06-10 | Actual Labor Units
EC1250 | Fourth Floor Slab & Collar Beam | EC00620.1.1 | 0% | 2011-05-06 | 2011-06-10 | Budgeted Labor Units | 2011-05-01: 272; 2011-06-01: 112
EC1300 | Fourth Floor Masonry Structure | EC00620.1.1 | 0% | 2011-06-10 | 2011-06-28 | Actual Labor Cost
EC1300 | Fourth Floor Masonry Structure | EC00620.1.1 | 0% | 2011-06-10 | 2011-06-28 | Budgeted Labor Cost | 2011-06-01: 6720
EC1300 | Fourth Floor Masonry Structure | EC00620.1.1 | 0% | 2011-06-10 | 2011-06-28 | Actual Labor Units
EC1300 | Fourth Floor Masonry Structure | EC00620.1.1 | 0% | 2011-06-10 | 2011-06-28 | Budgeted Labor Units | 2011-06-01: 192
EC1310 | Roof Slab | EC00620.1.1 | 0% | 2011-06-28 | 2011-08-02 | Actual Labor Cost
EC1310 | Roof Slab | EC00620.1.1 | 0% | 2011-06-28 | 2011-08-02 | Budgeted Labor Cost | 2011-06-01: 1680; 2011-07-01: 11200; 2011-08-01: 560
EC1310 | Roof Slab | EC00620.1.1 | 0% | 2011-06-28 | 2011-08-02 | Actual Labor Units
EC1310 | Roof Slab | EC00620.1.1 | 0% | 2011-06-28 | 2011-08-02 | Budgeted Labor Units | 2011-06-01: 48; 2011-07-01: 320; 2011-08-01: 16
EC1340 | Stair and Elevator Masonry Structure | EC00620.1.1 | 0% | 2011-08-02 | 2011-08-08 | Actual Labor Cost
EC1340 | Stair and Elevator Masonry Structure | EC00620.1.1 | 0% | 2011-08-02 | 2011-08-08 | Budgeted Labor Cost | 2011-08-01: 2688
EC1340 | Stair and Elevator Masonry Structure | EC00620.1.1 | 0% | 2011-08-02 | 2011-08-08 | Actual Labor Units
EC1340 | Stair and Elevator Masonry Structure | EC00620.1.1 | 0% | 2011-08-02 | 2011-08-08 | Budgeted Labor Units | 2011-08-01: 77
EC1350 | Roof Slab/Collar Beam | EC00620.1.1 | 0% | 2011-08-08 | 2011-08-24 | Actual Labor Cost
EC1350 | Roof Slab/Collar Beam | EC00620.1.1 | 0% | 2011-08-08 | 2011-08-24 | Budgeted Labor Cost | 2011-08-01: 6720
EC1350 | Roof Slab/Collar Beam | EC00620.1.1 | 0% | 2011-08-08 | 2011-08-24 | Actual Labor Units
EC1350 | Roof Slab/Collar Beam | EC00620.1.1 | 0% | 2011-08-08 | 2011-08-24 | Budgeted Labor Units | 2011-08-01: 192
EC00620.1.2 Roof |  |  | 0% | 2011-08-24 | 2011-12-02 | Actual Labor Cost
EC00620.1.2 Roof |  |  | 0% | 2011-08-24 | 2011-12-02 | Budgeted Labor Cost | 2011-08-01: 21892; 2011-09-01: 83378; 2011-10-01: 50400; 2011-11-01: 37605; 2011-12-01: 1605
EC00620.1.2 Roof |  |  | 0% | 2011-08-24 | 2011-12-02 | Actual Labor Units
EC00620.1.2 Roof |  |  | 0% | 2011-08-24 | 2011-12-02 | Budgeted Labor Units | 2011-08-01: 253; 2011-09-01: 972; 2011-10-01: 672; 2011-11-01: 501; 2011-12-01: 21
EC1390 | Place Roof Trusses and Sheathing | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Actual Labor Cost
EC1390 | Place Roof Trusses and Sheathing | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Budgeted Labor Cost | 2011-08-01: 15577; 2011-09-01: 55463
EC1390 | Place Roof Trusses and Sheathing | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Actual Labor Units
EC1390 | Place Roof Trusses and Sheathing | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Budgeted Labor Units | 2011-08-01: 168; 2011-09-01: 600
EC1400 | Place Mechanical Equipment Supports | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Actual Labor Cost
EC1400 | Place Mechanical Equipment Supports | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Budgeted Labor Cost | 2011-08-01: 6315; 2011-09-01: 22485
EC1400 | Place Mechanical Equipment Supports | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Actual Labor Units
EC1400 | Place Mechanical Equipment Supports | EC00620.1.2 | 0% | 2011-08-24 | 2011-09-28 | Budgeted Labor Units | 2011-08-01: 84; 2011-09-01: 300
EC1530 | Built-Up Asphalt Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-11-15 | Actual Labor Cost
EC1530 | Built-Up Asphalt Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-11-15 | Budgeted Labor Cost | 2011-09-01: 2715; 2011-10-01: 25200; 2011-11-01: 12405
EC1530 | Built-Up Asphalt Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-11-15 | Actual Labor Units
EC1530 | Built-Up Asphalt Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-11-15 | Budgeted Labor Units | 2011-09-01: 36; 2011-10-01: 336; 2011-11-01: 165
EC1540 | Felt and Tile Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-12-02 | Actual Labor Cost
EC1540 | Felt and Tile Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-12-02 | Budgeted Labor Cost | 2011-09-01: 2715; 2011-10-01: 25200; 2011-11-01: 25200; 2011-12-01: 1605
EC1540 | Felt and Tile Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-12-02 | Actual Labor Units
EC1540 | Felt and Tile Roofing | EC00620.1.2 | 0% | 2011-09-28 | 2011-12-02 | Budgeted Labor Units | 2011-09-01: 36; 2011-10-01: 336; 2011-11-01: 336; 2011-12-01: 21
EC1780 | Roof Complete | EC00620.1.2 | 0% |  | 2011-12-02 | Actual Labor Cost
EC1780 | Roof Complete | EC00620.1.2 | 0% |  | 2011-12-02 | Budgeted Labor Cost
EC1780 | Roof Complete | EC00620.1.2 | 0% |  | 2011-12-02 | Actual Labor Units
EC1780 | Roof Complete | EC00620.1.2 | 0% |  | 2011-12-02 | Budgeted Labor Units
EC00620.1.3 Envelope |  |  | 0% | 2011-08-08 | 2012-04-27 | Actual Labor Cost
EC00620.1.3 Envelope |  |  | 0% | 2011-08-08 | 2012-04-27 | Budgeted Labor Cost | 2011-08-01: 16512; 2011-09-01: 34176; 2011-10-01: 44736; 2011-11-01: 34752; 2011-12-01: 20160; 2012-01-01: 20160; 2012-02-01: 20160; 2012-03-01: 27264; 2012-04-01: 26112
EC00620.1.3 Envelope |  |  | 0% | 2011-08-08 | 2012-04-27 | Actual Labor Units
EC00620.1.3 Envelope |  |  | 0% | 2011-08-08 | 2012-04-27 | Budgeted Labor Units | 2011-08-01: 138; 2011-09-01: 285; 2011-10-01: 373; 2011-11-01: 290; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 267; 2012-04-01: 218
EC1360 | Mobilize Scaffolding | EC00620.1.3 | 0% | 2011-08-08 | 2011-08-24 | Actual Labor Cost
EC1360 | Mobilize Scaffolding | EC00620.1.3 | 0% | 2011-08-08 | 2011-08-24 | Budgeted Labor Cost | 2011-08-01: 11520
EC1360 | Mobilize Scaffolding | EC00620.1.3 | 0% | 2011-08-08 | 2011-08-24 | Actual Labor Units
EC1360 | Mobilize Scaffolding | EC00620.1.3 | 0% | 2011-08-08 | 2011-08-24 | Budgeted Labor Units | 2011-08-01: 96
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.1.3 | 0% | 2011-08-24 | 2011-09-22 | Actual Labor Cost
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.1.3 | 0% | 2011-08-24 | 2011-09-22 | Budgeted Labor Cost | 2011-08-01: 4992; 2011-09-01: 13440
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.1.3 | 0% | 2011-08-24 | 2011-09-22 | Actual Labor Units
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.1.3 | 0% | 2011-08-24 | 2011-09-22 | Budgeted Labor Units | 2011-08-01: 42; 2011-09-01: 112
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.1.3 | 0% | 2011-09-15 | 2011-10-12 | Actual Labor Cost
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.1.3 | 0% | 2011-09-15 | 2011-10-12 | Budgeted Labor Cost | 2011-09-01: 11520; 2011-10-01: 6912
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.1.3 | 0% | 2011-09-15 | 2011-10-12 | Actual Labor Units
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.1.3 | 0% | 2011-09-15 | 2011-10-12 | Budgeted Labor Units | 2011-09-01: 96; 2011-10-01: 58
EC1490 | Install Backing & Cauld Windows Floor1 | EC00620.1.3 | 0% | 2011-09-16 | 2011-09-29 | Actual Labor Cost
EC1490 | Install Backing & Cauld Windows Floor1 | EC00620.1.3 | 0% | 2011-09-16 | 2011-09-29 | Budgeted Labor Cost | 2011-09-01: 9216
EC1490 | Install Backing & Cauld Windows Floor1 | EC00620.1.3 | 0% | 2011-09-16 | 2011-09-29 | Actual Labor Units
EC1490 | Install Backing & Cauld Windows Floor1 | EC00620.1.3 | 0% | 2011-09-16 | 2011-09-29 | Budgeted Labor Units | 2011-09-01: 77
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.1.3 | 0% | 2011-10-05 | 2011-10-28 | Actual Labor Cost
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.1.3 | 0% | 2011-10-05 | 2011-10-28 | Budgeted Labor Cost | 2011-10-01: 16128
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.1.3 | 0% | 2011-10-05 | 2011-10-28 | Actual Labor Units
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.1.3 | 0% | 2011-10-05 | 2011-10-28 | Budgeted Labor Units | 2011-10-01: 134
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00620.1.3 | 0% | 2011-10-06 | 2011-10-19 | Actual Labor Cost
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00620.1.3 | 0% | 2011-10-06 | 2011-10-19 | Budgeted Labor Cost | 2011-10-01: 9216
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00620.1.3 | 0% | 2011-10-06 | 2011-10-19 | Actual Labor Units
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00620.1.3 | 0% | 2011-10-06 | 2011-10-19 | Budgeted Labor Units | 2011-10-01: 77
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.1.3 | 0% | 2011-10-21 | 2011-11-21 | Actual Labor Cost
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.1.3 | 0% | 2011-10-21 | 2011-11-21 | Budgeted Labor Cost | 2011-10-01: 6720; 2011-11-01: 14016
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.1.3 | 0% | 2011-10-21 | 2011-11-21 | Actual Labor Units
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.1.3 | 0% | 2011-10-21 | 2011-11-21 | Budgeted Labor Units | 2011-10-01: 56; 2011-11-01: 117
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00620.1.3 | 0% | 2011-10-24 | 2011-11-02 | Actual Labor Cost
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00620.1.3 | 0% | 2011-10-24 | 2011-11-02 | Budgeted Labor Cost | 2011-10-01: 5760; 2011-11-01: 1152
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00620.1.3 | 0% | 2011-10-24 | 2011-11-02 | Actual Labor Units
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00620.1.3 | 0% | 2011-10-24 | 2011-11-02 | Budgeted Labor Units | 2011-10-01: 48; 2011-11-01: 10
EC1580 | Stucco Bands | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-29 | Actual Labor Cost
EC1580 | Stucco Bands | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-29 | Budgeted Labor Cost | 2011-11-01: 9216
EC1580 | Stucco Bands | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-29 | Actual Labor Units
EC1580 | Stucco Bands | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-29 | Budgeted Labor Units | 2011-11-01: 77
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-30 | Actual Labor Cost
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-30 | Budgeted Labor Cost | 2011-11-01: 9216
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-30 | Actual Labor Units
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00620.1.3 | 0% | 2011-11-15 | 2011-11-30 | Budgeted Labor Units | 2011-11-01: 77
EC1660 | Stucco Grey | EC00620.1.3 | 0% | 2011-11-29 | 2011-12-27 | Actual Labor Cost
EC1660 | Stucco Grey | EC00620.1.3 | 0% | 2011-11-29 | 2011-12-27 | Budgeted Labor Cost | 2011-11-01: 1152; 2011-12-01: 17280
EC1660 | Stucco Grey | EC00620.1.3 | 0% | 2011-11-29 | 2011-12-27 | Actual Labor Units
EC1660 | Stucco Grey | EC00620.1.3 | 0% | 2011-11-29 | 2011-12-27 | Budgeted Labor Units | 2011-11-01: 10; 2011-12-01: 144
EC1690 | Stucco Finish Coat | EC00620.1.3 | 0% | 2011-12-28 | 2012-01-31 | Actual Labor Cost
EC1690 | Stucco Finish Coat | EC00620.1.3 | 0% | 2011-12-28 | 2012-01-31 | Budgeted Labor Cost | 2011-12-01: 2880; 2012-01-01: 20160
EC1690 | Stucco Finish Coat | EC00620.1.3 | 0% | 2011-12-28 | 2012-01-31 | Actual Labor Units
EC1690 | Stucco Finish Coat | EC00620.1.3 | 0% | 2011-12-28 | 2012-01-31 | Budgeted Labor Units | 2011-12-01: 24; 2012-01-01: 168
EC1840 | Caulk | EC00620.1.3 | 0% | 2012-02-01 | 2012-02-14 | Actual Labor Cost
EC1840 | Caulk | EC00620.1.3 | 0% | 2012-02-01 | 2012-02-14 | Budgeted Labor Cost | 2012-02-01: 9216
EC1840 | Caulk | EC00620.1.3 | 0% | 2012-02-01 | 2012-02-14 | Actual Labor Units
EC1840 | Caulk | EC00620.1.3 | 0% | 2012-02-01 | 2012-02-14 | Budgeted Labor Units | 2012-02-01: 77
EC1900 | Stucco Band Trim | EC00620.1.3 | 0% | 2012-02-14 | 2012-03-01 | Actual Labor Cost
EC1900 | Stucco Band Trim | EC00620.1.3 | 0% | 2012-02-14 | 2012-03-01 | Budgeted Labor Cost | 2012-02-01: 10944; 2012-03-01: 576
EC1900 | Stucco Band Trim | EC00620.1.3 | 0% | 2012-02-14 | 2012-03-01 | Actual Labor Units
EC1900 | Stucco Band Trim | EC00620.1.3 | 0% | 2012-02-14 | 2012-03-01 | Budgeted Labor Units | 2012-02-01: 91; 2012-03-01: 5
EC1980 | Paint Exterior | EC00620.1.3 | 0% | 2012-03-08 | 2012-03-26 | Actual Labor Cost
EC1980 | Paint Exterior | EC00620.1.3 | 0% | 2012-03-08 | 2012-03-26 | Budgeted Labor Cost | 2012-03-01: 6720
EC1980 | Paint Exterior | EC00620.1.3 | 0% | 2012-03-08 | 2012-03-26 | Actual Labor Units
EC1980 | Paint Exterior | EC00620.1.3 | 0% | 2012-03-08 | 2012-03-26 | Budgeted Labor Units | 2012-03-01: 96
EC1990 | Install Railings | EC00620.1.3 | 0% | 2012-03-08 | 2012-04-27 | Actual Labor Cost
EC1990 | Install Railings | EC00620.1.3 | 0% | 2012-03-08 | 2012-04-27 | Budgeted Labor Cost | 2012-03-01: 15744; 2012-04-01: 18816
EC1990 | Install Railings | EC00620.1.3 | 0% | 2012-03-08 | 2012-04-27 | Actual Labor Units
EC1990 | Install Railings | EC00620.1.3 | 0% | 2012-03-08 | 2012-04-27 | Budgeted Labor Units | 2012-03-01: 131; 2012-04-01: 157
EC2110 | Demobilize Scaffolding | EC00620.1.3 | 0% | 2012-03-26 | 2012-04-11 | Actual Labor Cost
EC2110 | Demobilize Scaffolding | EC00620.1.3 | 0% | 2012-03-26 | 2012-04-11 | Budgeted Labor Cost | 2012-03-01: 4224; 2012-04-01: 7296
EC2110 | Demobilize Scaffolding | EC00620.1.3 | 0% | 2012-03-26 | 2012-04-11 | Actual Labor Units
EC2110 | Demobilize Scaffolding | EC00620.1.3 | 0% | 2012-03-26 | 2012-04-11 | Budgeted Labor Units | 2012-03-01: 35; 2012-04-01: 61
EC2140 | Shell Complete | EC00620.1.3 | 0% |  | 2012-04-27 | Actual Labor Cost
EC2140 | Shell Complete | EC00620.1.3 | 0% |  | 2012-04-27 | Budgeted Labor Cost
EC2140 | Shell Complete | EC00620.1.3 | 0% |  | 2012-04-27 | Actual Labor Units
EC2140 | Shell Complete | EC00620.1.3 | 0% |  | 2012-04-27 | Budgeted Labor Units
EC00620.1.4 Interior Finishes |  |  | 0% | 2011-09-28 | 2013-01-03 | Actual Labor Cost
EC00620.1.4 Interior Finishes |  |  | 0% | 2011-09-28 | 2013-01-03 | Budgeted Labor Cost | 2011-09-01: 628.59; 2011-10-01: 18081.64; 2011-11-01: 47112.94; 2011-12-01: 72205.87; 2012-01-01: 72031.89; 2012-02-01: 68954.72; 2012-03-01: 57539.28; 2012-04-01: 47550.82; 2012-05-01: 49815.15; 2012-06-01: 47550.82; 2012-07-01: 56806.97; 2012-08-01: 36186.57; 2012-09-01: 14088.68; 2012-10-01: 17054.72; 2012-11-01: 27694.27; 2012-12-01: 31673.05; 2013-01-01: 1900.38
EC00620.1.4 Interior Finishes |  |  | 0% | 2011-09-28 | 2013-01-03 | Actual Labor Units
EC00620.1.4 Interior Finishes |  |  | 0% | 2011-09-28 | 2013-01-03 | Budgeted Labor Units | 2011-09-01: 11; 2011-10-01: 308; 2011-11-01: 804; 2011-12-01: 1125; 2012-01-01: 1119; 2012-02-01: 1075; 2012-03-01: 955; 2012-04-01: 827; 2012-05-01: 866; 2012-06-01: 827; 2012-07-01: 986; 2012-08-01: 627; 2012-09-01: 251; 2012-10-01: 304; 2012-11-01: 487; 2012-12-01: 564; 2013-01-01: 34
EC1550 | Unit Finishes Building North - Floor 1 | EC00620.1.4 | 0% | 2011-09-28 | 2012-07-06 | Actual Labor Cost
EC1550 | Unit Finishes Building North - Floor 1 | EC00620.1.4 | 0% | 2011-09-28 | 2012-07-06 | Budgeted Labor Cost | 2011-09-01: 628.59; 2011-10-01: 6000.13; 2011-11-01: 6000.13; 2011-12-01: 6000.13; 2012-01-01: 5367.06; 2012-02-01: 5354.77; 2012-03-01: 5609.76; 2012-04-01: 5354.77; 2012-05-01: 5609.76; 2012-06-01: 5354.77; 2012-07-01: 917.96
EC1550 | Unit Finishes Building North - Floor 1 | EC00620.1.4 | 0% | 2011-09-28 | 2012-07-06 | Actual Labor Units
EC1550 | Unit Finishes Building North - Floor 1 | EC00620.1.4 | 0% | 2011-09-28 | 2012-07-06 | Budgeted Labor Units | 2011-09-01: 11; 2011-10-01: 102; 2011-11-01: 102; 2011-12-01: 102; 2012-01-01: 93; 2012-02-01: 93; 2012-03-01: 98; 2012-04-01: 93; 2012-05-01: 98; 2012-06-01: 93; 2012-07-01: 16
EC1630 | Unit Finishes Building South - Floor 1 | EC00620.1.4 | 0% | 2011-10-05 | 2012-07-18 | Actual Labor Cost
EC1630 | Unit Finishes Building South - Floor 1 | EC00620.1.4 | 0% | 2011-10-05 | 2012-07-18 | Budgeted Labor Cost | 2011-10-01: 5137.46; 2011-11-01: 5927.84; 2011-12-01: 5927.84; 2012-01-01: 5478.49; 2012-02-01: 5290.25; 2012-03-01: 5542.17; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 2771.09
EC1630 | Unit Finishes Building South - Floor 1 | EC00620.1.4 | 0% | 2011-10-05 | 2012-07-18 | Actual Labor Units
EC1630 | Unit Finishes Building South - Floor 1 | EC00620.1.4 | 0% | 2011-10-05 | 2012-07-18 | Budgeted Labor Units | 2011-10-01: 88; 2011-11-01: 101; 2011-12-01: 101; 2012-01-01: 95; 2012-02-01: 92; 2012-03-01: 96; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 48
EC1670 | Unit Finishes Building North - Floor 2 | EC00620.1.4 | 0% | 2011-10-12 | 2012-07-25 | Actual Labor Cost
EC1670 | Unit Finishes Building North - Floor 2 | EC00620.1.4 | 0% | 2011-10-12 | 2012-07-25 | Budgeted Labor Cost | 2011-10-01: 3726.07; 2011-11-01: 5927.84; 2011-12-01: 5927.84; 2012-01-01: 5630.3; 2012-02-01: 5290.25; 2012-03-01: 5542.17; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 4030.67
EC1670 | Unit Finishes Building North - Floor 2 | EC00620.1.4 | 0% | 2011-10-12 | 2012-07-25 | Actual Labor Units
EC1670 | Unit Finishes Building North - Floor 2 | EC00620.1.4 | 0% | 2011-10-12 | 2012-07-25 | Budgeted Labor Units | 2011-10-01: 64; 2011-11-01: 101; 2011-12-01: 101; 2012-01-01: 97; 2012-02-01: 92; 2012-03-01: 96; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 70
EC1700 | Unit Finishes Building South - Floor 2 | EC00620.1.4 | 0% | 2011-10-19 | 2012-08-01 | Actual Labor Cost
EC1700 | Unit Finishes Building South - Floor 2 | EC00620.1.4 | 0% | 2011-10-19 | 2012-08-01 | Budgeted Labor Cost | 2011-10-01: 2314.68; 2011-11-01: 5927.84; 2011-12-01: 5927.84; 2012-01-01: 5782.11; 2012-02-01: 5290.25; 2012-03-01: 5542.17; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 5290.25
EC1700 | Unit Finishes Building South - Floor 2 | EC00620.1.4 | 0% | 2011-10-19 | 2012-08-01 | Actual Labor Units
EC1700 | Unit Finishes Building South - Floor 2 | EC00620.1.4 | 0% | 2011-10-19 | 2012-08-01 | Budgeted Labor Units | 2011-10-01: 39; 2011-11-01: 101; 2011-12-01: 101; 2012-01-01: 99; 2012-02-01: 92; 2012-03-01: 96; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 92
EC1790 | Unit Finishes Building North - Floor 3 | EC00620.1.4 | 0% | 2011-10-26 | 2012-08-08 | Actual Labor Cost
EC1790 | Unit Finishes Building North - Floor 3 | EC00620.1.4 | 0% | 2011-10-26 | 2012-08-08 | Budgeted Labor Cost | 2011-10-01: 903.29; 2011-11-01: 5927.84; 2011-12-01: 5927.84; 2012-01-01: 5927.84; 2012-02-01: 5296.32; 2012-03-01: 5542.17; 2012-04-01: 5290.25; 2012-05-01: 5542.17; 2012-06-01: 5290.25; 2012-07-01: 5290.25; 2012-08-01: 1259.59
EC1790 | Unit Finishes Building North - Floor 3 | EC00620.1.4 | 0% | 2011-10-26 | 2012-08-08 | Actual Labor Units
EC1790 | Unit Finishes Building North - Floor 3 | EC00620.1.4 | 0% | 2011-10-26 | 2012-08-08 | Budgeted Labor Units | 2011-10-01: 15; 2011-11-01: 101; 2011-12-01: 101; 2012-01-01: 101; 2012-02-01: 92; 2012-03-01: 96; 2012-04-01: 92; 2012-05-01: 96; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 22
EC1820 | Building 2 Elevators Complete | EC00620.1.4 | 0% | 2011-12-02 | 2012-03-12 | Actual Labor Cost
EC1820 | Building 2 Elevators Complete | EC00620.1.4 | 0% | 2011-12-02 | 2012-03-12 | Budgeted Labor Cost | 2011-12-01: 18924.14; 2012-01-01: 20275.86; 2012-02-01: 20275.86; 2012-03-01: 7724.14
EC1820 | Building 2 Elevators Complete | EC00620.1.4 | 0% | 2011-12-02 | 2012-03-12 | Actual Labor Units
EC1820 | Building 2 Elevators Complete | EC00620.1.4 | 0% | 2011-12-02 | 2012-03-12 | Budgeted Labor Units | 2011-12-01: 216; 2012-01-01: 232; 2012-02-01: 232; 2012-03-01: 88
EC1850 | Unit Finishes Building South - Floor 3 | EC00620.1.4 | 0% | 2011-11-02 | 2012-08-15 | Actual Labor Cost
EC1850 | Unit Finishes Building South - Floor 3 | EC00620.1.4 | 0% | 2011-11-02 | 2012-08-15 | Budgeted Labor Cost | 2011-11-01: 10874.77; 2011-12-01: 11855.68; 2012-01-01: 11855.68; 2012-02-01: 10892.47; 2012-03-01: 11084.34; 2012-04-01: 10580.5; 2012-05-01: 11084.34; 2012-06-01: 10580.5; 2012-07-01: 10580.5; 2012-08-01: 5006.85
EC1850 | Unit Finishes Building South - Floor 3 | EC00620.1.4 | 0% | 2011-11-02 | 2012-08-15 | Actual Labor Units
EC1850 | Unit Finishes Building South - Floor 3 | EC00620.1.4 | 0% | 2011-11-02 | 2012-08-15 | Budgeted Labor Units | 2011-11-01: 185; 2011-12-01: 202; 2012-01-01: 202; 2012-02-01: 188; 2012-03-01: 193; 2012-04-01: 184; 2012-05-01: 193; 2012-06-01: 184; 2012-07-01: 184; 2012-08-01: 87
EC1910 | Unit Finishes Building North - Floor 4 | EC00620.1.4 | 0% | 2011-11-09 | 2012-08-24 | Actual Labor Cost
EC1910 | Unit Finishes Building North - Floor 4 | EC00620.1.4 | 0% | 2011-11-09 | 2012-08-24 | Budgeted Labor Cost | 2011-11-01: 3960.63; 2011-12-01: 5857.27; 2012-01-01: 5857.27; 2012-02-01: 5557.27; 2012-03-01: 5476.19; 2012-04-01: 5227.27; 2012-05-01: 5476.19; 2012-06-01: 5227.27; 2012-07-01: 5227.27; 2012-08-01: 4331.17
EC1910 | Unit Finishes Building North - Floor 4 | EC00620.1.4 | 0% | 2011-11-09 | 2012-08-24 | Actual Labor Units
EC1910 | Unit Finishes Building North - Floor 4 | EC00620.1.4 | 0% | 2011-11-09 | 2012-08-24 | Budgeted Labor Units | 2011-11-01: 68; 2011-12-01: 100; 2012-01-01: 100; 2012-02-01: 96; 2012-03-01: 95; 2012-04-01: 91; 2012-05-01: 95; 2012-06-01: 91; 2012-07-01: 91; 2012-08-01: 75
EC1950 | Unit Finishes Building South - Floor 4 | EC00620.1.4 | 0% | 2011-11-16 | 2012-08-31 | Actual Labor Cost
EC1950 | Unit Finishes Building South - Floor 4 | EC00620.1.4 | 0% | 2011-11-16 | 2012-08-31 | Budgeted Labor Cost | 2011-11-01: 2566.04; 2011-12-01: 5857.27; 2012-01-01: 5857.27; 2012-02-01: 5707.27; 2012-03-01: 5476.19; 2012-04-01: 5227.27; 2012-05-01: 5476.19; 2012-06-01: 5227.27; 2012-07-01: 5227.27; 2012-08-01: 5575.76
EC1950 | Unit Finishes Building South - Floor 4 | EC00620.1.4 | 0% | 2011-11-16 | 2012-08-31 | Actual Labor Units
EC1950 | Unit Finishes Building South - Floor 4 | EC00620.1.4 | 0% | 2011-11-16 | 2012-08-31 | Budgeted Labor Units | 2011-11-01: 44; 2011-12-01: 100; 2012-01-01: 100; 2012-02-01: 98; 2012-03-01: 95; 2012-04-01: 91; 2012-05-01: 95; 2012-06-01: 91; 2012-07-01: 91; 2012-08-01: 97
EC2240 | Tenant Finishes for Clubhouse Areas | EC00620.1.4 | 0% | 2012-07-03 | 2013-01-03 | Actual Labor Cost
EC2240 | Tenant Finishes for Clubhouse Areas | EC00620.1.4 | 0% | 2012-07-03 | 2013-01-03 | Budgeted Labor Cost | 2012-07-01: 17471.7; 2012-08-01: 20013.21; 2012-09-01: 14088.68; 2012-10-01: 17054.72; 2012-11-01: 15571.7; 2012-12-01: 14830.19; 2013-01-01: 889.81
EC2240 | Tenant Finishes for Clubhouse Areas | EC00620.1.4 | 0% | 2012-07-03 | 2013-01-03 | Actual Labor Units
EC2240 | Tenant Finishes for Clubhouse Areas | EC00620.1.4 | 0% | 2012-07-03 | 2013-01-03 | Budgeted Labor Units | 2012-07-01: 302; 2012-08-01: 346; 2012-09-01: 251; 2012-10-01: 304; 2012-11-01: 277; 2012-12-01: 264; 2013-01-01: 16
EC2370 | Final Inspections and Punchlist | EC00620.1.4 | 0% | 2012-11-13 | 2013-01-03 | Actual Labor Cost
EC2370 | Final Inspections and Punchlist | EC00620.1.4 | 0% | 2012-11-13 | 2013-01-03 | Budgeted Labor Cost | 2012-11-01: 12122.57; 2012-12-01: 16842.86; 2013-01-01: 1010.57
EC2370 | Final Inspections and Punchlist | EC00620.1.4 | 0% | 2012-11-13 | 2013-01-03 | Actual Labor Units
EC2370 | Final Inspections and Punchlist | EC00620.1.4 | 0% | 2012-11-13 | 2013-01-03 | Budgeted Labor Units | 2012-11-01: 210; 2012-12-01: 300; 2013-01-01: 18
EC00620.1.5 Pool & Courtyard |  |  | 0% | 2012-03-28 | 2012-11-29 | Actual Labor Cost
EC00620.1.5 Pool & Courtyard |  |  | 0% | 2012-03-28 | 2012-11-29 | Budgeted Labor Cost | 2012-03-01: 2441.69; 2012-04-01: 20928.81; 2012-05-01: 21925.42; 2012-06-01: 20928.81; 2012-07-01: 20928.81; 2012-08-01: 22922.03; 2012-09-01: 32144.59; 2012-10-01: 50748.81; 2012-11-01: 32823
EC00620.1.5 Pool & Courtyard |  |  | 0% | 2012-03-28 | 2012-11-29 | Actual Labor Units
EC00620.1.5 Pool & Courtyard |  |  | 0% | 2012-03-28 | 2012-11-29 | Budgeted Labor Units | 2012-03-01: 23; 2012-04-01: 199; 2012-05-01: 209; 2012-06-01: 199; 2012-07-01: 199; 2012-08-01: 218; 2012-09-01: 306; 2012-10-01: 483; 2012-11-01: 313
EC2080 | Pool & Deck | EC00620.1.5 | 0% | 2012-03-28 | 2012-10-17 | Actual Labor Cost
EC2080 | Pool & Deck | EC00620.1.5 | 0% | 2012-03-28 | 2012-10-17 | Budgeted Labor Cost | 2012-03-01: 2441.69; 2012-04-01: 20928.81; 2012-05-01: 21925.42; 2012-06-01: 20928.81; 2012-07-01: 20928.81; 2012-08-01: 22922.03; 2012-09-01: 18935.59; 2012-10-01: 12108.81
EC2080 | Pool & Deck | EC00620.1.5 | 0% | 2012-03-28 | 2012-10-17 | Actual Labor Units
EC2080 | Pool & Deck | EC00620.1.5 | 0% | 2012-03-28 | 2012-10-17 | Budgeted Labor Units | 2012-03-01: 23; 2012-04-01: 199; 2012-05-01: 209; 2012-06-01: 199; 2012-07-01: 199; 2012-08-01: 218; 2012-09-01: 180; 2012-10-01: 115
EC2270 | Pergola and Amenities | EC00620.1.5 | 0% | 2012-09-19 | 2012-11-29 | Actual Labor Cost
EC2270 | Pergola and Amenities | EC00620.1.5 | 0% | 2012-09-19 | 2012-11-29 | Budgeted Labor Cost | 2012-09-01: 13209; 2012-10-01: 38640; 2012-11-01: 32823
EC2270 | Pergola and Amenities | EC00620.1.5 | 0% | 2012-09-19 | 2012-11-29 | Actual Labor Units
EC2270 | Pergola and Amenities | EC00620.1.5 | 0% | 2012-09-19 | 2012-11-29 | Budgeted Labor Units | 2012-09-01: 126; 2012-10-01: 368; 2012-11-01: 313
EC00620.2 Building 2 |  |  | 6.59% | 30-Nov-10 A | 2013-03-11 | Actual Labor Cost | 2010-11-01: 1132.65; 2010-12-01: 23785.71; 2011-01-01: 23785.71; 2011-02-01: 9945.92; 2011-03-01: 2987.96; 2011-04-01: 12167.04
EC00620.2 Building 2 |  |  | 6.59% | 30-Nov-10 A | 2013-03-11 | Budgeted Labor Cost | 2010-11-01: 1200; 2010-12-01: 25200; 2011-01-01: 25200; 2011-02-01: 6000; 2011-03-01: 6020; 2011-04-01: 11725; 2011-05-01: 9380; 2011-06-01: 12320; 2011-07-01: 11200; 2011-08-01: 12852; 2011-09-01: 11760; 2011-10-01: 188344.2; 2011-11-01: 167497; 2011-12-01: 100431; 2012-01-01: 80001.15; 2012-02-01: 79483.29; 2012-03-01: 92955.48; 2012-04-01: 92329.9; 2012-05-01: 88126.96; 2012-06-01: 103702.22; 2012-07-01: 121606.22; 2012-08-01: 90788.91; 2012-09-01: 50728.9; 2012-10-01: 55486.25; 2012-11-01: 25882.95; 2012-12-01: 20811.58; 2013-01-01: 12741.33; 2013-02-01: 6780; 2013-03-01: 2042.48
EC00620.2 Building 2 |  |  | 6.59% | 30-Nov-10 A | 2013-03-11 | Actual Labor Units | 2010-11-01: 15; 2010-12-01: 317; 2011-01-01: 317; 2011-02-01: 181; 2011-03-01: 85; 2011-04-01: 348
EC00620.2 Building 2 |  |  | 6.59% | 30-Nov-10 A | 2013-03-11 | Budgeted Labor Units | 2010-11-01: 16; 2010-12-01: 336; 2011-01-01: 336; 2011-02-01: 80; 2011-03-01: 172; 2011-04-01: 335; 2011-05-01: 268; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 367; 2011-09-01: 336; 2011-10-01: 1951; 2011-11-01: 1765; 2011-12-01: 1114; 2012-01-01: 894; 2012-02-01: 1059; 2012-03-01: 1275; 2012-04-01: 1213; 2012-05-01: 1141; 2012-06-01: 1245; 2012-07-01: 1394; 2012-08-01: 1173; 2012-09-01: 965; 2012-10-01: 1071; 2012-11-01: 549; 2012-12-01: 456; 2013-01-01: 264; 2013-02-01: 120; 2013-03-01: 36
EC2420 | Complete Building 2 | EC00620.2 | 0% |  | 2013-03-11 | Actual Labor Cost
EC2420 | Complete Building 2 | EC00620.2 | 0% |  | 2013-03-11 | Budgeted Labor Cost
EC2420 | Complete Building 2 | EC00620.2 | 0% |  | 2013-03-11 | Actual Labor Units
EC2420 | Complete Building 2 | EC00620.2 | 0% |  | 2013-03-11 | Budgeted Labor Units
EC00620.2.1 Structure |  |  | 70.91% | 30-Nov-10 A | 2011-10-03 | Actual Labor Cost | 2010-11-01: 1132.65; 2010-12-01: 23785.71; 2011-01-01: 23785.71; 2011-02-01: 9945.92; 2011-03-01: 2987.96; 2011-04-01: 12167.04
EC00620.2.1 Structure |  |  | 70.91% | 30-Nov-10 A | 2011-10-03 | Budgeted Labor Cost | 2010-11-01: 1200; 2010-12-01: 25200; 2011-01-01: 25200; 2011-02-01: 6000; 2011-03-01: 6020; 2011-04-01: 11725; 2011-05-01: 9380; 2011-06-01: 12320; 2011-07-01: 11200; 2011-08-01: 12852; 2011-09-01: 11760; 2011-10-01: 7
EC00620.2.1 Structure |  |  | 70.91% | 30-Nov-10 A | 2011-10-03 | Actual Labor Units | 2010-11-01: 15; 2010-12-01: 317; 2011-01-01: 317; 2011-02-01: 181; 2011-03-01: 85; 2011-04-01: 348
EC00620.2.1 Structure |  |  | 70.91% | 30-Nov-10 A | 2011-10-03 | Budgeted Labor Units | 2010-11-01: 16; 2010-12-01: 336; 2011-01-01: 336; 2011-02-01: 80; 2011-03-01: 172; 2011-04-01: 335; 2011-05-01: 268; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 367; 2011-09-01: 336; 2011-10-01: 0
EC1150 | Building Slab Incl. UG Utils | EC00620.2.1 | 100% | 30-Nov-10 A | 09-Feb-11 A | Actual Labor Cost | 2010-11-01: 1132.65; 2010-12-01: 23785.71; 2011-01-01: 23785.71; 2011-02-01: 6795.92
EC1150 | Building Slab Incl. UG Utils | EC00620.2.1 | 100% | 30-Nov-10 A | 09-Feb-11 A | Budgeted Labor Cost | 2010-11-01: 1200; 2010-12-01: 25200; 2011-01-01: 25200; 2011-02-01: 6000
EC1150 | Building Slab Incl. UG Utils | EC00620.2.1 | 100% | 30-Nov-10 A | 09-Feb-11 A | Actual Labor Units | 2010-11-01: 15; 2010-12-01: 317; 2011-01-01: 317; 2011-02-01: 91
EC1150 | Building Slab Incl. UG Utils | EC00620.2.1 | 100% | 30-Nov-10 A | 09-Feb-11 A | Budgeted Labor Units | 2010-11-01: 16; 2010-12-01: 336; 2011-01-01: 336; 2011-02-01: 80
EC1220 | First Floor Masonry Structure | EC00620.2.1 | 100% | 07-Feb-11 A | 25-Feb-11 A | Actual Labor Cost | 2011-02-01: 3150
EC1220 | First Floor Masonry Structure | EC00620.2.1 | 100% | 07-Feb-11 A | 25-Feb-11 A | Budgeted Labor Cost | 2011-03-01: 3360
EC1220 | First Floor Masonry Structure | EC00620.2.1 | 100% | 07-Feb-11 A | 25-Feb-11 A | Actual Labor Units | 2011-02-01: 90
EC1220 | First Floor Masonry Structure | EC00620.2.1 | 100% | 07-Feb-11 A | 25-Feb-11 A | Budgeted Labor Units | 2011-03-01: 96
EC1230 | Second Floor Slab & Collar Beam | EC00620.2.1 | 100% | 24-Mar-11 A | 29-Apr-11 A | Actual Labor Cost | 2011-03-01: 1655.77; 2011-04-01: 5519.23
EC1230 | Second Floor Slab & Collar Beam | EC00620.2.1 | 100% | 24-Mar-11 A | 29-Apr-11 A | Budgeted Labor Cost | 2011-03-01: 1680; 2011-04-01: 5040
EC1230 | Second Floor Slab & Collar Beam | EC00620.2.1 | 100% | 24-Mar-11 A | 29-Apr-11 A | Actual Labor Units | 2011-03-01: 47; 2011-04-01: 158
EC1230 | Second Floor Slab & Collar Beam | EC00620.2.1 | 100% | 24-Mar-11 A | 29-Apr-11 A | Budgeted Labor Units | 2011-03-01: 48; 2011-04-01: 144
EC1260 | Second Floor Masonry Structure | EC00620.2.1 | 100% | 28-Mar-11 A | 11-Apr-11 A | Actual Labor Cost | 2011-03-01: 1332.19; 2011-04-01: 2342.81
EC1260 | Second Floor Masonry Structure | EC00620.2.1 | 100% | 28-Mar-11 A | 11-Apr-11 A | Budgeted Labor Cost | 2011-03-01: 980; 2011-04-01: 2380
EC1260 | Second Floor Masonry Structure | EC00620.2.1 | 100% | 28-Mar-11 A | 11-Apr-11 A | Actual Labor Units | 2011-03-01: 38; 2011-04-01: 67
EC1260 | Second Floor Masonry Structure | EC00620.2.1 | 100% | 28-Mar-11 A | 11-Apr-11 A | Budgeted Labor Units | 2011-03-01: 28; 2011-04-01: 68
EC1290 | Third Floor Slab & Collar Beam | EC00620.2.1 | 54.17% | 08-Apr-11 A | 2011-05-12 | Actual Labor Cost | 2011-04-01: 4305
EC1290 | Third Floor Slab & Collar Beam | EC00620.2.1 | 54.17% | 08-Apr-11 A | 2011-05-12 | Budgeted Labor Cost | 2011-04-01: 4305; 2011-05-01: 2415
EC1290 | Third Floor Slab & Collar Beam | EC00620.2.1 | 54.17% | 08-Apr-11 A | 2011-05-12 | Actual Labor Units | 2011-04-01: 123
EC1290 | Third Floor Slab & Collar Beam | EC00620.2.1 | 54.17% | 08-Apr-11 A | 2011-05-12 | Budgeted Labor Units | 2011-04-01: 123; 2011-05-01: 69
EC1320 | Third Floor Masonry Structure | EC00620.2.1 | 0% | 2011-05-12 | 2011-05-31 | Actual Labor Cost
EC1320 | Third Floor Masonry Structure | EC00620.2.1 | 0% | 2011-05-12 | 2011-05-31 | Budgeted Labor Cost | 2011-05-01: 6720
EC1320 | Third Floor Masonry Structure | EC00620.2.1 | 0% | 2011-05-12 | 2011-05-31 | Actual Labor Units
EC1320 | Third Floor Masonry Structure | EC00620.2.1 | 0% | 2011-05-12 | 2011-05-31 | Budgeted Labor Units | 2011-05-01: 192
EC1330 | Fourth Floor Slab & Collar Beam | EC00620.2.1 | 0% | 2011-05-31 | 2011-07-05 | Actual Labor Cost
EC1330 | Fourth Floor Slab & Collar Beam | EC00620.2.1 | 0% | 2011-05-31 | 2011-07-05 | Budgeted Labor Cost | 2011-05-01: 245; 2011-06-01: 12320; 2011-07-01: 875
EC1330 | Fourth Floor Slab & Collar Beam | EC00620.2.1 | 0% | 2011-05-31 | 2011-07-05 | Actual Labor Units
EC1330 | Fourth Floor Slab & Collar Beam | EC00620.2.1 | 0% | 2011-05-31 | 2011-07-05 | Budgeted Labor Units | 2011-05-01: 7; 2011-06-01: 352; 2011-07-01: 25
EC1380 | Fourth Floor Masonry Structure | EC00620.2.1 | 0% | 2011-07-05 | 2011-07-21 | Actual Labor Cost
EC1380 | Fourth Floor Masonry Structure | EC00620.2.1 | 0% | 2011-07-05 | 2011-07-21 | Budgeted Labor Cost | 2011-07-01: 6720
EC1380 | Fourth Floor Masonry Structure | EC00620.2.1 | 0% | 2011-07-05 | 2011-07-21 | Actual Labor Units
EC1380 | Fourth Floor Masonry Structure | EC00620.2.1 | 0% | 2011-07-05 | 2011-07-21 | Budgeted Labor Units | 2011-07-01: 192
EC1480 | Roof Slab | EC00620.2.1 | 0% | 2011-07-21 | 2011-08-22 | Actual Labor Cost
EC1480 | Roof Slab | EC00620.2.1 | 0% | 2011-07-21 | 2011-08-22 | Budgeted Labor Cost | 2011-07-01: 3605; 2011-08-01: 8491
EC1480 | Roof Slab | EC00620.2.1 | 0% | 2011-07-21 | 2011-08-22 | Actual Labor Units
EC1480 | Roof Slab | EC00620.2.1 | 0% | 2011-07-21 | 2011-08-22 | Budgeted Labor Units | 2011-07-01: 103; 2011-08-01: 243
EC1620 | Stair and Elevator Masonry Structure | EC00620.2.1 | 0% | 2011-08-22 | 2011-08-29 | Actual Labor Cost
EC1620 | Stair and Elevator Masonry Structure | EC00620.2.1 | 0% | 2011-08-22 | 2011-08-29 | Budgeted Labor Cost | 2011-08-01: 2688
EC1620 | Stair and Elevator Masonry Structure | EC00620.2.1 | 0% | 2011-08-22 | 2011-08-29 | Actual Labor Units
EC1620 | Stair and Elevator Masonry Structure | EC00620.2.1 | 0% | 2011-08-22 | 2011-08-29 | Budgeted Labor Units | 2011-08-01: 77
EC1640 | Roof Slab/Collar Beam | EC00620.2.1 | 0% | 2011-08-29 | 2011-10-03 | Actual Labor Cost
EC1640 | Roof Slab/Collar Beam | EC00620.2.1 | 0% | 2011-08-29 | 2011-10-03 | Budgeted Labor Cost | 2011-08-01: 1673; 2011-09-01: 11760; 2011-10-01: 7
EC1640 | Roof Slab/Collar Beam | EC00620.2.1 | 0% | 2011-08-29 | 2011-10-03 | Actual Labor Units
EC1640 | Roof Slab/Collar Beam | EC00620.2.1 | 0% | 2011-08-29 | 2011-10-03 | Budgeted Labor Units | 2011-08-01: 48; 2011-09-01: 336; 2011-10-01: 0
EC00620.2.2 Roof |  |  | 0% | 2011-10-03 | 2012-01-11 | Actual Labor Cost
EC00620.2.2 Roof |  |  | 0% | 2011-10-03 | 2012-01-11 | Budgeted Labor Cost | 2011-10-01: 87308; 2011-11-01: 55702; 2011-12-01: 43935; 2012-01-01: 7935
EC00620.2.2 Roof |  |  | 0% | 2011-10-03 | 2012-01-11 | Actual Labor Units
EC00620.2.2 Roof |  |  | 0% | 2011-10-03 | 2012-01-11 | Budgeted Labor Units | 2011-10-01: 1007; 2011-11-01: 720; 2011-12-01: 586; 2012-01-01: 106
EC1710 | Place Roof Trusses and Sheathing | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Actual Labor Cost
EC1710 | Place Roof Trusses and Sheathing | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Budgeted Labor Cost | 2011-10-01: 62123; 2011-11-01: 8917
EC1710 | Place Roof Trusses and Sheathing | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Actual Labor Units
EC1710 | Place Roof Trusses and Sheathing | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Budgeted Labor Units | 2011-10-01: 672; 2011-11-01: 96
EC1720 | Place Mechanical Equipment Supports | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Actual Labor Cost
EC1720 | Place Mechanical Equipment Supports | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Budgeted Labor Cost | 2011-10-01: 25185; 2011-11-01: 3615
EC1720 | Place Mechanical Equipment Supports | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Actual Labor Units
EC1720 | Place Mechanical Equipment Supports | EC00620.2.2 | 0% | 2011-10-03 | 2011-11-04 | Budgeted Labor Units | 2011-10-01: 336; 2011-11-01: 48
EC1860 | Built-Up Asphalt Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2011-12-22 | Actual Labor Cost
EC1860 | Built-Up Asphalt Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2011-12-22 | Budgeted Labor Cost | 2011-11-01: 21585; 2011-12-01: 18735
EC1860 | Built-Up Asphalt Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2011-12-22 | Actual Labor Units
EC1860 | Built-Up Asphalt Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2011-12-22 | Budgeted Labor Units | 2011-11-01: 288; 2011-12-01: 250
EC1870 | Felt and Tile Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2012-01-11 | Actual Labor Cost
EC1870 | Felt and Tile Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2012-01-11 | Budgeted Labor Cost | 2011-11-01: 21585; 2011-12-01: 25200; 2012-01-01: 7935
EC1870 | Felt and Tile Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2012-01-11 | Actual Labor Units
EC1870 | Felt and Tile Roofing | EC00620.2.2 | 0% | 2011-11-04 | 2012-01-11 | Budgeted Labor Units | 2011-11-01: 288; 2011-12-01: 336; 2012-01-01: 106
EC2020 | Roof Complete | EC00620.2.2 | 0% |  | 2012-01-11 | Actual Labor Cost
EC2020 | Roof Complete | EC00620.2.2 | 0% |  | 2012-01-11 | Budgeted Labor Cost
EC2020 | Roof Complete | EC00620.2.2 | 0% |  | 2012-01-11 | Actual Labor Units
EC2020 | Roof Complete | EC00620.2.2 | 0% |  | 2012-01-11 | Budgeted Labor Units
EC00620.2.3 Envelope |  |  | 0% | 2011-10-03 | 2012-09-04 | Actual Labor Cost
EC00620.2.3 Envelope |  |  | 0% | 2011-10-03 | 2012-09-04 | Budgeted Labor Cost | 2011-10-01: 101029.2; 2011-11-01: 111795; 2011-12-01: 56496; 2012-01-01: 44724.6; 2012-02-01: 20376; 2012-03-01: 21120; 2012-04-01: 33504; 2012-05-01: 42240; 2012-06-01: 61128; 2012-07-01: 79032; 2012-08-01: 44160; 2012-09-01: 312
EC00620.2.3 Envelope |  |  | 0% | 2011-10-03 | 2012-09-04 | Actual Labor Units
EC00620.2.3 Envelope |  |  | 0% | 2011-10-03 | 2012-09-04 | Budgeted Labor Units | 2011-10-01: 943; 2011-11-01: 1045; 2011-12-01: 528; 2012-01-01: 402; 2012-02-01: 170; 2012-03-01: 176; 2012-04-01: 279; 2012-05-01: 352; 2012-06-01: 509; 2012-07-01: 659; 2012-08-01: 368; 2012-09-01: 3
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.2.3 | 0% | 2011-10-03 | 2011-11-04 | Actual Labor Cost
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.2.3 | 0% | 2011-10-03 | 2011-11-04 | Budgeted Labor Cost | 2011-10-01: 69510.6; 2011-11-01: 9977.4
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.2.3 | 0% | 2011-10-03 | 2011-11-04 | Actual Labor Units
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00620.2.3 | 0% | 2011-10-03 | 2011-11-04 | Budgeted Labor Units | 2011-10-01: 672; 2011-11-01: 96
EC1740 | Mobilize Scaffolding | EC00620.2.3 | 0% | 2011-10-03 | 2011-10-19 | Actual Labor Cost
EC1740 | Mobilize Scaffolding | EC00620.2.3 | 0% | 2011-10-03 | 2011-10-19 | Budgeted Labor Cost | 2011-10-01: 23040
EC1740 | Mobilize Scaffolding | EC00620.2.3 | 0% | 2011-10-03 | 2011-10-19 | Actual Labor Units
EC1740 | Mobilize Scaffolding | EC00620.2.3 | 0% | 2011-10-03 | 2011-10-19 | Budgeted Labor Units | 2011-10-01: 192
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.2.3 | 0% | 2011-10-28 | 2011-11-29 | Actual Labor Cost
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.2.3 | 0% | 2011-10-28 | 2011-11-29 | Budgeted Labor Cost | 2011-10-01: 6582.6; 2011-11-01: 64956.6
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.2.3 | 0% | 2011-10-28 | 2011-11-29 | Actual Labor Units
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00620.2.3 | 0% | 2011-10-28 | 2011-11-29 | Budgeted Labor Units | 2011-10-01: 64; 2011-11-01: 628
EC1830 | Install Backing & Cauld Windows Floor1 | EC00620.2.3 | 0% | 2011-10-31 | 2011-11-16 | Actual Labor Cost
EC1830 | Install Backing & Cauld Windows Floor1 | EC00620.2.3 | 0% | 2011-10-31 | 2011-11-16 | Budgeted Labor Cost | 2011-10-01: 1896; 2011-11-01: 21144
EC1830 | Install Backing & Cauld Windows Floor1 | EC00620.2.3 | 0% | 2011-10-31 | 2011-11-16 | Actual Labor Units
EC1830 | Install Backing & Cauld Windows Floor1 | EC00620.2.3 | 0% | 2011-10-31 | 2011-11-16 | Budgeted Labor Units | 2011-10-01: 16; 2011-11-01: 176
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.2.3 | 0% | 2011-11-21 | 2011-12-22 | Actual Labor Cost
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.2.3 | 0% | 2011-11-21 | 2011-12-22 | Budgeted Labor Cost | 2011-11-01: 10557; 2011-12-01: 25212.6
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.2.3 | 0% | 2011-11-21 | 2011-12-22 | Actual Labor Units
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00620.2.3 | 0% | 2011-11-21 | 2011-12-22 | Budgeted Labor Units | 2011-11-01: 102; 2011-12-01: 244
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00620.2.3 | 0% | 2011-11-22 | 2011-12-07 | Actual Labor Cost
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00620.2.3 | 0% | 2011-11-22 | 2011-12-07 | Budgeted Labor Cost | 2011-11-01: 5160; 2011-12-01: 4056
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00620.2.3 | 0% | 2011-11-22 | 2011-12-07 | Actual Labor Units
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00620.2.3 | 0% | 2011-11-22 | 2011-12-07 | Budgeted Labor Units | 2011-11-01: 43; 2011-12-01: 34
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.2.3 | 0% | 2011-12-15 | 2012-01-20 | Actual Labor Cost
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.2.3 | 0% | 2011-12-15 | 2012-01-20 | Budgeted Labor Cost | 2011-12-01: 17843.4; 2012-01-01: 21900.6
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.2.3 | 0% | 2011-12-15 | 2012-01-20 | Actual Labor Units
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00620.2.3 | 0% | 2011-12-15 | 2012-01-20 | Budgeted Labor Units | 2011-12-01: 172; 2012-01-01: 212
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00620.2.3 | 0% | 2011-12-16 | 2012-01-05 | Actual Labor Cost
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00620.2.3 | 0% | 2011-12-16 | 2012-01-05 | Budgeted Labor Cost | 2011-12-01: 9384; 2012-01-01: 2136
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00620.2.3 | 0% | 2011-12-16 | 2012-01-05 | Actual Labor Units
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00620.2.3 | 0% | 2011-12-16 | 2012-01-05 | Budgeted Labor Units | 2011-12-01: 78; 2012-01-01: 18
EC1940 | Stucco Bands | EC00620.2.3 | 0% | 2012-01-18 | 2012-02-03 | Actual Labor Cost
EC1940 | Stucco Bands | EC00620.2.3 | 0% | 2012-01-18 | 2012-02-03 | Budgeted Labor Cost | 2012-01-01: 9384; 2012-02-01: 2136
EC1940 | Stucco Bands | EC00620.2.3 | 0% | 2012-01-18 | 2012-02-03 | Actual Labor Units
EC1940 | Stucco Bands | EC00620.2.3 | 0% | 2012-01-18 | 2012-02-03 | Budgeted Labor Units | 2012-01-01: 78; 2012-02-01: 18
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00620.2.3 | 0% | 2012-01-16 | 2012-02-01 | Actual Labor Cost
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00620.2.3 | 0% | 2012-01-16 | 2012-02-01 | Budgeted Labor Cost | 2012-01-01: 11304; 2012-02-01: 216
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00620.2.3 | 0% | 2012-01-16 | 2012-02-01 | Actual Labor Units
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00620.2.3 | 0% | 2012-01-16 | 2012-02-01 | Budgeted Labor Units | 2012-01-01: 94; 2012-02-01: 2
EC1970 | Stucco Grey | EC00620.2.3 | 0% | 2012-02-03 | 2012-03-08 | Actual Labor Cost
EC1970 | Stucco Grey | EC00620.2.3 | 0% | 2012-02-03 | 2012-03-08 | Budgeted Labor Cost | 2012-02-01: 18024; 2012-03-01: 5016
EC1970 | Stucco Grey | EC00620.2.3 | 0% | 2012-02-03 | 2012-03-08 | Actual Labor Units
EC1970 | Stucco Grey | EC00620.2.3 | 0% | 2012-02-03 | 2012-03-08 | Budgeted Labor Units | 2012-02-01: 150; 2012-03-01: 42
EC2050 | Stucco Finish Coat | EC00620.2.3 | 0% | 2012-03-08 | 2012-04-11 | Actual Labor Cost
EC2050 | Stucco Finish Coat | EC00620.2.3 | 0% | 2012-03-08 | 2012-04-11 | Budgeted Labor Cost | 2012-03-01: 16104; 2012-04-01: 6936
EC2050 | Stucco Finish Coat | EC00620.2.3 | 0% | 2012-03-08 | 2012-04-11 | Actual Labor Units
EC2050 | Stucco Finish Coat | EC00620.2.3 | 0% | 2012-03-08 | 2012-04-11 | Budgeted Labor Units | 2012-03-01: 134; 2012-04-01: 58
EC2130 | Caulk | EC00620.2.3 | 0% | 2012-04-11 | 2012-04-27 | Actual Labor Cost
EC2130 | Caulk | EC00620.2.3 | 0% | 2012-04-11 | 2012-04-27 | Budgeted Labor Cost | 2012-04-01: 23040
EC2130 | Caulk | EC00620.2.3 | 0% | 2012-04-11 | 2012-04-27 | Actual Labor Units
EC2130 | Caulk | EC00620.2.3 | 0% | 2012-04-11 | 2012-04-27 | Budgeted Labor Units | 2012-04-01: 192
EC2160 | Stucco Band Trim | EC00620.2.3 | 0% | 2012-04-27 | 2012-06-01 | Actual Labor Cost
EC2160 | Stucco Band Trim | EC00620.2.3 | 0% | 2012-04-27 | 2012-06-01 | Budgeted Labor Cost | 2012-04-01: 3528; 2012-05-01: 42240; 2012-06-01: 312
EC2160 | Stucco Band Trim | EC00620.2.3 | 0% | 2012-04-27 | 2012-06-01 | Actual Labor Units
EC2160 | Stucco Band Trim | EC00620.2.3 | 0% | 2012-04-27 | 2012-06-01 | Budgeted Labor Units | 2012-04-01: 29; 2012-05-01: 352; 2012-06-01: 3
EC2220 | Paint Exterior | EC00620.2.3 | 0% | 2012-06-08 | 2012-08-16 | Actual Labor Cost
EC2220 | Paint Exterior | EC00620.2.3 | 0% | 2012-06-08 | 2012-08-16 | Budgeted Labor Cost | 2012-06-01: 30408; 2012-07-01: 40320; 2012-08-01: 21432
EC2220 | Paint Exterior | EC00620.2.3 | 0% | 2012-06-08 | 2012-08-16 | Actual Labor Units
EC2220 | Paint Exterior | EC00620.2.3 | 0% | 2012-06-08 | 2012-08-16 | Budgeted Labor Units | 2012-06-01: 253; 2012-07-01: 336; 2012-08-01: 179
EC2230 | Install Railings | EC00620.2.3 | 0% | 2012-06-08 | 2012-07-31 | Actual Labor Cost
EC2230 | Install Railings | EC00620.2.3 | 0% | 2012-06-08 | 2012-07-31 | Budgeted Labor Cost | 2012-06-01: 30408; 2012-07-01: 38712
EC2230 | Install Railings | EC00620.2.3 | 0% | 2012-06-08 | 2012-07-31 | Actual Labor Units
EC2230 | Install Railings | EC00620.2.3 | 0% | 2012-06-08 | 2012-07-31 | Budgeted Labor Units | 2012-06-01: 253; 2012-07-01: 323
EC2300 | Demobilize Scaffolding | EC00620.2.3 | 0% | 2012-08-16 | 2012-09-04 | Actual Labor Cost
EC2300 | Demobilize Scaffolding | EC00620.2.3 | 0% | 2012-08-16 | 2012-09-04 | Budgeted Labor Cost | 2012-08-01: 22728; 2012-09-01: 312
EC2300 | Demobilize Scaffolding | EC00620.2.3 | 0% | 2012-08-16 | 2012-09-04 | Actual Labor Units
EC2300 | Demobilize Scaffolding | EC00620.2.3 | 0% | 2012-08-16 | 2012-09-04 | Budgeted Labor Units | 2012-08-01: 189; 2012-09-01: 3
EC2320 | Shell Complete | EC00620.2.3 | 0% |  | 2012-09-04 | Actual Labor Cost
EC2320 | Shell Complete | EC00620.2.3 | 0% |  | 2012-09-04 | Budgeted Labor Cost
EC2320 | Shell Complete | EC00620.2.3 | 0% |  | 2012-09-04 | Actual Labor Units
EC2320 | Shell Complete | EC00620.2.3 | 0% |  | 2012-09-04 | Budgeted Labor Units
EC00620.2.4 Interior Finishes |  |  | 0% | 2012-01-04 | 2013-03-11 | Actual Labor Cost
EC00620.2.4 Interior Finishes |  |  | 0% | 2012-01-04 | 2013-03-11 | Budgeted Labor Cost | 2012-01-01: 27341.55; 2012-02-01: 59107.29; 2012-03-01: 71835.48; 2012-04-01: 58825.9; 2012-05-01: 45886.96; 2012-06-01: 42574.22; 2012-07-01: 42574.22; 2012-08-01: 46628.91; 2012-09-01: 38519.53; 2012-10-01: 40959.93; 2012-11-01: 12619.79; 2012-12-01: 8180; 2013-01-01: 7459.75; 2013-02-01: 6780; 2013-03-01: 2042.48
EC00620.2.4 Interior Finishes |  |  | 0% | 2012-01-04 | 2013-03-11 | Actual Labor Units
EC00620.2.4 Interior Finishes |  |  | 0% | 2012-01-04 | 2013-03-11 | Budgeted Labor Units | 2012-01-01: 386; 2012-02-01: 889; 2012-03-01: 1099; 2012-04-01: 934; 2012-05-01: 789; 2012-06-01: 735; 2012-07-01: 735; 2012-08-01: 805; 2012-09-01: 665; 2012-10-01: 708; 2012-11-01: 218; 2012-12-01: 140; 2013-01-01: 132; 2013-02-01: 120; 2013-03-01: 36
EC2000 | Unit Finishes Building North - Floor 1 | EC00620.2.4 | 0% | 2012-01-04 | 2012-10-17 | Actual Labor Cost
EC2000 | Unit Finishes Building North - Floor 1 | EC00620.2.4 | 0% | 2012-01-04 | 2012-10-17 | Budgeted Labor Cost | 2012-01-01: 5452.68; 2012-02-01: 5910; 2012-03-01: 6191.43; 2012-04-01: 5370.83; 2012-05-01: 5458.1; 2012-06-01: 5210; 2012-07-01: 5210; 2012-08-01: 5706.19; 2012-09-01: 4713.81; 2012-10-01: 3032.96
EC2000 | Unit Finishes Building North - Floor 1 | EC00620.2.4 | 0% | 2012-01-04 | 2012-10-17 | Actual Labor Units
EC2000 | Unit Finishes Building North - Floor 1 | EC00620.2.4 | 0% | 2012-01-04 | 2012-10-17 | Budgeted Labor Units | 2012-01-01: 92; 2012-02-01: 100; 2012-03-01: 105; 2012-04-01: 92; 2012-05-01: 94; 2012-06-01: 90; 2012-07-01: 90; 2012-08-01: 99; 2012-09-01: 81; 2012-10-01: 52
EC2030 | Unit Finishes Building South - Floor 1 | EC00620.2.4 | 0% | 2012-01-11 | 2012-10-24 | Actual Labor Cost
EC2030 | Unit Finishes Building South - Floor 1 | EC00620.2.4 | 0% | 2012-01-11 | 2012-10-24 | Budgeted Labor Cost | 2012-01-01: 4045.54; 2012-02-01: 5910; 2012-03-01: 6191.43; 2012-04-01: 5537.5; 2012-05-01: 5458.1; 2012-06-01: 5210; 2012-07-01: 5210; 2012-08-01: 5706.19; 2012-09-01: 4713.81; 2012-10-01: 4273.44
EC2030 | Unit Finishes Building South - Floor 1 | EC00620.2.4 | 0% | 2012-01-11 | 2012-10-24 | Actual Labor Units
EC2030 | Unit Finishes Building South - Floor 1 | EC00620.2.4 | 0% | 2012-01-11 | 2012-10-24 | Budgeted Labor Units | 2012-01-01: 68; 2012-02-01: 100; 2012-03-01: 105; 2012-04-01: 95; 2012-05-01: 94; 2012-06-01: 90; 2012-07-01: 90; 2012-08-01: 99; 2012-09-01: 81; 2012-10-01: 74
EC2040 | Building 1 Elevators Complete | EC00620.2.4 | 0% | 2012-01-11 | 2012-04-18 | Actual Labor Cost
EC2040 | Building 1 Elevators Complete | EC00620.2.4 | 0% | 2012-01-11 | 2012-04-18 | Budgeted Labor Cost | 2012-01-01: 13879.31; 2012-02-01: 20275.86; 2012-03-01: 21241.38; 2012-04-01: 11803.45
EC2040 | Building 1 Elevators Complete | EC00620.2.4 | 0% | 2012-01-11 | 2012-04-18 | Actual Labor Units
EC2040 | Building 1 Elevators Complete | EC00620.2.4 | 0% | 2012-01-11 | 2012-04-18 | Budgeted Labor Units | 2012-01-01: 159; 2012-02-01: 232; 2012-03-01: 243; 2012-04-01: 135
EC2070 | Unit Finishes Building North - Floor 2 | EC00620.2.4 | 0% | 2012-01-18 | 2012-10-24 | Actual Labor Cost
EC2070 | Unit Finishes Building North - Floor 2 | EC00620.2.4 | 0% | 2012-01-18 | 2012-10-24 | Budgeted Labor Cost | 2012-01-01: 2702.74; 2012-02-01: 6054.15; 2012-03-01: 6342.44; 2012-04-01: 5788.66; 2012-05-01: 5591.22; 2012-06-01: 5337.07; 2012-07-01: 5337.07; 2012-08-01: 5845.37; 2012-09-01: 4828.78; 2012-10-01: 4428.5
EC2070 | Unit Finishes Building North - Floor 2 | EC00620.2.4 | 0% | 2012-01-18 | 2012-10-24 | Actual Labor Units
EC2070 | Unit Finishes Building North - Floor 2 | EC00620.2.4 | 0% | 2012-01-18 | 2012-10-24 | Budgeted Labor Units | 2012-01-01: 46; 2012-02-01: 102; 2012-03-01: 107; 2012-04-01: 99; 2012-05-01: 97; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 76
EC2120 | Unit Finishes Building South - Floor 2 | EC00620.2.4 | 0% | 2012-01-25 | 2012-10-31 | Actual Labor Cost
EC2120 | Unit Finishes Building South - Floor 2 | EC00620.2.4 | 0% | 2012-01-25 | 2012-10-31 | Budgeted Labor Cost | 2012-01-01: 1261.28; 2012-02-01: 6054.15; 2012-03-01: 6342.44; 2012-04-01: 5959.39; 2012-05-01: 5591.22; 2012-06-01: 5337.07; 2012-07-01: 5337.07; 2012-08-01: 5845.37; 2012-09-01: 4828.78; 2012-10-01: 5699.23
EC2120 | Unit Finishes Building South - Floor 2 | EC00620.2.4 | 0% | 2012-01-25 | 2012-10-31 | Actual Labor Units
EC2120 | Unit Finishes Building South - Floor 2 | EC00620.2.4 | 0% | 2012-01-25 | 2012-10-31 | Budgeted Labor Units | 2012-01-01: 21; 2012-02-01: 102; 2012-03-01: 107; 2012-04-01: 101; 2012-05-01: 97; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 98
EC2150 | Unit Finishes Building North - Floor 3 | EC00620.2.4 | 0% | 2012-02-01 | 2012-11-07 | Actual Labor Cost
EC2150 | Unit Finishes Building North - Floor 3 | EC00620.2.4 | 0% | 2012-02-01 | 2012-11-07 | Budgeted Labor Cost | 2012-02-01: 5873.96; 2012-03-01: 6342.44; 2012-04-01: 6054.15; 2012-05-01: 5667.2; 2012-06-01: 5337.07; 2012-07-01: 5337.07; 2012-08-01: 5845.37; 2012-09-01: 4828.78; 2012-10-01: 5845.37; 2012-11-01: 1124.6
EC2150 | Unit Finishes Building North - Floor 3 | EC00620.2.4 | 0% | 2012-02-01 | 2012-11-07 | Actual Labor Units
EC2150 | Unit Finishes Building North - Floor 3 | EC00620.2.4 | 0% | 2012-02-01 | 2012-11-07 | Budgeted Labor Units | 2012-02-01: 99; 2012-03-01: 107; 2012-04-01: 102; 2012-05-01: 98; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 101; 2012-11-01: 19
EC2170 | Unit Finishes Building South - Floor 3 | EC00620.2.4 | 0% | 2012-02-08 | 2012-11-14 | Actual Labor Cost
EC2170 | Unit Finishes Building South - Floor 3 | EC00620.2.4 | 0% | 2012-02-08 | 2012-11-14 | Budgeted Labor Cost | 2012-02-01: 4432.5; 2012-03-01: 6342.44; 2012-04-01: 6054.15; 2012-05-01: 5837.93; 2012-06-01: 5337.07; 2012-07-01: 5337.07; 2012-08-01: 5845.37; 2012-09-01: 4828.78; 2012-10-01: 5845.37; 2012-11-01: 2395.33
EC2170 | Unit Finishes Building South - Floor 3 | EC00620.2.4 | 0% | 2012-02-08 | 2012-11-14 | Actual Labor Units
EC2170 | Unit Finishes Building South - Floor 3 | EC00620.2.4 | 0% | 2012-02-08 | 2012-11-14 | Budgeted Labor Units | 2012-02-01: 75; 2012-03-01: 107; 2012-04-01: 102; 2012-05-01: 100; 2012-06-01: 92; 2012-07-01: 92; 2012-08-01: 101; 2012-09-01: 83; 2012-10-01: 101; 2012-11-01: 41
EC2200 | Unit Finishes Building North - Floor 4 | EC00620.2.4 | 0% | 2012-02-15 | 2012-11-19 | Actual Labor Cost
EC2200 | Unit Finishes Building North - Floor 4 | EC00620.2.4 | 0% | 2012-02-15 | 2012-11-19 | Budgeted Labor Cost | 2012-02-01: 3027.96; 2012-03-01: 6420.74; 2012-04-01: 6128.89; 2012-05-01: 6055.19; 2012-06-01: 5402.96; 2012-07-01: 5402.96; 2012-08-01: 5917.53; 2012-09-01: 4888.4; 2012-10-01: 5917.53; 2012-11-01: 3093.84
EC2200 | Unit Finishes Building North - Floor 4 | EC00620.2.4 | 0% | 2012-02-15 | 2012-11-19 | Actual Labor Units
EC2200 | Unit Finishes Building North - Floor 4 | EC00620.2.4 | 0% | 2012-02-15 | 2012-11-19 | Budgeted Labor Units | 2012-02-01: 51; 2012-03-01: 109; 2012-04-01: 104; 2012-05-01: 103; 2012-06-01: 93; 2012-07-01: 93; 2012-08-01: 102; 2012-09-01: 84; 2012-10-01: 102; 2012-11-01: 53
EC2210 | Unit Finishes Building South - Floor 4 | EC00620.2.4 | 0% | 2012-02-22 | 2012-11-27 | Actual Labor Cost
EC2210 | Unit Finishes Building South - Floor 4 | EC00620.2.4 | 0% | 2012-02-22 | 2012-11-27 | Budgeted Labor Cost | 2012-02-01: 1568.7; 2012-03-01: 6420.74; 2012-04-01: 6128.89; 2012-05-01: 6228.03; 2012-06-01: 5402.96; 2012-07-01: 5402.96; 2012-08-01: 5917.53; 2012-09-01: 4888.4; 2012-10-01: 5917.53; 2012-11-01: 4380.26
EC2210 | Unit Finishes Building South - Floor 4 | EC00620.2.4 | 0% | 2012-02-22 | 2012-11-27 | Actual Labor Units
EC2210 | Unit Finishes Building South - Floor 4 | EC00620.2.4 | 0% | 2012-02-22 | 2012-11-27 | Budgeted Labor Units | 2012-02-01: 27; 2012-03-01: 109; 2012-04-01: 104; 2012-05-01: 106; 2012-06-01: 93; 2012-07-01: 93; 2012-08-01: 102; 2012-09-01: 84; 2012-10-01: 102; 2012-11-01: 76
EC2410 | Final Inspections and Punchlist | EC00620.2.4 | 0% | 2012-11-27 | 2013-03-11 | Actual Labor Cost
EC2410 | Final Inspections and Punchlist | EC00620.2.4 | 0% | 2012-11-27 | 2013-03-11 | Budgeted Labor Cost | 2012-11-01: 1625.78; 2012-12-01: 8180; 2013-01-01: 7459.75; 2013-02-01: 6780; 2013-03-01: 2042.48
EC2410 | Final Inspections and Punchlist | EC00620.2.4 | 0% | 2012-11-27 | 2013-03-11 | Actual Labor Units
EC2410 | Final Inspections and Punchlist | EC00620.2.4 | 0% | 2012-11-27 | 2013-03-11 | Budgeted Labor Units | 2012-11-01: 28; 2012-12-01: 140; 2013-01-01: 132; 2013-02-01: 120; 2013-03-01: 36
EC00620.2.5 Courtyard |  |  | 0% | 2012-09-04 | 2013-01-14 | Actual Labor Cost
EC00620.2.5 Courtyard |  |  | 0% | 2012-09-04 | 2013-01-14 | Budgeted Labor Cost | 2012-09-01: 11897.37; 2012-10-01: 14526.32; 2012-11-01: 13263.16; 2012-12-01: 12631.58; 2013-01-01: 5281.58
EC00620.2.5 Courtyard |  |  | 0% | 2012-09-04 | 2013-01-14 | Actual Labor Units
EC00620.2.5 Courtyard |  |  | 0% | 2012-09-04 | 2013-01-14 | Budgeted Labor Units | 2012-09-01: 297; 2012-10-01: 363; 2012-11-01: 332; 2012-12-01: 316; 2013-01-01: 132
EC2330 | Courtyard Walks and Amenities | EC00620.2.5 | 0% | 2012-09-04 | 2013-01-14 | Actual Labor Cost
EC2330 | Courtyard Walks and Amenities | EC00620.2.5 | 0% | 2012-09-04 | 2013-01-14 | Budgeted Labor Cost | 2012-09-01: 11897.37; 2012-10-01: 14526.32; 2012-11-01: 13263.16; 2012-12-01: 12631.58; 2013-01-01: 5281.58
EC2330 | Courtyard Walks and Amenities | EC00620.2.5 | 0% | 2012-09-04 | 2013-01-14 | Actual Labor Units
EC2330 | Courtyard Walks and Amenities | EC00620.2.5 | 0% | 2012-09-04 | 2013-01-14 | Budgeted Labor Units | 2012-09-01: 297; 2012-10-01: 363; 2012-11-01: 332; 2012-12-01: 316; 2013-01-01: 132
EC00620.5 Garage 1 |  |  | 0% | 2011-06-23 | 2012-12-18 | Actual Labor Cost
EC00620.5 Garage 1 |  |  | 0% | 2011-06-23 | 2012-12-18 | Budgeted Labor Cost | 2011-06-01: 7077.97; 2011-07-01: 26033.9; 2011-08-01: 29938.98; 2011-09-01: 27335.59; 2011-10-01: 19252.88; 2011-11-01: 20501.69; 2011-12-01: 20501.69; 2012-01-01: 14347.43; 2012-02-01: 10351.76; 2012-03-01: 10844.71; 2012-04-01: 10351.76; 2012-05-01: 10176.47; 2012-06-01: 22554.04; 2012-07-01: 23100; 2012-08-01: 45200; 2012-09-01: 38718.75; 2012-10-01: 36800; 2012-11-01: 32150; 2012-12-01: 9390
EC00620.5 Garage 1 |  |  | 0% | 2011-06-23 | 2012-12-18 | Actual Labor Units
EC00620.5 Garage 1 |  |  | 0% | 2011-06-23 | 2012-12-18 | Budgeted Labor Units | 2011-06-01: 94; 2011-07-01: 347; 2011-08-01: 399; 2011-09-01: 364; 2011-10-01: 264; 2011-11-01: 273; 2011-12-01: 273; 2012-01-01: 192; 2012-02-01: 128; 2012-03-01: 134; 2012-04-01: 128; 2012-05-01: 127; 2012-06-01: 274; 2012-07-01: 280; 2012-08-01: 572; 2012-09-01: 506; 2012-10-01: 491; 2012-11-01: 429; 2012-12-01: 138
EC1420 | Start Garage | EC00620.5 | 0% | 2011-06-23 |  | Actual Labor Cost
EC1420 | Start Garage | EC00620.5 | 0% | 2011-06-23 |  | Budgeted Labor Cost
EC1420 | Start Garage | EC00620.5 | 0% | 2011-06-23 |  | Actual Labor Units
EC1420 | Start Garage | EC00620.5 | 0% | 2011-06-23 |  | Budgeted Labor Units
EC1430 | Shop Drawings, Review & Approval | EC00620.5 | 0% | 2011-06-23 | 2011-10-05 | Actual Labor Cost
EC1430 | Shop Drawings, Review & Approval | EC00620.5 | 0% | 2011-06-23 | 2011-10-05 | Budgeted Labor Cost | 2011-06-01: 7077.97; 2011-07-01: 26033.9; 2011-08-01: 29938.98; 2011-09-01: 27335.59; 2011-10-01: 1252.88
EC1430 | Shop Drawings, Review & Approval | EC00620.5 | 0% | 2011-06-23 | 2011-10-05 | Actual Labor Units
EC1430 | Shop Drawings, Review & Approval | EC00620.5 | 0% | 2011-06-23 | 2011-10-05 | Budgeted Labor Units | 2011-06-01: 94; 2011-07-01: 347; 2011-08-01: 399; 2011-09-01: 364; 2011-10-01: 24
EC1810 | Fab & Delivery | EC00620.5 | 0% | 2011-10-05 | 2012-01-18 | Actual Labor Cost
EC1810 | Fab & Delivery | EC00620.5 | 0% | 2011-10-05 | 2012-01-18 | Budgeted Labor Cost | 2011-10-01: 18000; 2011-11-01: 20501.69; 2011-12-01: 20501.69; 2012-01-01: 9726.1
EC1810 | Fab & Delivery | EC00620.5 | 0% | 2011-10-05 | 2012-01-18 | Actual Labor Units
EC1810 | Fab & Delivery | EC00620.5 | 0% | 2011-10-05 | 2012-01-18 | Budgeted Labor Units | 2011-10-01: 240; 2011-11-01: 273; 2011-12-01: 273; 2012-01-01: 135
EC2090 | Erect Precast Structure | EC00620.5 | 0% | 2012-01-18 | 2012-06-01 | Actual Labor Cost
EC2090 | Erect Precast Structure | EC00620.5 | 0% | 2012-01-18 | 2012-06-01 | Budgeted Labor Cost | 2012-01-01: 4621.32; 2012-02-01: 10351.76; 2012-03-01: 10844.71; 2012-04-01: 10351.76; 2012-05-01: 10176.47; 2012-06-01: 72.79
EC2090 | Erect Precast Structure | EC00620.5 | 0% | 2012-01-18 | 2012-06-01 | Actual Labor Units
EC2090 | Erect Precast Structure | EC00620.5 | 0% | 2012-01-18 | 2012-06-01 | Budgeted Labor Units | 2012-01-01: 57; 2012-02-01: 128; 2012-03-01: 134; 2012-04-01: 128; 2012-05-01: 127; 2012-06-01: 1
EC2280 | Fire Protection and Lighting | EC00620.5 | 0% | 2012-06-01 | 2012-09-13 | Actual Labor Cost
EC2280 | Fire Protection and Lighting | EC00620.5 | 0% | 2012-06-01 | 2012-09-13 | Budgeted Labor Cost | 2012-06-01: 22481.25; 2012-07-01: 23100; 2012-08-01: 25300; 2012-09-01: 8318.75
EC2280 | Fire Protection and Lighting | EC00620.5 | 0% | 2012-06-01 | 2012-09-13 | Actual Labor Units
EC2280 | Fire Protection and Lighting | EC00620.5 | 0% | 2012-06-01 | 2012-09-13 | Budgeted Labor Units | 2012-06-01: 272; 2012-07-01: 280; 2012-08-01: 307; 2012-09-01: 101
EC2310 | Finishes, Barrier Cables & Striping | EC00620.5 | 0% | 2012-08-15 | 2012-11-27 | Actual Labor Cost
EC2310 | Finishes, Barrier Cables & Striping | EC00620.5 | 0% | 2012-08-15 | 2012-11-27 | Budgeted Labor Cost | 2012-08-01: 19900; 2012-09-01: 30400; 2012-10-01: 36800; 2012-11-01: 28100
EC2310 | Finishes, Barrier Cables & Striping | EC00620.5 | 0% | 2012-08-15 | 2012-11-27 | Actual Labor Units
EC2310 | Finishes, Barrier Cables & Striping | EC00620.5 | 0% | 2012-08-15 | 2012-11-27 | Budgeted Labor Units | 2012-08-01: 265; 2012-09-01: 405; 2012-10-01: 491; 2012-11-01: 375
EC2380 | Punchlist Garage | EC00620.5 | 0% | 2012-11-27 | 2012-12-18 | Actual Labor Cost
EC2380 | Punchlist Garage | EC00620.5 | 0% | 2012-11-27 | 2012-12-18 | Budgeted Labor Cost | 2012-11-01: 4050; 2012-12-01: 9390
EC2380 | Punchlist Garage | EC00620.5 | 0% | 2012-11-27 | 2012-12-18 | Actual Labor Units
EC2380 | Punchlist Garage | EC00620.5 | 0% | 2012-11-27 | 2012-12-18 | Budgeted Labor Units | 2012-11-01: 54; 2012-12-01: 138
EC2390 | Complete Garage 1 | EC00620.5 | 0% |  | 2012-12-18 | Actual Labor Cost
EC2390 | Complete Garage 1 | EC00620.5 | 0% |  | 2012-12-18 | Budgeted Labor Cost
EC2390 | Complete Garage 1 | EC00620.5 | 0% |  | 2012-12-18 | Actual Labor Units
EC2390 | Complete Garage 1 | EC00620.5 | 0% |  | 2012-12-18 | Budgeted Labor Units
EC2400 | Complete Garage | EC00620.5 | 0% |  | 2012-12-18 | Actual Labor Cost
EC2400 | Complete Garage | EC00620.5 | 0% |  | 2012-12-18 | Budgeted Labor Cost
EC2400 | Complete Garage | EC00620.5 | 0% |  | 2012-12-18 | Actual Labor Units
EC2400 | Complete Garage | EC00620.5 | 0% |  | 2012-12-18 | Budgeted Labor Units
EC00620.6 Garage 2 |  |  | 31.41% | 01-Nov-10 A | 2012-07-05 | Actual Labor Cost | 2010-11-01: 14766.1; 2010-12-01: 14766.1; 2011-01-01: 14766.1; 2011-02-01: 7322.03; 2011-03-01: 11040; 2011-04-01: 10080
EC00620.6 Garage 2 |  |  | 31.41% | 01-Nov-10 A | 2012-07-05 | Budgeted Labor Cost | 2010-11-01: 13667.8; 2010-12-01: 13667.8; 2011-01-01: 13667.8; 2011-02-01: 7216.27; 2011-03-01: 11040; 2011-04-01: 10080; 2011-05-01: 10781.3; 2011-06-01: 21531.43; 2011-07-01: 18701.3; 2011-08-01: 21506.49; 2011-09-01: 19636.36; 2011-10-01: 17417.45; 2011-11-01: 23692.31; 2011-12-01: 24849.45; 2012-01-01: 32692.31; 2012-02-01: 14400; 2012-03-01: 15085.71; 2012-04-01: 14207.14; 2012-05-01: 13200; 2012-06-01: 12600; 2012-07-01: 1350
EC00620.6 Garage 2 |  |  | 31.41% | 01-Nov-10 A | 2012-07-05 | Actual Labor Units | 2010-11-01: 198; 2010-12-01: 198; 2011-01-01: 198; 2011-02-01: 98; 2011-03-01: 147; 2011-04-01: 134
EC00620.6 Garage 2 |  |  | 31.41% | 01-Nov-10 A | 2012-07-05 | Budgeted Labor Units | 2010-11-01: 182; 2010-12-01: 182; 2011-01-01: 182; 2011-02-01: 100; 2011-03-01: 147; 2011-04-01: 134; 2011-05-01: 144; 2011-06-01: 287; 2011-07-01: 249; 2011-08-01: 287; 2011-09-01: 262; 2011-10-01: 231; 2011-11-01: 287; 2011-12-01: 303; 2012-01-01: 417; 2012-02-01: 192; 2012-03-01: 201; 2012-04-01: 189; 2012-05-01: 176; 2012-06-01: 168; 2012-07-01: 18
EC1020 | Design Building Addition | EC00620.6 | 100% | 01-Nov-10 A |  | Actual Labor Cost
EC1020 | Design Building Addition | EC00620.6 | 100% | 01-Nov-10 A |  | Budgeted Labor Cost
EC1020 | Design Building Addition | EC00620.6 | 100% | 01-Nov-10 A |  | Actual Labor Units
EC1020 | Design Building Addition | EC00620.6 | 100% | 01-Nov-10 A |  | Budgeted Labor Units
EC1030 | Shop Drawings, Review and Approval | EC00620.6 | 100% | 01-Nov-10 A | 10-Feb-11 A | Actual Labor Cost | 2010-11-01: 14766.1; 2010-12-01: 14766.1; 2011-01-01: 14766.1; 2011-02-01: 4922.03
EC1030 | Shop Drawings, Review and Approval | EC00620.6 | 100% | 01-Nov-10 A | 10-Feb-11 A | Budgeted Labor Cost | 2010-11-01: 13667.8; 2010-12-01: 13667.8; 2011-01-01: 13667.8; 2011-02-01: 4816.27
EC1030 | Shop Drawings, Review and Approval | EC00620.6 | 100% | 01-Nov-10 A | 10-Feb-11 A | Actual Labor Units | 2010-11-01: 198; 2010-12-01: 198; 2011-01-01: 198; 2011-02-01: 66
EC1030 | Shop Drawings, Review and Approval | EC00620.6 | 100% | 01-Nov-10 A | 10-Feb-11 A | Budgeted Labor Units | 2010-11-01: 182; 2010-12-01: 182; 2011-01-01: 182; 2011-02-01: 68
EC1180 | Fab & Delivery | EC00620.6 | 80.56% | 22-Feb-11 A | 2011-05-31 | Actual Labor Cost | 2011-02-01: 2400; 2011-03-01: 11040; 2011-04-01: 10080
EC1180 | Fab & Delivery | EC00620.6 | 80.56% | 22-Feb-11 A | 2011-05-31 | Budgeted Labor Cost | 2011-02-01: 2400; 2011-03-01: 11040; 2011-04-01: 10080; 2011-05-01: 10080; 2011-06-01: 960
EC1180 | Fab & Delivery | EC00620.6 | 80.56% | 22-Feb-11 A | 2011-05-31 | Actual Labor Units | 2011-02-01: 32; 2011-03-01: 147; 2011-04-01: 134
EC1180 | Fab & Delivery | EC00620.6 | 80.56% | 22-Feb-11 A | 2011-05-31 | Budgeted Labor Units | 2011-02-01: 32; 2011-03-01: 147; 2011-04-01: 134; 2011-05-01: 134; 2011-06-01: 13
EC1280 | Erect Precast Structure | EC00620.6 | 0% | 2011-05-31 | 2011-10-14 | Actual Labor Cost
EC1280 | Erect Precast Structure | EC00620.6 | 0% | 2011-05-31 | 2011-10-14 | Budgeted Labor Cost | 2011-05-01: 701.3; 2011-06-01: 20571.43; 2011-07-01: 18701.3; 2011-08-01: 21506.49; 2011-09-01: 19636.36; 2011-10-01: 4161.04
EC1280 | Erect Precast Structure | EC00620.6 | 0% | 2011-05-31 | 2011-10-14 | Actual Labor Units
EC1280 | Erect Precast Structure | EC00620.6 | 0% | 2011-05-31 | 2011-10-14 | Budgeted Labor Units | 2011-05-01: 9; 2011-06-01: 274; 2011-07-01: 249; 2011-08-01: 287; 2011-09-01: 262; 2011-10-01: 70
EC1590 | Fire Protection and Lighting | EC00620.6 | 0% | 2011-10-14 | 2012-01-27 | Actual Labor Cost
EC1590 | Fire Protection and Lighting | EC00620.6 | 0% | 2011-10-14 | 2012-01-27 | Budgeted Labor Cost | 2011-10-01: 13256.41; 2011-11-01: 23692.31; 2011-12-01: 23692.31; 2012-01-01: 18292.31
EC1590 | Fire Protection and Lighting | EC00620.6 | 0% | 2011-10-14 | 2012-01-27 | Actual Labor Units
EC1590 | Fire Protection and Lighting | EC00620.6 | 0% | 2011-10-14 | 2012-01-27 | Budgeted Labor Units | 2011-10-01: 161; 2011-11-01: 287; 2011-12-01: 287; 2012-01-01: 225
EC1680 | Finishes and Striping | EC00620.6 | 0% | 2011-12-29 | 2012-04-26 | Actual Labor Cost
EC1680 | Finishes and Striping | EC00620.6 | 0% | 2011-12-29 | 2012-04-26 | Budgeted Labor Cost | 2011-12-01: 1157.14; 2012-01-01: 14400; 2012-02-01: 14400; 2012-03-01: 15085.71; 2012-04-01: 12557.14
EC1680 | Finishes and Striping | EC00620.6 | 0% | 2011-12-29 | 2012-04-26 | Actual Labor Units
EC1680 | Finishes and Striping | EC00620.6 | 0% | 2011-12-29 | 2012-04-26 | Budgeted Labor Units | 2011-12-01: 15; 2012-01-01: 192; 2012-02-01: 192; 2012-03-01: 201; 2012-04-01: 167
EC2060 | Punch List Garage | EC00620.6 | 0% | 2012-04-26 | 2012-07-05 | Actual Labor Cost
EC2060 | Punch List Garage | EC00620.6 | 0% | 2012-04-26 | 2012-07-05 | Budgeted Labor Cost | 2012-04-01: 1650; 2012-05-01: 13200; 2012-06-01: 12600; 2012-07-01: 1350
EC2060 | Punch List Garage | EC00620.6 | 0% | 2012-04-26 | 2012-07-05 | Actual Labor Units
EC2060 | Punch List Garage | EC00620.6 | 0% | 2012-04-26 | 2012-07-05 | Budgeted Labor Units | 2012-04-01: 22; 2012-05-01: 176; 2012-06-01: 168; 2012-07-01: 18
EC2180 | Complete Garage 2 | EC00620.6 | 0% |  | 2012-07-05 | Actual Labor Cost
EC2180 | Complete Garage 2 | EC00620.6 | 0% |  | 2012-07-05 | Budgeted Labor Cost
EC2180 | Complete Garage 2 | EC00620.6 | 0% |  | 2012-07-05 | Actual Labor Units
EC2180 | Complete Garage 2 | EC00620.6 | 0% |  | 2012-07-05 | Budgeted Labor Units
EC2190 | Complete Garage | EC00620.6 | 0% |  | 2012-07-05 | Actual Labor Cost
EC2190 | Complete Garage | EC00620.6 | 0% |  | 2012-07-05 | Budgeted Labor Cost
EC2190 | Complete Garage | EC00620.6 | 0% |  | 2012-07-05 | Actual Labor Units
EC2190 | Complete Garage | EC00620.6 | 0% |  | 2012-07-05 | Budgeted Labor Units
EC00620.7 Roads, Utilities & Pavers |  |  | 32.07% | 01-Nov-10 A | 2012-12-26 | Actual Labor Cost | 2010-11-01: 89952.55; 2010-12-01: 71301.96; 2011-01-01: 69021.96; 2011-02-01: 32478.54; 2011-03-01: 5750; 2011-04-01: 5250
EC00620.7 Roads, Utilities & Pavers |  |  | 32.07% | 01-Nov-10 A | 2012-12-26 | Budgeted Labor Cost | 2010-11-01: 83200; 2010-12-01: 64440; 2011-01-01: 62160; 2011-02-01: 30652.57; 2011-03-01: 5782.86; 2011-04-01: 5280; 2011-05-01: 4324.57; 2011-06-01: 43242.33; 2011-07-01: 41600; 2011-08-01: 22996.67; 2011-09-01: 31920; 2011-10-01: 88261; 2011-11-01: 107520; 2011-12-01: 107520; 2012-01-01: 21004; 2012-05-01: 5775; 2012-06-01: 95448; 2012-07-01: 97104; 2012-08-01: 106352; 2012-09-01: 103248; 2012-10-01: 103554.8; 2012-11-01: 51681; 2012-12-01: 34034
EC00620.7 Roads, Utilities & Pavers |  |  | 32.07% | 01-Nov-10 A | 2012-12-26 | Actual Labor Units | 2010-11-01: 921; 2010-12-01: 776; 2011-01-01: 752; 2011-02-01: 375; 2011-03-01: 144; 2011-04-01: 131
EC00620.7 Roads, Utilities & Pavers |  |  | 32.07% | 01-Nov-10 A | 2012-12-26 | Budgeted Labor Units | 2010-11-01: 848; 2010-12-01: 696; 2011-01-01: 672; 2011-02-01: 375; 2011-03-01: 145; 2011-04-01: 132; 2011-05-01: 108; 2011-06-01: 333; 2011-07-01: 320; 2011-08-01: 200; 2011-09-01: 336; 2011-10-01: 860; 2011-11-01: 1008; 2011-12-01: 1008; 2012-01-01: 198; 2012-05-01: 55; 2012-06-01: 990; 2012-07-01: 1008; 2012-08-01: 1104; 2012-09-01: 1030; 2012-10-01: 1052; 2012-11-01: 412; 2012-12-01: 262
EC1000 | Curbing | EC00620.7 | 100% | 01-Nov-10 A | 15-Feb-11 A | Actual Labor Cost | 2010-11-01: 22625.34; 2010-12-01: 22625.34; 2011-01-01: 22625.34; 2011-02-01: 10773.97
EC1000 | Curbing | EC00620.7 | 100% | 01-Nov-10 A | 15-Feb-11 A | Budgeted Labor Cost | 2010-11-01: 21840; 2010-12-01: 21840; 2011-01-01: 21840; 2011-02-01: 9360
EC1000 | Curbing | EC00620.7 | 100% | 01-Nov-10 A | 15-Feb-11 A | Actual Labor Units | 2010-11-01: 174; 2010-12-01: 174; 2011-01-01: 174; 2011-02-01: 83
EC1000 | Curbing | EC00620.7 | 100% | 01-Nov-10 A | 15-Feb-11 A | Budgeted Labor Units | 2010-11-01: 168; 2010-12-01: 168; 2011-01-01: 168; 2011-02-01: 72
EC1040 | Electric to Building 4 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 11-Feb-11 A | Actual Labor Cost | 2010-11-01: 19107.04; 2010-12-01: 19107.04; 2011-01-01: 19107.04; 2011-02-01: 7278.87
EC1040 | Electric to Building 4 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 11-Feb-11 A | Budgeted Labor Cost | 2010-11-01: 15960; 2010-12-01: 15960; 2011-01-01: 15960; 2011-02-01: 6840
EC1040 | Electric to Building 4 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 11-Feb-11 A | Actual Labor Units | 2010-11-01: 201; 2010-12-01: 201; 2011-01-01: 201; 2011-02-01: 77
EC1040 | Electric to Building 4 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 11-Feb-11 A | Budgeted Labor Units | 2010-11-01: 168; 2010-12-01: 168; 2011-01-01: 168; 2011-02-01: 72
EC1050 | Electric to Building 3 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 06-Dec-10 A | Actual Labor Cost | 2010-11-01: 15960; 2010-12-01: 2280
EC1050 | Electric to Building 3 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 06-Dec-10 A | Budgeted Labor Cost | 2010-11-01: 15960; 2010-12-01: 2280
EC1050 | Electric to Building 3 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 06-Dec-10 A | Actual Labor Units | 2010-11-01: 168; 2010-12-01: 24
EC1050 | Electric to Building 3 Power Vault | EC00620.7 | 100% | 01-Nov-10 A | 06-Dec-10 A | Budgeted Labor Units | 2010-11-01: 168; 2010-12-01: 24
EC1100 | Storm Drainage Site Work | EC00620.7 | 100% | 02-Nov-10 A | 15-Feb-11 A | Actual Labor Cost | 2010-11-01: 18812.5; 2010-12-01: 19753.13; 2011-01-01: 19753.13; 2011-02-01: 9406.25
EC1100 | Storm Drainage Site Work | EC00620.7 | 100% | 02-Nov-10 A | 15-Feb-11 A | Budgeted Labor Cost | 2010-11-01: 16800; 2010-12-01: 17640; 2011-01-01: 17640; 2011-02-01: 8400
EC1100 | Storm Drainage Site Work | EC00620.7 | 100% | 02-Nov-10 A | 15-Feb-11 A | Actual Labor Units | 2010-11-01: 179; 2010-12-01: 188; 2011-01-01: 188; 2011-02-01: 90
EC1100 | Storm Drainage Site Work | EC00620.7 | 100% | 02-Nov-10 A | 15-Feb-11 A | Budgeted Labor Units | 2010-11-01: 160; 2010-12-01: 168; 2011-01-01: 168; 2011-02-01: 80
EC1110 | Site Electrical Work & Temp Power | EC00620.7 | 100% | 02-Nov-10 A | 17-Nov-10 A | Actual Labor Cost | 2010-11-01: 9500
EC1110 | Site Electrical Work & Temp Power | EC00620.7 | 100% | 02-Nov-10 A | 17-Nov-10 A | Budgeted Labor Cost | 2010-11-01: 9120
EC1110 | Site Electrical Work & Temp Power | EC00620.7 | 100% | 02-Nov-10 A | 17-Nov-10 A | Actual Labor Units | 2010-11-01: 100
EC1110 | Site Electrical Work & Temp Power | EC00620.7 | 100% | 02-Nov-10 A | 17-Nov-10 A | Budgeted Labor Units | 2010-11-01: 96
EC1130 | Walkways | EC00620.7 | 100% | 15-Nov-10 A | 16-Feb-11 A | Actual Labor Cost | 2010-11-01: 3947.66; 2010-12-01: 7536.45; 2011-01-01: 7536.45; 2011-02-01: 4019.44
EC1130 | Walkways | EC00620.7 | 100% | 15-Nov-10 A | 16-Feb-11 A | Budgeted Labor Cost | 2010-11-01: 3520; 2010-12-01: 6720; 2011-01-01: 6720; 2011-02-01: 4544
EC1130 | Walkways | EC00620.7 | 100% | 15-Nov-10 A | 16-Feb-11 A | Actual Labor Units | 2010-11-01: 99; 2010-12-01: 188; 2011-01-01: 188; 2011-02-01: 100
EC1130 | Walkways | EC00620.7 | 100% | 15-Nov-10 A | 16-Feb-11 A | Budgeted Labor Units | 2010-11-01: 88; 2010-12-01: 168; 2011-01-01: 168; 2011-02-01: 114
EC1200 | Roadway Pavers | EC00620.7 | 78.57% | 23-Feb-11 A | 2011-06-02 | Actual Labor Cost | 2011-02-01: 1000; 2011-03-01: 5750; 2011-04-01: 5250
EC1200 | Roadway Pavers | EC00620.7 | 78.57% | 23-Feb-11 A | 2011-06-02 | Budgeted Labor Cost | 2011-02-01: 1508.57; 2011-03-01: 5782.86; 2011-04-01: 5280; 2011-05-01: 4324.57
EC1200 | Roadway Pavers | EC00620.7 | 78.57% | 23-Feb-11 A | 2011-06-02 | Actual Labor Units | 2011-02-01: 25; 2011-03-01: 144; 2011-04-01: 131
EC1200 | Roadway Pavers | EC00620.7 | 78.57% | 23-Feb-11 A | 2011-06-02 | Budgeted Labor Units | 2011-02-01: 38; 2011-03-01: 145; 2011-04-01: 132; 2011-05-01: 108
EC1270 | Finish Paving, Striping and Signs | EC00620.7 | 0% | 2011-06-02 | 2011-08-10 | Actual Labor Cost
EC1270 | Finish Paving, Striping and Signs | EC00620.7 | 0% | 2011-06-02 | 2011-08-10 | Budgeted Labor Cost | 2011-06-01: 43242.33; 2011-07-01: 41600; 2011-08-01: 14997.67
EC1270 | Finish Paving, Striping and Signs | EC00620.7 | 0% | 2011-06-02 | 2011-08-10 | Actual Labor Units
EC1270 | Finish Paving, Striping and Signs | EC00620.7 | 0% | 2011-06-02 | 2011-08-10 | Budgeted Labor Units | 2011-06-01: 333; 2011-07-01: 320; 2011-08-01: 115
EC1440 | Electric to Building 2 Power Vault | EC00620.7 | 0% | 2011-08-24 | 2012-01-05 | Actual Labor Cost
EC1440 | Electric to Building 2 Power Vault | EC00620.7 | 0% | 2011-08-24 | 2012-01-05 | Budgeted Labor Cost | 2011-08-01: 7999; 2011-09-01: 31920; 2011-10-01: 31920; 2011-11-01: 31920; 2011-12-01: 31920; 2012-01-01: 2945
EC1440 | Electric to Building 2 Power Vault | EC00620.7 | 0% | 2011-08-24 | 2012-01-05 | Actual Labor Units
EC1440 | Electric to Building 2 Power Vault | EC00620.7 | 0% | 2011-08-24 | 2012-01-05 | Budgeted Labor Units | 2011-08-01: 84; 2011-09-01: 336; 2011-10-01: 336; 2011-11-01: 336; 2011-12-01: 336; 2012-01-01: 31
EC1610 | Curbs & Paving | EC00620.7 | 0% | 2011-10-14 | 2012-01-09 | Actual Labor Cost
EC1610 | Curbs & Paving | EC00620.7 | 0% | 2011-10-14 | 2012-01-09 | Budgeted Labor Cost | 2011-10-01: 24440; 2011-11-01: 43680; 2011-12-01: 43680; 2012-01-01: 8008
EC1610 | Curbs & Paving | EC00620.7 | 0% | 2011-10-14 | 2012-01-09 | Actual Labor Units
EC1610 | Curbs & Paving | EC00620.7 | 0% | 2011-10-14 | 2012-01-09 | Budgeted Labor Units | 2011-10-01: 188; 2011-11-01: 336; 2011-12-01: 336; 2012-01-01: 62
EC1750 | Electric to Building 1 Power Vault | EC00620.7 | 0% | 2011-10-03 | 2012-01-11 | Actual Labor Cost
EC1750 | Electric to Building 1 Power Vault | EC00620.7 | 0% | 2011-10-03 | 2012-01-11 | Budgeted Labor Cost | 2011-10-01: 31901; 2011-11-01: 31920; 2011-12-01: 31920; 2012-01-01: 10051
EC1750 | Electric to Building 1 Power Vault | EC00620.7 | 0% | 2011-10-03 | 2012-01-11 | Actual Labor Units
EC1750 | Electric to Building 1 Power Vault | EC00620.7 | 0% | 2011-10-03 | 2012-01-11 | Budgeted Labor Units | 2011-10-01: 336; 2011-11-01: 336; 2011-12-01: 336; 2012-01-01: 106
EC2250 | Fountain/Water Feature | EC00620.7 | 0% | 2012-05-25 | 2012-11-07 | Actual Labor Cost
EC2250 | Fountain/Water Feature | EC00620.7 | 0% | 2012-05-25 | 2012-11-07 | Budgeted Labor Cost | 2012-05-01: 5775; 2012-06-01: 35280; 2012-07-01: 35280; 2012-08-01: 38640; 2012-09-01: 31920; 2012-10-01: 38640; 2012-11-01: 8001
EC2250 | Fountain/Water Feature | EC00620.7 | 0% | 2012-05-25 | 2012-11-07 | Actual Labor Units
EC2250 | Fountain/Water Feature | EC00620.7 | 0% | 2012-05-25 | 2012-11-07 | Budgeted Labor Units | 2012-05-01: 55; 2012-06-01: 336; 2012-07-01: 336; 2012-08-01: 368; 2012-09-01: 304; 2012-10-01: 368; 2012-11-01: 76
EC2260 | Entry Feature/Sign Wall | EC00620.7 | 0% | 2012-06-01 | 2012-10-26 | Actual Labor Cost
EC2260 | Entry Feature/Sign Wall | EC00620.7 | 0% | 2012-06-01 | 2012-10-26 | Budgeted Labor Cost | 2012-06-01: 17658; 2012-07-01: 18144; 2012-08-01: 19872; 2012-09-01: 16416; 2012-10-01: 17074.8
EC2260 | Entry Feature/Sign Wall | EC00620.7 | 0% | 2012-06-01 | 2012-10-26 | Actual Labor Units
EC2260 | Entry Feature/Sign Wall | EC00620.7 | 0% | 2012-06-01 | 2012-10-26 | Budgeted Labor Units | 2012-06-01: 327; 2012-07-01: 336; 2012-08-01: 368; 2012-09-01: 304; 2012-10-01: 316
EC2290 | Curbs & Paving | EC00620.7 | 0% | 2012-06-01 | 2012-09-13 | Actual Labor Cost
EC2290 | Curbs & Paving | EC00620.7 | 0% | 2012-06-01 | 2012-09-13 | Budgeted Labor Cost | 2012-06-01: 42510; 2012-07-01: 43680; 2012-08-01: 47840; 2012-09-01: 15730
EC2290 | Curbs & Paving | EC00620.7 | 0% | 2012-06-01 | 2012-09-13 | Actual Labor Units
EC2290 | Curbs & Paving | EC00620.7 | 0% | 2012-06-01 | 2012-09-13 | Budgeted Labor Units | 2012-06-01: 327; 2012-07-01: 336; 2012-08-01: 368; 2012-09-01: 121
EC2340 | Curbs & Paving | EC00620.7 | 0% | 2012-09-04 | 2012-12-26 | Actual Labor Cost
EC2340 | Curbs & Paving | EC00620.7 | 0% | 2012-09-04 | 2012-12-26 | Budgeted Labor Cost | 2012-09-01: 39182; 2012-10-01: 47840; 2012-11-01: 43680; 2012-12-01: 34034
EC2340 | Curbs & Paving | EC00620.7 | 0% | 2012-09-04 | 2012-12-26 | Actual Labor Units
EC2340 | Curbs & Paving | EC00620.7 | 0% | 2012-09-04 | 2012-12-26 | Budgeted Labor Units | 2012-09-01: 301; 2012-10-01: 368; 2012-11-01: 336; 2012-12-01: 262
EC00620.8 Landscape & Irrigation |  |  | 0% | 2011-05-24 | 2014-01-08 | Actual Labor Cost
EC00620.8 Landscape & Irrigation |  |  | 0% | 2011-05-24 | 2014-01-08 | Budgeted Labor Cost | 2011-05-01: 3200; 2011-06-01: 14080; 2011-07-01: 12800; 2011-08-01: 640; 2012-11-01: 1800; 2012-12-01: 4864.86; 2013-01-01: 5351.35; 2013-02-01: 4627.03; 2013-03-01: 2837.84; 2013-04-01: 2972.97; 2013-05-01: 2972.97; 2013-06-01: 2702.7; 2013-07-01: 2972.97; 2013-08-01: 2972.97; 2013-09-01: 2702.7; 2013-10-01: 3108.11; 2013-11-01: 2702.7; 2013-12-01: 2837.84; 2014-01-01: 756.76
EC00620.8 Landscape & Irrigation |  |  | 0% | 2011-05-24 | 2014-01-08 | Actual Labor Units
EC00620.8 Landscape & Irrigation |  |  | 0% | 2011-05-24 | 2014-01-08 | Budgeted Labor Units | 2011-05-01: 80; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 16; 2012-11-01: 40; 2012-12-01: 108; 2013-01-01: 119; 2013-02-01: 102; 2013-03-01: 57; 2013-04-01: 59; 2013-05-01: 59; 2013-06-01: 54; 2013-07-01: 59; 2013-08-01: 59; 2013-09-01: 54; 2013-10-01: 62; 2013-11-01: 54; 2013-12-01: 57; 2014-01-01: 15
EC1600 | Site Cleanup | EC00620.8 | 0% | 2011-05-24 | 2011-08-02 | Actual Labor Cost
EC1600 | Site Cleanup | EC00620.8 | 0% | 2011-05-24 | 2011-08-02 | Budgeted Labor Cost | 2011-05-01: 3200; 2011-06-01: 14080; 2011-07-01: 12800; 2011-08-01: 640
EC1600 | Site Cleanup | EC00620.8 | 0% | 2011-05-24 | 2011-08-02 | Actual Labor Units
EC1600 | Site Cleanup | EC00620.8 | 0% | 2011-05-24 | 2011-08-02 | Budgeted Labor Units | 2011-05-01: 80; 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 16
EC2360 | Landscape & Irrigation | EC00620.8 | 0% | 2012-11-20 | 2014-01-08 | Actual Labor Cost
EC2360 | Landscape & Irrigation | EC00620.8 | 0% | 2012-11-20 | 2014-01-08 | Budgeted Labor Cost | 2012-11-01: 1800; 2012-12-01: 4864.86; 2013-01-01: 5351.35; 2013-02-01: 4627.03; 2013-03-01: 2837.84; 2013-04-01: 2972.97; 2013-05-01: 2972.97; 2013-06-01: 2702.7; 2013-07-01: 2972.97; 2013-08-01: 2972.97; 2013-09-01: 2702.7; 2013-10-01: 3108.11; 2013-11-01: 2702.7; 2013-12-01: 2837.84; 2014-01-01: 756.76
EC2360 | Landscape & Irrigation | EC00620.8 | 0% | 2012-11-20 | 2014-01-08 | Actual Labor Units
EC2360 | Landscape & Irrigation | EC00620.8 | 0% | 2012-11-20 | 2014-01-08 | Budgeted Labor Units | 2012-11-01: 40; 2012-12-01: 108; 2013-01-01: 119; 2013-02-01: 102; 2013-03-01: 57; 2013-04-01: 59; 2013-05-01: 59; 2013-06-01: 54; 2013-07-01: 59; 2013-08-01: 59; 2013-09-01: 54; 2013-10-01: 62; 2013-11-01: 54; 2013-12-01: 57; 2014-01-01: 15
EC00630 Saratoga Senior Community |  |  | 0% | 2011-06-01 | 2015-01-05 | Actual Labor Cost
EC00630 Saratoga Senior Community |  |  | 0% | 2011-06-01 | 2015-01-05 | Budgeted Labor Cost | [9 empty] | 228837.29 | 238833.9 | 268938.98 | 177810.35 | 48360 | 44580 | 42480 | 50857.82 | 59569.06 | 77034.38 | 66522.37 | 153405.38 | 292793.37 | 431905.6 | 447650.77 | 350680.94 | 332472.77 | 275178.57 | 254003.64 | 280114.96 | 178616.46 | 229426.37 | 354527.07 | 335496.37 | 284123.93 | 299889.52 | 267459.28 | 156410.77 | 170214.41 | 52878.83 | 24454.22 | 19456.66 | 5405.41 | 5675.68 | 5945.95 | 5945.95 | 5675.68 | 6216.22 | 5675.68 | 5945.95 | 6216.22 | 5405.41 | 6216.22 | 739.86
EC00630 Saratoga Senior Community |  |  | 0% | 2011-06-01 | 2015-01-05 | Actual Labor Units
EC00630 Saratoga Senior Community |  |  | 0% | 2011-06-01 | 2015-01-05 | Budgeted Labor Units | [9 empty] | 2438 | 2747 | 3159 | 2309 | 1037 | 929 | 869 | 942 | 909 | 1164 | 1092 | 1934 | 3231 | 4708 | 4990 | 3984 | 4111 | 3771 | 3570 | 3838 | 2630 | 3195 | 4433 | 4214 | 3656 | 4163 | 3697 | 2049 | 2465 | 970 | 479 | 383 | 108 | 114 | 119 | 119 | 114 | 124 | 114 | 119 | 124 | 108 | 124 | 15
EC1010 | Curbs & Paving | EC00630 | 0% | 2011-06-01 |  | Actual Labor Cost
EC1010 | Curbs & Paving | EC00630 | 0% | 2011-06-01 |  | Budgeted Labor Cost
EC1010 | Curbs & Paving | EC00630 | 0% | 2011-06-01 |  | Actual Labor Units
EC1010 | Curbs & Paving | EC00630 | 0% | 2011-06-01 |  | Budgeted Labor Units
EC1080 | Curbing | EC00630 | 0% | 2011-06-01 | 2015-01-05 | Actual Labor Cost
EC1080 | Curbing | EC00630 | 0% | 2011-06-01 | 2015-01-05 | Budgeted Labor Cost
EC1080 | Curbing | EC00630 | 0% | 2011-06-01 | 2015-01-05 | Actual Labor Units
EC1080 | Curbing | EC00630 | 0% | 2011-06-01 | 2015-01-05 | Budgeted Labor Units
EC2430 | Substantial Completion - All TCO | EC00630 | 0% |  | 2015-01-05 | Actual Labor Cost
EC2430 | Substantial Completion - All TCO | EC00630 | 0% |  | 2015-01-05 | Budgeted Labor Cost
EC2430 | Substantial Completion - All TCO | EC00630 | 0% |  | 2015-01-05 | Actual Labor Units
EC2430 | Substantial Completion - All TCO | EC00630 | 0% |  | 2015-01-05 | Budgeted Labor Units
EC00630.1 Building 1 |  |  | 0% | 2011-06-01 | 2015-01-05 | Actual Labor Cost
EC00630.1 Building 1 |  |  | 0% | 2011-06-01 | 2015-01-05 | Budgeted Labor Cost | 2011-06-01: 17600; 2011-07-01: 16000; 2011-08-01: 12680; 2011-09-01: 5880; 2011-10-01: 5880; 2011-11-01: 5880; 2011-12-01: 5880; 2012-01-01: 5880; 2012-02-01: 5880; 2012-03-01: 6160; 2012-04-01: 17852; 2012-05-01: 72760; 2012-06-01: 79127.98; 2012-07-01: 94077.59; 2012-08-01: 105078.82; 2012-09-01: 79395.75; 2012-10-01: 93728.43; 2012-11-01: 83122.43; 2012-12-01: 68721.54; 2013-01-01: 87651.83; 2013-02-01: 56262.26; 2013-03-01: 52724.98; 2013-04-01: 60796.43; 2013-05-01: 56349.74; 2013-06-01: 39641.54; 2013-07-01: 50695.31; 2013-08-01: 49382.61; 2013-09-01: 39422.9; 2013-10-01: 43023.15; 2013-11-01: 9072.06
EC00630.1 Building 1 |  |  | 0% | 2011-06-01 | 2015-01-05 | Actual Labor Units
EC00630.1 Building 1 |  |  | 0% | 2011-06-01 | 2015-01-05 | Budgeted Labor Units | 2011-06-01: 176; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 267; 2012-05-01: 752; 2012-06-01: 864; 2012-07-01: 1201; 2012-08-01: 1403; 2012-09-01: 1091; 2012-10-01: 1288; 2012-11-01: 1141; 2012-12-01: 1000; 2013-01-01: 1146; 2013-02-01: 845; 2013-03-01: 835; 2013-04-01: 970; 2013-05-01: 892; 2013-06-01: 609; 2013-07-01: 775; 2013-08-01: 664; 2013-09-01: 555; 2013-10-01: 686; 2013-11-01: 159
EC2440 | Complete Building 1 | EC00630.1 | 0% |  | 2015-01-05 | Actual Labor Cost
EC2440 | Complete Building 1 | EC00630.1 | 0% |  | 2015-01-05 | Budgeted Labor Cost
EC2440 | Complete Building 1 | EC00630.1 | 0% |  | 2015-01-05 | Actual Labor Units
EC2440 | Complete Building 1 | EC00630.1 | 0% |  | 2015-01-05 | Budgeted Labor Units
EC00630.1.1 Structure |  |  | 0% | 2011-06-01 | 2012-05-01 | Actual Labor Cost
EC00630.1.1 Structure |  |  | 0% | 2011-06-01 | 2012-05-01 | Budgeted Labor Cost | 2011-06-01: 17600; 2011-07-01: 16000; 2011-08-01: 12680; 2011-09-01: 5880; 2011-10-01: 5880; 2011-11-01: 5880; 2011-12-01: 5880; 2012-01-01: 5880; 2012-02-01: 5880; 2012-03-01: 6160; 2012-04-01: 5852; 2012-05-01: 280
EC00630.1.1 Structure |  |  | 0% | 2011-06-01 | 2012-05-01 | Actual Labor Units
EC00630.1.1 Structure |  |  | 0% | 2011-06-01 | 2012-05-01 | Budgeted Labor Units | 2011-06-01: 176; 2011-07-01: 160; 2011-08-01: 184; 2011-09-01: 168; 2011-10-01: 168; 2011-11-01: 168; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 167; 2012-05-01: 8
EC1090 | Building Pad Including UG Utils | EC00630.1.1 | 0% | 2011-06-01 | 2011-08-17 | Actual Labor Cost
EC1090 | Building Pad Including UG Utils | EC00630.1.1 | 0% | 2011-06-01 | 2011-08-17 | Budgeted Labor Cost | 2011-06-01: 17600; 2011-07-01: 16000; 2011-08-01: 9600
EC1090 | Building Pad Including UG Utils | EC00630.1.1 | 0% | 2011-06-01 | 2011-08-17 | Actual Labor Units
EC1090 | Building Pad Including UG Utils | EC00630.1.1 | 0% | 2011-06-01 | 2011-08-17 | Budgeted Labor Units | 2011-06-01: 176; 2011-07-01: 160; 2011-08-01: 96
EC1140 | First Floor Masonry Structure | EC00630.1.1 | 0% | 2011-08-17 | 2011-09-06 | Actual Labor Cost
EC1140 | First Floor Masonry Structure | EC00630.1.1 | 0% | 2011-08-17 | 2011-09-06 | Budgeted Labor Cost | 2011-08-01: 3080; 2011-09-01: 700
EC1140 | First Floor Masonry Structure | EC00630.1.1 | 0% | 2011-08-17 | 2011-09-06 | Actual Labor Units
EC1140 | First Floor Masonry Structure | EC00630.1.1 | 0% | 2011-08-17 | 2011-09-06 | Budgeted Labor Units | 2011-08-01: 88; 2011-09-01: 20
EC1170 | Second Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-09-06 | 2011-10-13 | Actual Labor Cost
EC1170 | Second Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-09-06 | 2011-10-13 | Budgeted Labor Cost | 2011-09-01: 5180; 2011-10-01: 2380
EC1170 | Second Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-09-06 | 2011-10-13 | Actual Labor Units
EC1170 | Second Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-09-06 | 2011-10-13 | Budgeted Labor Units | 2011-09-01: 148; 2011-10-01: 68
EC1190 | Second Floor Masonry Structure | EC00630.1.1 | 0% | 2011-10-13 | 2011-11-02 | Actual Labor Cost
EC1190 | Second Floor Masonry Structure | EC00630.1.1 | 0% | 2011-10-13 | 2011-11-02 | Budgeted Labor Cost | 2011-10-01: 3500; 2011-11-01: 280
EC1190 | Second Floor Masonry Structure | EC00630.1.1 | 0% | 2011-10-13 | 2011-11-02 | Actual Labor Units
EC1190 | Second Floor Masonry Structure | EC00630.1.1 | 0% | 2011-10-13 | 2011-11-02 | Budgeted Labor Units | 2011-10-01: 100; 2011-11-01: 8
EC1210 | Third Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-11-02 | 2011-12-12 | Actual Labor Cost
EC1210 | Third Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-11-02 | 2011-12-12 | Budgeted Labor Cost | 2011-11-01: 5600; 2011-12-01: 1960
EC1210 | Third Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-11-02 | 2011-12-12 | Actual Labor Units
EC1210 | Third Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-11-02 | 2011-12-12 | Budgeted Labor Units | 2011-11-01: 160; 2011-12-01: 56
EC1240 | Third Floor Masonry Structure | EC00630.1.1 | 0% | 2011-12-12 | 2011-12-30 | Actual Labor Cost
EC1240 | Third Floor Masonry Structure | EC00630.1.1 | 0% | 2011-12-12 | 2011-12-30 | Budgeted Labor Cost | 2011-12-01: 3780
EC1240 | Third Floor Masonry Structure | EC00630.1.1 | 0% | 2011-12-12 | 2011-12-30 | Actual Labor Units
EC1240 | Third Floor Masonry Structure | EC00630.1.1 | 0% | 2011-12-12 | 2011-12-30 | Budgeted Labor Units | 2011-12-01: 108
EC1250 | Fourth Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-12-30 | 2012-02-08 | Actual Labor Cost
EC1250 | Fourth Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-12-30 | 2012-02-08 | Budgeted Labor Cost | 2011-12-01: 140; 2012-01-01: 5880; 2012-02-01: 1540
EC1250 | Fourth Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-12-30 | 2012-02-08 | Actual Labor Units
EC1250 | Fourth Floor Slab & Collar Beam | EC00630.1.1 | 0% | 2011-12-30 | 2012-02-08 | Budgeted Labor Units | 2011-12-01: 4; 2012-01-01: 168; 2012-02-01: 44
EC1300 | Fourth Floor Masonry Structure | EC00630.1.1 | 0% | 2012-02-08 | 2012-02-27 | Actual Labor Cost
EC1300 | Fourth Floor Masonry Structure | EC00630.1.1 | 0% | 2012-02-08 | 2012-02-27 | Budgeted Labor Cost | 2012-02-01: 3780
EC1300 | Fourth Floor Masonry Structure | EC00630.1.1 | 0% | 2012-02-08 | 2012-02-27 | Actual Labor Units
EC1300 | Fourth Floor Masonry Structure | EC00630.1.1 | 0% | 2012-02-08 | 2012-02-27 | Budgeted Labor Units | 2012-02-01: 108
EC1310 | Roof Slab | EC00630.1.1 | 0% | 2012-02-28 | 2012-04-04 | Actual Labor Cost
EC1310 | Roof Slab | EC00630.1.1 | 0% | 2012-02-28 | 2012-04-04 | Budgeted Labor Cost | 2012-02-01: 560; 2012-03-01: 6160; 2012-04-01: 840
EC1310 | Roof Slab | EC00630.1.1 | 0% | 2012-02-28 | 2012-04-04 | Actual Labor Units
EC1310 | Roof Slab | EC00630.1.1 | 0% | 2012-02-28 | 2012-04-04 | Budgeted Labor Units | 2012-02-01: 16; 2012-03-01: 176; 2012-04-01: 24
EC1340 | Stair and Elevator Masonry Structure | EC00630.1.1 | 0% | 2012-04-05 | 2012-04-12 | Actual Labor Cost
EC1340 | Stair and Elevator Masonry Structure | EC00630.1.1 | 0% | 2012-04-05 | 2012-04-12 | Budgeted Labor Cost | 2012-04-01: 1512
EC1340 | Stair and Elevator Masonry Structure | EC00630.1.1 | 0% | 2012-04-05 | 2012-04-12 | Actual Labor Units
EC1340 | Stair and Elevator Masonry Structure | EC00630.1.1 | 0% | 2012-04-05 | 2012-04-12 | Budgeted Labor Units | 2012-04-01: 43
EC1350 | Roof Slab/Collar Beam | EC00630.1.1 | 0% | 2012-04-12 | 2012-05-01 | Actual Labor Cost
EC1350 | Roof Slab/Collar Beam | EC00630.1.1 | 0% | 2012-04-12 | 2012-05-01 | Budgeted Labor Cost | 2012-04-01: 3500; 2012-05-01: 280
EC1350 | Roof Slab/Collar Beam | EC00630.1.1 | 0% | 2012-04-12 | 2012-05-01 | Actual Labor Units
EC1350 | Roof Slab/Collar Beam | EC00630.1.1 | 0% | 2012-04-12 | 2012-05-01 | Budgeted Labor Units | 2012-04-01: 100; 2012-05-01: 8
EC00630.1.2 Roof |  |  | 0% | 2012-05-01 | 2012-08-22 | Actual Labor Cost
EC00630.1.2 Roof |  |  | 0% | 2012-05-01 | 2012-08-22 | Budgeted Labor Cost | 2012-05-01: 43680; 2012-06-01: 30480; 2012-07-01: 25200; 2012-08-01: 10260
EC00630.1.2 Roof |  |  | 0% | 2012-05-01 | 2012-08-22 | Actual Labor Units
EC00630.1.2 Roof |  |  | 0% | 2012-05-01 | 2012-08-22 | Budgeted Labor Units | 2012-05-01: 504; 2012-06-01: 384; 2012-07-01: 336; 2012-08-01: 137
EC1390 | Place Roof Trusses and Sheathing | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Actual Labor Cost
EC1390 | Place Roof Trusses and Sheathing | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Budgeted Labor Cost | 2012-05-01: 31080; 2012-06-01: 8880
EC1390 | Place Roof Trusses and Sheathing | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Actual Labor Units
EC1390 | Place Roof Trusses and Sheathing | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Budgeted Labor Units | 2012-05-01: 336; 2012-06-01: 96
EC1400 | Place Mechanical Equipment Supports | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Actual Labor Cost
EC1400 | Place Mechanical Equipment Supports | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Budgeted Labor Cost | 2012-05-01: 12600; 2012-06-01: 3600
EC1400 | Place Mechanical Equipment Supports | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Actual Labor Units
EC1400 | Place Mechanical Equipment Supports | EC00630.1.2 | 0% | 2012-05-01 | 2012-06-08 | Budgeted Labor Units | 2012-05-01: 168; 2012-06-01: 48
EC1530 | Built-Up Asphalt Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-02 | Actual Labor Cost
EC1530 | Built-Up Asphalt Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-02 | Budgeted Labor Cost | 2012-06-01: 9000; 2012-07-01: 12600; 2012-08-01: 1080
EC1530 | Built-Up Asphalt Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-02 | Actual Labor Units
EC1530 | Built-Up Asphalt Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-02 | Budgeted Labor Units | 2012-06-01: 120; 2012-07-01: 168; 2012-08-01: 14
EC1540 | Felt and Tile Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-22 | Actual Labor Cost
EC1540 | Felt and Tile Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-22 | Budgeted Labor Cost | 2012-06-01: 9000; 2012-07-01: 12600; 2012-08-01: 9180
EC1540 | Felt and Tile Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-22 | Actual Labor Units
EC1540 | Felt and Tile Roofing | EC00630.1.2 | 0% | 2012-06-08 | 2012-08-22 | Budgeted Labor Units | 2012-06-01: 120; 2012-07-01: 168; 2012-08-01: 122
EC1780 | Roof Complete | EC00630.1.2 | 0% |  | 2012-08-22 | Actual Labor Cost
EC1780 | Roof Complete | EC00630.1.2 | 0% |  | 2012-08-22 | Budgeted Labor Cost
EC1780 | Roof Complete | EC00630.1.2 | 0% |  | 2012-08-22 | Actual Labor Units
EC1780 | Roof Complete | EC00630.1.2 | 0% |  | 2012-08-22 | Budgeted Labor Units
EC00630.1.3 Envelope |  |  | 0% | 2012-04-12 | 2013-02-11 | Actual Labor Cost
EC00630.1.3 Envelope |  |  | 0% | 2012-04-12 | 2013-02-11 | Budgeted Labor Cost | 2012-04-01: 12000; 2012-05-01: 28800; 2012-06-01: 40128; 2012-07-01: 35520; 2012-08-01: 35424; 2012-09-01: 18336; 2012-10-01: 22080; 2012-11-01: 20160; 2012-12-01: 21232; 2013-01-01: 34808; 2013-02-01: 6048
EC00630.1.3 Envelope |  |  | 0% | 2012-04-12 | 2013-02-11 | Actual Labor Units
EC00630.1.3 Envelope |  |  | 0% | 2012-04-12 | 2013-02-11 | Budgeted Labor Units | 2012-04-01: 100; 2012-05-01: 240; 2012-06-01: 334; 2012-07-01: 296; 2012-08-01: 295; 2012-09-01: 153; 2012-10-01: 184; 2012-11-01: 168; 2012-12-01: 218; 2013-01-01: 294; 2013-02-01: 50
EC1360 | Mobilize Scaffolding | EC00630.1.3 | 0% | 2012-04-12 | 2012-05-01 | Actual Labor Cost
EC1360 | Mobilize Scaffolding | EC00630.1.3 | 0% | 2012-04-12 | 2012-05-01 | Budgeted Labor Cost | 2012-04-01: 12000; 2012-05-01: 960
EC1360 | Mobilize Scaffolding | EC00630.1.3 | 0% | 2012-04-12 | 2012-05-01 | Actual Labor Units
EC1360 | Mobilize Scaffolding | EC00630.1.3 | 0% | 2012-04-12 | 2012-05-01 | Budgeted Labor Units | 2012-04-01: 100; 2012-05-01: 8
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.1.3 | 0% | 2012-05-01 | 2012-06-01 | Actual Labor Cost
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.1.3 | 0% | 2012-05-01 | 2012-06-01 | Budgeted Labor Cost | 2012-05-01: 20160; 2012-06-01: 576
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.1.3 | 0% | 2012-05-01 | 2012-06-01 | Actual Labor Units
EC1410 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.1.3 | 0% | 2012-05-01 | 2012-06-01 | Budgeted Labor Units | 2012-05-01: 168; 2012-06-01: 5
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.1.3 | 0% | 2012-05-24 | 2012-06-26 | Actual Labor Cost
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.1.3 | 0% | 2012-05-24 | 2012-06-26 | Budgeted Labor Cost | 2012-05-01: 4320; 2012-06-01: 16416
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.1.3 | 0% | 2012-05-24 | 2012-06-26 | Actual Labor Units
EC1470 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.1.3 | 0% | 2012-05-24 | 2012-06-26 | Budgeted Labor Units | 2012-05-01: 36; 2012-06-01: 137
EC1490 | Install Backing & Cauld Windows Floor1 | EC00630.1.3 | 0% | 2012-05-25 | 2012-06-12 | Actual Labor Cost
EC1490 | Install Backing & Cauld Windows Floor1 | EC00630.1.3 | 0% | 2012-05-25 | 2012-06-12 | Budgeted Labor Cost | 2012-05-01: 3360; 2012-06-01: 7008
EC1490 | Install Backing & Cauld Windows Floor1 | EC00630.1.3 | 0% | 2012-05-25 | 2012-06-12 | Actual Labor Units
EC1490 | Install Backing & Cauld Windows Floor1 | EC00630.1.3 | 0% | 2012-05-25 | 2012-06-12 | Budgeted Labor Units | 2012-05-01: 28; 2012-06-01: 58
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.1.3 | 0% | 2012-06-19 | 2012-07-17 | Actual Labor Cost
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.1.3 | 0% | 2012-06-19 | 2012-07-17 | Budgeted Labor Cost | 2012-06-01: 8544; 2012-07-01: 9600
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.1.3 | 0% | 2012-06-19 | 2012-07-17 | Actual Labor Units
EC1500 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.1.3 | 0% | 2012-06-19 | 2012-07-17 | Budgeted Labor Units | 2012-06-01: 71; 2012-07-01: 80
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00630.1.3 | 0% | 2012-06-20 | 2012-07-06 | Actual Labor Cost
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00630.1.3 | 0% | 2012-06-20 | 2012-07-06 | Budgeted Labor Cost | 2012-06-01: 7584; 2012-07-01: 2784
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00630.1.3 | 0% | 2012-06-20 | 2012-07-06 | Actual Labor Units
EC1510 | Install Backing & Cauld Windows Floor 2 | EC00630.1.3 | 0% | 2012-06-20 | 2012-07-06 | Budgeted Labor Units | 2012-06-01: 63; 2012-07-01: 23
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.1.3 | 0% | 2012-07-10 | 2012-08-13 | Actual Labor Cost
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.1.3 | 0% | 2012-07-10 | 2012-08-13 | Budgeted Labor Cost | 2012-07-01: 15360; 2012-08-01: 7968
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.1.3 | 0% | 2012-07-10 | 2012-08-13 | Actual Labor Units
EC1520 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.1.3 | 0% | 2012-07-10 | 2012-08-13 | Budgeted Labor Units | 2012-07-01: 128; 2012-08-01: 66
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00630.1.3 | 0% | 2012-07-11 | 2012-07-23 | Actual Labor Cost
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00630.1.3 | 0% | 2012-07-11 | 2012-07-23 | Budgeted Labor Cost | 2012-07-01: 7776
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00630.1.3 | 0% | 2012-07-11 | 2012-07-23 | Actual Labor Units
EC1570 | Install Backing & Cauld Windows Floor 3 | EC00630.1.3 | 0% | 2012-07-11 | 2012-07-23 | Budgeted Labor Units | 2012-07-01: 65
EC1580 | Stucco Bands | EC00630.1.3 | 0% | 2012-08-08 | 2012-08-23 | Actual Labor Cost
EC1580 | Stucco Bands | EC00630.1.3 | 0% | 2012-08-08 | 2012-08-23 | Budgeted Labor Cost | 2012-08-01: 10368
EC1580 | Stucco Bands | EC00630.1.3 | 0% | 2012-08-08 | 2012-08-23 | Actual Labor Units
EC1580 | Stucco Bands | EC00630.1.3 | 0% | 2012-08-08 | 2012-08-23 | Budgeted Labor Units | 2012-08-01: 86
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00630.1.3 | 0% | 2012-08-07 | 2012-08-22 | Actual Labor Cost
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00630.1.3 | 0% | 2012-08-07 | 2012-08-22 | Budgeted Labor Cost | 2012-08-01: 10368
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00630.1.3 | 0% | 2012-08-07 | 2012-08-22 | Actual Labor Units
EC1650 | Install Backing & Cauld Windows Floor 4 | EC00630.1.3 | 0% | 2012-08-07 | 2012-08-22 | Budgeted Labor Units | 2012-08-01: 86
EC1660 | Stucco Grey | EC00630.1.3 | 0% | 2012-08-22 | 2012-09-24 | Actual Labor Cost
EC1660 | Stucco Grey | EC00630.1.3 | 0% | 2012-08-22 | 2012-09-24 | Budgeted Labor Cost | 2012-08-01: 6720; 2012-09-01: 14016
EC1660 | Stucco Grey | EC00630.1.3 | 0% | 2012-08-22 | 2012-09-24 | Actual Labor Units
EC1660 | Stucco Grey | EC00630.1.3 | 0% | 2012-08-22 | 2012-09-24 | Budgeted Labor Units | 2012-08-01: 56; 2012-09-01: 117
EC1690 | Stucco Finish Coat | EC00630.1.3 | 0% | 2012-09-24 | 2012-10-31 | Actual Labor Cost
EC1690 | Stucco Finish Coat | EC00630.1.3 | 0% | 2012-09-24 | 2012-10-31 | Budgeted Labor Cost | 2012-09-01: 4320; 2012-10-01: 21600
EC1690 | Stucco Finish Coat | EC00630.1.3 | 0% | 2012-09-24 | 2012-10-31 | Actual Labor Units
EC1690 | Stucco Finish Coat | EC00630.1.3 | 0% | 2012-09-24 | 2012-10-31 | Budgeted Labor Units | 2012-09-01: 36; 2012-10-01: 180
EC1840 | Caulk | EC00630.1.3 | 0% | 2012-10-31 | 2012-11-15 | Actual Labor Cost
EC1840 | Caulk | EC00630.1.3 | 0% | 2012-10-31 | 2012-11-15 | Budgeted Labor Cost | 2012-10-01: 480; 2012-11-01: 9888
EC1840 | Caulk | EC00630.1.3 | 0% | 2012-10-31 | 2012-11-15 | Actual Labor Units
EC1840 | Caulk | EC00630.1.3 | 0% | 2012-10-31 | 2012-11-15 | Budgeted Labor Units | 2012-10-01: 4; 2012-11-01: 82
EC1900 | Stucco Band Trim | EC00630.1.3 | 0% | 2012-11-15 | 2012-12-05 | Actual Labor Cost
EC1900 | Stucco Band Trim | EC00630.1.3 | 0% | 2012-11-15 | 2012-12-05 | Budgeted Labor Cost | 2012-11-01: 10272; 2012-12-01: 2688
EC1900 | Stucco Band Trim | EC00630.1.3 | 0% | 2012-11-15 | 2012-12-05 | Actual Labor Units
EC1900 | Stucco Band Trim | EC00630.1.3 | 0% | 2012-11-15 | 2012-12-05 | Budgeted Labor Units | 2012-11-01: 86; 2012-12-01: 22
EC1980 | Paint Exterior | EC00630.1.3 | 0% | 2012-12-12 | 2013-01-03 | Actual Labor Cost
EC1980 | Paint Exterior | EC00630.1.3 | 0% | 2012-12-12 | 2013-01-03 | Budgeted Labor Cost | 2012-12-01: 6832; 2013-01-01: 728
EC1980 | Paint Exterior | EC00630.1.3 | 0% | 2012-12-12 | 2013-01-03 | Actual Labor Units
EC1980 | Paint Exterior | EC00630.1.3 | 0% | 2012-12-12 | 2013-01-03 | Budgeted Labor Units | 2012-12-01: 98; 2013-01-01: 10
EC1990 | Install Railings | EC00630.1.3 | 0% | 2012-12-12 | 2013-02-11 | Actual Labor Cost
EC1990 | Install Railings | EC00630.1.3 | 0% | 2012-12-12 | 2013-02-11 | Budgeted Labor Cost | 2012-12-01: 11712; 2013-01-01: 21120; 2013-02-01: 6048
EC1990 | Install Railings | EC00630.1.3 | 0% | 2012-12-12 | 2013-02-11 | Actual Labor Units
EC1990 | Install Railings | EC00630.1.3 | 0% | 2012-12-12 | 2013-02-11 | Budgeted Labor Units | 2012-12-01: 98; 2013-01-01: 176; 2013-02-01: 50
EC2110 | Demobilize Scaffolding | EC00630.1.3 | 0% | 2013-01-03 | 2013-01-22 | Actual Labor Cost
EC2110 | Demobilize Scaffolding | EC00630.1.3 | 0% | 2013-01-03 | 2013-01-22 | Budgeted Labor Cost | 2013-01-01: 12960
EC2110 | Demobilize Scaffolding | EC00630.1.3 | 0% | 2013-01-03 | 2013-01-22 | Actual Labor Units
EC2110 | Demobilize Scaffolding | EC00630.1.3 | 0% | 2013-01-03 | 2013-01-22 | Budgeted Labor Units | 2013-01-01: 108
EC2140 | Shell Complete | EC00630.1.3 | 0% |  | 2013-02-11 | Actual Labor Cost
EC2140 | Shell Complete | EC00630.1.3 | 0% |  | 2013-02-11 | Budgeted Labor Cost
EC2140 | Shell Complete | EC00630.1.3 | 0% |  | 2013-02-11 | Actual Labor Units
EC2140 | Shell Complete | EC00630.1.3 | 0% |  | 2013-02-11 | Budgeted Labor Units
EC00630.1.4 Interior Finishes |  |  | 0% | 2012-06-08 | 2013-11-11 | Actual Labor Cost
EC00630.1.4 Interior Finishes |  |  | 0% | 2012-06-08 | 2013-11-11 | Budgeted Labor Cost | 2012-06-01: 8519.98; 2012-07-01: 33357.59; 2012-08-01: 59394.82; 2012-09-01: 61059.75; 2012-10-01: 71648.43; 2012-11-01: 62962.43; 2012-12-01: 47489.54; 2013-01-01: 44272.98; 2013-02-01: 40248.16; 2013-03-01: 42260.57; 2013-04-01: 49833.72; 2013-05-01: 45387.03; 2013-06-01: 29675.44; 2013-07-01: 35616.6; 2013-08-01: 23378.21; 2013-09-01: 22622.9; 2013-10-01: 34791.15; 2013-11-01: 9072.06
EC00630.1.4 Interior Finishes |  |  | 0% | 2012-06-08 | 2013-11-11 | Actual Labor Units
EC00630.1.4 Interior Finishes |  |  | 0% | 2012-06-08 | 2013-11-11 | Budgeted Labor Units | 2012-06-01: 145; 2012-07-01: 569; 2012-08-01: 971; 2012-09-01: 939; 2012-10-01: 1104; 2012-11-01: 973; 2012-12-01: 783; 2013-01-01: 770; 2013-02-01: 700; 2013-03-01: 735; 2013-04-01: 866; 2013-05-01: 787; 2013-06-01: 514; 2013-07-01: 632; 2013-08-01: 416; 2013-09-01: 395; 2013-10-01: 608; 2013-11-01: 159
EC1550 | Unit Finishes Building North - Floor 1 | EC00630.1.4 | 0% | 2012-06-08 | 2013-04-23 | Actual Labor Cost
EC1550 | Unit Finishes Building North - Floor 1 | EC00630.1.4 | 0% | 2012-06-08 | 2013-04-23 | Budgeted Labor Cost | 2012-06-01: 4285.81; 2012-07-01: 6000.13; 2012-08-01: 6571.57; 2012-09-01: 5299.62; 2012-10-01: 5864.74; 2012-11-01: 5354.77; 2012-12-01: 5099.78; 2013-01-01: 5609.76; 2013-02-01: 5099.78; 2013-03-01: 5354.77; 2013-04-01: 4181.82
EC1550 | Unit Finishes Building North - Floor 1 | EC00630.1.4 | 0% | 2012-06-08 | 2013-04-23 | Actual Labor Units
EC1550 | Unit Finishes Building North - Floor 1 | EC00630.1.4 | 0% | 2012-06-08 | 2013-04-23 | Budgeted Labor Units | 2012-06-01: 73; 2012-07-01: 102; 2012-08-01: 112; 2012-09-01: 91; 2012-10-01: 102; 2012-11-01: 93; 2012-12-01: 89; 2013-01-01: 98; 2013-02-01: 89; 2013-03-01: 93; 2013-04-01: 73
EC1630 | Unit Finishes Building South - Floor 1 | EC00630.1.4 | 0% | 2012-06-15 | 2013-05-03 | Actual Labor Cost
EC1630 | Unit Finishes Building South - Floor 1 | EC00630.1.4 | 0% | 2012-06-15 | 2013-05-03 | Budgeted Labor Cost | 2012-06-01: 2822.78; 2012-07-01: 5927.84; 2012-08-01: 6492.4; 2012-09-01: 5363.29; 2012-10-01: 5845.7; 2012-11-01: 5290.25; 2012-12-01: 5038.33; 2013-01-01: 5542.17; 2013-02-01: 5038.33; 2013-03-01: 5290.25; 2013-04-01: 5542.17; 2013-05-01: 529.03
EC1630 | Unit Finishes Building South - Floor 1 | EC00630.1.4 | 0% | 2012-06-15 | 2013-05-03 | Actual Labor Units
EC1630 | Unit Finishes Building South - Floor 1 | EC00630.1.4 | 0% | 2012-06-15 | 2013-05-03 | Budgeted Labor Units | 2012-06-01: 48; 2012-07-01: 101; 2012-08-01: 111; 2012-09-01: 91; 2012-10-01: 102; 2012-11-01: 92; 2012-12-01: 88; 2013-01-01: 96; 2013-02-01: 88; 2013-03-01: 92; 2013-04-01: 96; 2013-05-01: 9
EC1670 | Unit Finishes Building North - Floor 2 | EC00630.1.4 | 0% | 2012-06-22 | 2013-05-10 | Actual Labor Cost
EC1670 | Unit Finishes Building North - Floor 2 | EC00630.1.4 | 0% | 2012-06-22 | 2013-05-10 | Budgeted Labor Cost | 2012-06-01: 1411.39; 2012-07-01: 5927.84; 2012-08-01: 6492.4; 2012-09-01: 5363.29; 2012-10-01: 5997.51; 2012-11-01: 5290.25; 2012-12-01: 5038.33; 2013-01-01: 5542.17; 2013-02-01: 5038.33; 2013-03-01: 5290.25; 2013-04-01: 5542.17; 2013-05-01: 1788.61
EC1670 | Unit Finishes Building North - Floor 2 | EC00630.1.4 | 0% | 2012-06-22 | 2013-05-10 | Actual Labor Units
EC1670 | Unit Finishes Building North - Floor 2 | EC00630.1.4 | 0% | 2012-06-22 | 2013-05-10 | Budgeted Labor Units | 2012-06-01: 24; 2012-07-01: 101; 2012-08-01: 111; 2012-09-01: 91; 2012-10-01: 104; 2012-11-01: 92; 2012-12-01: 88; 2013-01-01: 96; 2013-02-01: 88; 2013-03-01: 92; 2013-04-01: 96; 2013-05-01: 31
EC1700 | Unit Finishes Building South - Floor 2 | EC00630.1.4 | 0% | 2012-06-29 | 2013-05-17 | Actual Labor Cost
EC1700 | Unit Finishes Building South - Floor 2 | EC00630.1.4 | 0% | 2012-06-29 | 2013-05-17 | Budgeted Labor Cost | 2012-07-01: 5927.84; 2012-08-01: 6492.4; 2012-09-01: 5363.29; 2012-10-01: 6149.31; 2012-11-01: 5290.25; 2012-12-01: 5038.33; 2013-01-01: 5542.17; 2013-02-01: 5038.33; 2013-03-01: 5290.25; 2013-04-01: 5542.17; 2013-05-01: 3048.19
EC1700 | Unit Finishes Building South - Floor 2 | EC00630.1.4 | 0% | 2012-06-29 | 2013-05-17 | Actual Labor Units
EC1700 | Unit Finishes Building South - Floor 2 | EC00630.1.4 | 0% | 2012-06-29 | 2013-05-17 | Budgeted Labor Units | 2012-07-01: 101; 2012-08-01: 111; 2012-09-01: 91; 2012-10-01: 106; 2012-11-01: 92; 2012-12-01: 88; 2013-01-01: 96; 2013-02-01: 88; 2013-03-01: 92; 2013-04-01: 96; 2013-05-01: 53
EC1790 | Unit Finishes Building North - Floor 3 | EC00630.1.4 | 0% | 2012-07-09 | 2013-05-24 | Actual Labor Cost
EC1790 | Unit Finishes Building North - Floor 3 | EC00630.1.4 | 0% | 2012-07-09 | 2013-05-24 | Budgeted Labor Cost | 2012-07-01: 4516.45; 2012-08-01: 6492.4; 2012-09-01: 5363.29; 2012-10-01: 6301.12; 2012-11-01: 5290.25; 2012-12-01: 5038.33; 2013-01-01: 5542.17; 2013-02-01: 5038.33; 2013-03-01: 5290.25; 2013-04-01: 5542.17; 2013-05-01: 4307.78
EC1790 | Unit Finishes Building North - Floor 3 | EC00630.1.4 | 0% | 2012-07-09 | 2013-05-24 | Actual Labor Units
EC1790 | Unit Finishes Building North - Floor 3 | EC00630.1.4 | 0% | 2012-07-09 | 2013-05-24 | Budgeted Labor Units | 2012-07-01: 77; 2012-08-01: 111; 2012-09-01: 91; 2012-10-01: 108; 2012-11-01: 92; 2012-12-01: 88; 2013-01-01: 96; 2013-02-01: 88; 2013-03-01: 92; 2013-04-01: 96; 2013-05-01: 75
EC1820 | Building 2 Elevators Complete | EC00630.1.4 | 0% | 2012-08-22 | 2012-12-12 | Actual Labor Cost
EC1820 | Building 2 Elevators Complete | EC00630.1.4 | 0% | 2012-08-22 | 2012-12-12 | Budgeted Labor Cost | 2012-08-01: 7531.03; 2012-09-01: 18344.83; 2012-10-01: 22206.9; 2012-11-01: 20275.86; 2012-12-01: 7241.38
EC1820 | Building 2 Elevators Complete | EC00630.1.4 | 0% | 2012-08-22 | 2012-12-12 | Actual Labor Units
EC1820 | Building 2 Elevators Complete | EC00630.1.4 | 0% | 2012-08-22 | 2012-12-12 | Budgeted Labor Units | 2012-08-01: 86; 2012-09-01: 210; 2012-10-01: 254; 2012-11-01: 232; 2012-12-01: 83
EC1850 | Unit Finishes Building South - Floor 3 | EC00630.1.4 | 0% | 2012-07-16 | 2013-06-03 | Actual Labor Cost
EC1850 | Unit Finishes Building South - Floor 3 | EC00630.1.4 | 0% | 2012-07-16 | 2013-06-03 | Budgeted Labor Cost | 2012-07-01: 3105.06; 2012-08-01: 6492.4; 2012-09-01: 5363.29; 2012-10-01: 6452.93; 2012-11-01: 5290.25; 2012-12-01: 5038.33; 2013-01-01: 5542.17; 2013-02-01: 5038.33; 2013-03-01: 5290.25; 2013-04-01: 5542.17; 2013-05-01: 5542.17; 2013-06-01: 25.19
EC1850 | Unit Finishes Building South - Floor 3 | EC00630.1.4 | 0% | 2012-07-16 | 2013-06-03 | Actual Labor Units
EC1850 | Unit Finishes Building South - Floor 3 | EC00630.1.4 | 0% | 2012-07-16 | 2013-06-03 | Budgeted Labor Units | 2012-07-01: 53; 2012-08-01: 111; 2012-09-01: 91; 2012-10-01: 110; 2012-11-01: 92; 2012-12-01: 88; 2013-01-01: 96; 2013-02-01: 88; 2013-03-01: 92; 2013-04-01: 96; 2013-05-01: 96; 2013-06-01: 0
EC1910 | Unit Finishes Building North - Floor 4 | EC00630.1.4 | 0% | 2012-07-23 | 2013-06-12 | Actual Labor Cost
EC1910 | Unit Finishes Building North - Floor 4 | EC00630.1.4 | 0% | 2012-07-23 | 2013-06-12 | Budgeted Labor Cost | 2012-07-01: 1673.51; 2012-08-01: 6415.11; 2012-09-01: 5299.44; 2012-10-01: 6415.11; 2012-11-01: 5365.27; 2012-12-01: 4978.35; 2013-01-01: 5476.19; 2013-02-01: 4978.35; 2013-03-01: 5227.27; 2013-04-01: 5476.19; 2013-05-01: 5476.19; 2013-06-01: 1941.56
EC1910 | Unit Finishes Building North - Floor 4 | EC00630.1.4 | 0% | 2012-07-23 | 2013-06-12 | Actual Labor Units
EC1910 | Unit Finishes Building North - Floor 4 | EC00630.1.4 | 0% | 2012-07-23 | 2013-06-12 | Budgeted Labor Units | 2012-07-01: 29; 2012-08-01: 109; 2012-09-01: 90; 2012-10-01: 109; 2012-11-01: 93; 2012-12-01: 87; 2013-01-01: 95; 2013-02-01: 87; 2013-03-01: 91; 2013-04-01: 95; 2013-05-01: 95; 2013-06-01: 34
EC1950 | Unit Finishes Building South - Floor 4 | EC00630.1.4 | 0% | 2012-07-30 | 2013-06-19 | Actual Labor Cost
EC1950 | Unit Finishes Building South - Floor 4 | EC00630.1.4 | 0% | 2012-07-30 | 2013-06-19 | Budgeted Labor Cost | 2012-07-01: 278.92; 2012-08-01: 6415.11; 2012-09-01: 5299.44; 2012-10-01: 6415.11; 2012-11-01: 5515.27; 2012-12-01: 4978.35; 2013-01-01: 5476.19; 2013-02-01: 4978.35; 2013-03-01: 5227.27; 2013-04-01: 5476.19; 2013-05-01: 5476.19; 2013-06-01: 3186.15
EC1950 | Unit Finishes Building South - Floor 4 | EC00630.1.4 | 0% | 2012-07-30 | 2013-06-19 | Actual Labor Units
EC1950 | Unit Finishes Building South - Floor 4 | EC00630.1.4 | 0% | 2012-07-30 | 2013-06-19 | Budgeted Labor Units | 2012-07-01: 5; 2012-08-01: 109; 2012-09-01: 90; 2012-10-01: 109; 2012-11-01: 95; 2012-12-01: 87; 2013-01-01: 95; 2013-02-01: 87; 2013-03-01: 91; 2013-04-01: 95; 2013-05-01: 95; 2013-06-01: 55
EC2240 | Tenant Finishes for Clubhouse Areas | EC00630.1.4 | 0% | 2013-04-19 | 2013-11-11 | Actual Labor Cost
EC2240 | Tenant Finishes for Clubhouse Areas | EC00630.1.4 | 0% | 2013-04-19 | 2013-11-11 | Budgeted Labor Cost | 2013-04-01: 6988.68; 2013-05-01: 19218.87; 2013-06-01: 17167.92; 2013-07-01: 16313.21; 2013-08-01: 16313.21; 2013-09-01: 14830.19; 2013-10-01: 17054.72; 2013-11-01: 4523.21
EC2240 | Tenant Finishes for Clubhouse Areas | EC00630.1.4 | 0% | 2013-04-19 | 2013-11-11 | Actual Labor Units
EC2240 | Tenant Finishes for Clubhouse Areas | EC00630.1.4 | 0% | 2013-04-19 | 2013-11-11 | Budgeted Labor Units | 2013-04-01: 121; 2013-05-01: 332; 2013-06-01: 298; 2013-07-01: 291; 2013-08-01: 291; 2013-09-01: 264; 2013-10-01: 304; 2013-11-01: 81
EC2370 | Final Inspections and Punchlist | EC00630.1.4 | 0% | 2013-06-19 | 2013-11-11 | Actual Labor Cost
EC2370 | Final Inspections and Punchlist | EC00630.1.4 | 0% | 2013-06-19 | 2013-11-11 | Budgeted Labor Cost | 2013-06-01: 7354.61; 2013-07-01: 19303.39; 2013-08-01: 7065; 2013-09-01: 7792.71; 2013-10-01: 17736.43; 2013-11-01: 4548.86
EC2370 | Final Inspections and Punchlist | EC00630.1.4 | 0% | 2013-06-19 | 2013-11-11 | Actual Labor Units
EC2370 | Final Inspections and Punchlist | EC00630.1.4 | 0% | 2013-06-19 | 2013-11-11 | Budgeted Labor Units | 2013-06-01: 127; 2013-07-01: 341; 2013-08-01: 126; 2013-09-01: 130; 2013-10-01: 304; 2013-11-01: 78
EC00630.1.5 Pool & Courtyard |  |  | 0% | 2013-01-08 | 2013-10-14 | Actual Labor Cost
EC00630.1.5 Pool & Courtyard |  |  | 0% | 2013-01-08 | 2013-10-14 | Budgeted Labor Cost | 2013-01-01: 8570.85; 2013-02-01: 9966.1; 2013-03-01: 10464.41; 2013-04-01: 10962.71; 2013-05-01: 10962.71; 2013-06-01: 9966.1; 2013-07-01: 15078.71; 2013-08-01: 26004.41; 2013-09-01: 16800; 2013-10-01: 8232
EC00630.1.5 Pool & Courtyard |  |  | 0% | 2013-01-08 | 2013-10-14 | Actual Labor Units
EC00630.1.5 Pool & Courtyard |  |  | 0% | 2013-01-08 | 2013-10-14 | Budgeted Labor Units | 2013-01-01: 82; 2013-02-01: 95; 2013-03-01: 100; 2013-04-01: 104; 2013-05-01: 104; 2013-06-01: 95; 2013-07-01: 144; 2013-08-01: 248; 2013-09-01: 160; 2013-10-01: 78
EC2080 | Pool & Deck | EC00630.1.5 | 0% | 2013-01-08 | 2013-08-22 | Actual Labor Cost
EC2080 | Pool & Deck | EC00630.1.5 | 0% | 2013-01-08 | 2013-08-22 | Budgeted Labor Cost | 2013-01-01: 8570.85; 2013-02-01: 9966.1; 2013-03-01: 10464.41; 2013-04-01: 10962.71; 2013-05-01: 10962.71; 2013-06-01: 9966.1; 2013-07-01: 10962.71; 2013-08-01: 7524.41
EC2080 | Pool & Deck | EC00630.1.5 | 0% | 2013-01-08 | 2013-08-22 | Actual Labor Units
EC2080 | Pool & Deck | EC00630.1.5 | 0% | 2013-01-08 | 2013-08-22 | Budgeted Labor Units | 2013-01-01: 82; 2013-02-01: 95; 2013-03-01: 100; 2013-04-01: 104; 2013-05-01: 104; 2013-06-01: 95; 2013-07-01: 104; 2013-08-01: 72
EC2270 | Pergola and Amenities | EC00630.1.5 | 0% | 2013-07-25 | 2013-10-14 | Actual Labor Cost
EC2270 | Pergola and Amenities | EC00630.1.5 | 0% | 2013-07-25 | 2013-10-14 | Budgeted Labor Cost | 2013-07-01: 4116; 2013-08-01: 18480; 2013-09-01: 16800; 2013-10-01: 8232
EC2270 | Pergola and Amenities | EC00630.1.5 | 0% | 2013-07-25 | 2013-10-14 | Actual Labor Units
EC2270 | Pergola and Amenities | EC00630.1.5 | 0% | 2013-07-25 | 2013-10-14 | Budgeted Labor Units | 2013-07-01: 39; 2013-08-01: 176; 2013-09-01: 160; 2013-10-01: 78
EC00630.2 Building 2 |  |  | 0% | 2011-06-29 | 2014-01-21 | Actual Labor Cost
EC00630.2 Building 2 |  |  | 0% | 2011-06-29 | 2014-01-21 | Budgeted Labor Cost | [9 empty] | 4800 | 48000 | 55200 | 28320 | 11760 | 7980 | 5880 | 5880 | 5880 | 7280 | 11795 | 12320 | 112113.6 | 186114 | 176409 | 138886.86 | 171505.06 | 142552.61 | 138135.88 | 143399.44 | 92636.55 | 93429.62 | 162362.63 | 153218.63 | 109202.39 | 94660.21 | 82790.27 | 30619.87 | 33340.32 | 25055.04 | 14238 | 9924.23
EC00630.2 Building 2 |  |  | 0% | 2011-06-29 | 2014-01-21 | Actual Labor Units
EC00630.2 Building 2 |  |  | 0% | 2011-06-29 | 2014-01-21 | Budgeted Labor Units | [9 empty] | 64 | 640 | 736 | 480 | 336 | 228 | 168 | 168 | 168 | 208 | 337 | 352 | 1245 | 1938 | 1869 | 1439 | 1961 | 1990 | 1960 | 2055 | 1421 | 1443 | 2049 | 1973 | 1543 | 1693 | 1538 | 626 | 685 | 525 | 252 | 176
EC2420 | Complete Building 2 | EC00630.2 | 0% |  | 2013-11-26 | Actual Labor Cost
EC2420 | Complete Building 2 | EC00630.2 | 0% |  | 2013-11-26 | Budgeted Labor Cost
EC2420 | Complete Building 2 | EC00630.2 | 0% |  | 2013-11-26 | Actual Labor Units
EC2420 | Complete Building 2 | EC00630.2 | 0% |  | 2013-11-26 | Budgeted Labor Units
EC00630.2.1 Structure |  |  | 0% | 2011-06-29 | 2012-06-14 | Actual Labor Cost
EC00630.2.1 Structure |  |  | 0% | 2011-06-29 | 2012-06-14 | Budgeted Labor Cost | 2011-06-01: 4800; 2011-07-01: 48000; 2011-08-01: 55200; 2011-09-01: 28320; 2011-10-01: 11760; 2011-11-01: 7980; 2011-12-01: 5880; 2012-01-01: 5880; 2012-02-01: 5880; 2012-03-01: 7280; 2012-04-01: 11795; 2012-05-01: 12320; 2012-06-01: 5397
EC00630.2.1 Structure |  |  | 0% | 2011-06-29 | 2012-06-14 | Actual Labor Units
EC00630.2.1 Structure |  |  | 0% | 2011-06-29 | 2012-06-14 | Budgeted Labor Units | 2011-06-01: 64; 2011-07-01: 640; 2011-08-01: 736; 2011-09-01: 480; 2011-10-01: 336; 2011-11-01: 228; 2011-12-01: 168; 2012-01-01: 168; 2012-02-01: 168; 2012-03-01: 208; 2012-04-01: 337; 2012-05-01: 352; 2012-06-01: 154
EC1150 | Building Slab Incl. UG Utils | EC00630.2.1 | 0% | 2011-06-29 | 2011-09-15 | Actual Labor Cost
EC1150 | Building Slab Incl. UG Utils | EC00630.2.1 | 0% | 2011-06-29 | 2011-09-15 | Budgeted Labor Cost | 2011-06-01: 4800; 2011-07-01: 48000; 2011-08-01: 55200; 2011-09-01: 21600
EC1150 | Building Slab Incl. UG Utils | EC00630.2.1 | 0% | 2011-06-29 | 2011-09-15 | Actual Labor Units
EC1150 | Building Slab Incl. UG Utils | EC00630.2.1 | 0% | 2011-06-29 | 2011-09-15 | Budgeted Labor Units | 2011-06-01: 64; 2011-07-01: 640; 2011-08-01: 736; 2011-09-01: 288
EC1220 | First Floor Masonry Structure | EC00630.2.1 | 0% | 2011-09-15 | 2011-10-04 | Actual Labor Cost
EC1220 | First Floor Masonry Structure | EC00630.2.1 | 0% | 2011-09-15 | 2011-10-04 | Budgeted Labor Cost | 2011-09-01: 6720; 2011-10-01: 840
EC1220 | First Floor Masonry Structure | EC00630.2.1 | 0% | 2011-09-15 | 2011-10-04 | Actual Labor Units
EC1220 | First Floor Masonry Structure | EC00630.2.1 | 0% | 2011-09-15 | 2011-10-04 | Budgeted Labor Units | 2011-09-01: 192; 2011-10-01: 24
EC1230 | Second Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-10-04 | 2011-11-10 | Actual Labor Cost
EC1230 | Second Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-10-04 | 2011-11-10 | Budgeted Labor Cost | 2011-10-01: 10920; 2011-11-01: 4200
EC1230 | Second Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-10-04 | 2011-11-10 | Actual Labor Units
EC1230 | Second Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-10-04 | 2011-11-10 | Budgeted Labor Units | 2011-10-01: 312; 2011-11-01: 120
EC1260 | Second Floor Masonry Structure | EC00630.2.1 | 0% | 2011-11-10 | 2011-11-30 | Actual Labor Cost
EC1260 | Second Floor Masonry Structure | EC00630.2.1 | 0% | 2011-11-10 | 2011-11-30 | Budgeted Labor Cost | 2011-11-01: 3780
EC1260 | Second Floor Masonry Structure | EC00630.2.1 | 0% | 2011-11-10 | 2011-11-30 | Actual Labor Units
EC1260 | Second Floor Masonry Structure | EC00630.2.1 | 0% | 2011-11-10 | 2011-11-30 | Budgeted Labor Units | 2011-11-01: 108
EC1290 | Third Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-12-01 | 2012-01-10 | Actual Labor Cost
EC1290 | Third Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-12-01 | 2012-01-10 | Budgeted Labor Cost | 2011-12-01: 5880; 2012-01-01: 1680
EC1290 | Third Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-12-01 | 2012-01-10 | Actual Labor Units
EC1290 | Third Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2011-12-01 | 2012-01-10 | Budgeted Labor Units | 2011-12-01: 168; 2012-01-01: 48
EC1320 | Third Floor Masonry Structure | EC00630.2.1 | 0% | 2012-01-11 | 2012-01-30 | Actual Labor Cost
EC1320 | Third Floor Masonry Structure | EC00630.2.1 | 0% | 2012-01-11 | 2012-01-30 | Budgeted Labor Cost | 2012-01-01: 3780
EC1320 | Third Floor Masonry Structure | EC00630.2.1 | 0% | 2012-01-11 | 2012-01-30 | Actual Labor Units
EC1320 | Third Floor Masonry Structure | EC00630.2.1 | 0% | 2012-01-11 | 2012-01-30 | Budgeted Labor Units | 2012-01-01: 108
EC1330 | Fourth Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2012-01-30 | 2012-03-07 | Actual Labor Cost
EC1330 | Fourth Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2012-01-30 | 2012-03-07 | Budgeted Labor Cost | 2012-01-01: 420; 2012-02-01: 5880; 2012-03-01: 1260
EC1330 | Fourth Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2012-01-30 | 2012-03-07 | Actual Labor Units
EC1330 | Fourth Floor Slab & Collar Beam | EC00630.2.1 | 0% | 2012-01-30 | 2012-03-07 | Budgeted Labor Units | 2012-01-01: 12; 2012-02-01: 168; 2012-03-01: 36
EC1380 | Fourth Floor Masonry Structure | EC00630.2.1 | 0% | 2012-03-07 | 2012-03-26 | Actual Labor Cost
EC1380 | Fourth Floor Masonry Structure | EC00630.2.1 | 0% | 2012-03-07 | 2012-03-26 | Budgeted Labor Cost | 2012-03-01: 3780
EC1380 | Fourth Floor Masonry Structure | EC00630.2.1 | 0% | 2012-03-07 | 2012-03-26 | Actual Labor Units
EC1380 | Fourth Floor Masonry Structure | EC00630.2.1 | 0% | 2012-03-07 | 2012-03-26 | Budgeted Labor Units | 2012-03-01: 108
EC1480 | Roof Slab | EC00630.2.1 | 0% | 2012-03-27 | 2012-04-30 | Actual Labor Cost
EC1480 | Roof Slab | EC00630.2.1 | 0% | 2012-03-27 | 2012-04-30 | Budgeted Labor Cost | 2012-03-01: 2240; 2012-04-01: 11368
EC1480 | Roof Slab | EC00630.2.1 | 0% | 2012-03-27 | 2012-04-30 | Actual Labor Units
EC1480 | Roof Slab | EC00630.2.1 | 0% | 2012-03-27 | 2012-04-30 | Budgeted Labor Units | 2012-03-01: 64; 2012-04-01: 325
EC1620 | Stair and Elevator Masonry Structure | EC00630.2.1 | 0% | 2012-04-30 | 2012-05-07 | Actual Labor Cost
EC1620 | Stair and Elevator Masonry Structure | EC00630.2.1 | 0% | 2012-04-30 | 2012-05-07 | Budgeted Labor Cost | 2012-04-01: 427; 2012-05-01: 2597
EC1620 | Stair and Elevator Masonry Structure | EC00630.2.1 | 0% | 2012-04-30 | 2012-05-07 | Actual Labor Units
EC1620 | Stair and Elevator Masonry Structure | EC00630.2.1 | 0% | 2012-04-30 | 2012-05-07 | Budgeted Labor Units | 2012-04-01: 12; 2012-05-01: 74
EC1640 | Roof Slab/Collar Beam | EC00630.2.1 | 0% | 2012-05-07 | 2012-06-14 | Actual Labor Cost
EC1640 | Roof Slab/Collar Beam | EC00630.2.1 | 0% | 2012-05-07 | 2012-06-14 | Budgeted Labor Cost | 2012-05-01: 9723; 2012-06-01: 5397
EC1640 | Roof Slab/Collar Beam | EC00630.2.1 | 0% | 2012-05-07 | 2012-06-14 | Actual Labor Units
EC1640 | Roof Slab/Collar Beam | EC00630.2.1 | 0% | 2012-05-07 | 2012-06-14 | Budgeted Labor Units | 2012-05-01: 278; 2012-06-01: 154
EC00630.2.2 Roof |  |  | 0% | 2012-06-14 | 2012-10-05 | Actual Labor Cost
EC00630.2.2 Roof |  |  | 0% | 2012-06-14 | 2012-10-05 | Budgeted Labor Cost | 2012-06-01: 47268; 2012-07-01: 77922; 2012-08-01: 55200; 2012-09-01: 34125; 2012-10-01: 4725
EC00630.2.2 Roof |  |  | 0% | 2012-06-14 | 2012-10-05 | Actual Labor Units
EC00630.2.2 Roof |  |  | 0% | 2012-06-14 | 2012-10-05 | Budgeted Labor Units | 2012-06-01: 545; 2012-07-01: 922; 2012-08-01: 736; 2012-09-01: 455; 2012-10-01: 63
EC1710 | Place Roof Trusses and Sheathing | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Actual Labor Cost
EC1710 | Place Roof Trusses and Sheathing | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Budgeted Labor Cost | 2012-06-01: 33633; 2012-07-01: 46287
EC1710 | Place Roof Trusses and Sheathing | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Actual Labor Units
EC1710 | Place Roof Trusses and Sheathing | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Budgeted Labor Units | 2012-06-01: 364; 2012-07-01: 500
EC1720 | Place Mechanical Equipment Supports | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Actual Labor Cost
EC1720 | Place Mechanical Equipment Supports | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Budgeted Labor Cost | 2012-06-01: 13635; 2012-07-01: 18765
EC1720 | Place Mechanical Equipment Supports | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Actual Labor Units
EC1720 | Place Mechanical Equipment Supports | EC00630.2.2 | 0% | 2012-06-14 | 2012-07-24 | Budgeted Labor Units | 2012-06-01: 182; 2012-07-01: 250
EC1860 | Built-Up Asphalt Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-09-17 | Actual Labor Cost
EC1860 | Built-Up Asphalt Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-09-17 | Budgeted Labor Cost | 2012-07-01: 6435; 2012-08-01: 27600; 2012-09-01: 11325
EC1860 | Built-Up Asphalt Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-09-17 | Actual Labor Units
EC1860 | Built-Up Asphalt Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-09-17 | Budgeted Labor Units | 2012-07-01: 86; 2012-08-01: 368; 2012-09-01: 151
EC1870 | Felt and Tile Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-10-05 | Actual Labor Cost
EC1870 | Felt and Tile Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-10-05 | Budgeted Labor Cost | 2012-07-01: 6435; 2012-08-01: 27600; 2012-09-01: 22800; 2012-10-01: 4725
EC1870 | Felt and Tile Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-10-05 | Actual Labor Units
EC1870 | Felt and Tile Roofing | EC00630.2.2 | 0% | 2012-07-24 | 2012-10-05 | Budgeted Labor Units | 2012-07-01: 86; 2012-08-01: 368; 2012-09-01: 304; 2012-10-01: 63
EC2020 | Roof Complete | EC00630.2.2 | 0% |  | 2012-10-05 | Actual Labor Cost
EC2020 | Roof Complete | EC00630.2.2 | 0% |  | 2012-10-05 | Budgeted Labor Cost
EC2020 | Roof Complete | EC00630.2.2 | 0% |  | 2012-10-05 | Actual Labor Units
EC2020 | Roof Complete | EC00630.2.2 | 0% |  | 2012-10-05 | Budgeted Labor Units
EC00630.2.3 Envelope |  |  | 0% | 2012-06-14 | 2013-07-03 | Actual Labor Cost
EC00630.2.3 Envelope |  |  | 0% | 2012-06-14 | 2013-07-03 | Budgeted Labor Cost | 2012-06-01: 59448.6; 2012-07-01: 108192; 2012-08-01: 121209; 2012-09-01: 104199; 2012-10-01: 90882.6; 2012-11-01: 23208; 2012-12-01: 19200; 2013-01-01: 21120; 2013-02-01: 19200; 2013-03-01: 19056; 2013-04-01: 84480; 2013-05-01: 75336; 2013-06-01: 38400; 2013-07-01: 4296
EC00630.2.3 Envelope |  |  | 0% | 2012-06-14 | 2013-07-03 | Actual Labor Units
EC00630.2.3 Envelope |  |  | 0% | 2012-06-14 | 2013-07-03 | Budgeted Labor Units | 2012-06-01: 545; 2012-07-01: 1016; 2012-08-01: 1133; 2012-09-01: 974; 2012-10-01: 816; 2012-11-01: 193; 2012-12-01: 160; 2013-01-01: 176; 2013-02-01: 160; 2013-03-01: 159; 2013-04-01: 704; 2013-05-01: 628; 2013-06-01: 320; 2013-07-01: 36
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-24 | Actual Labor Cost
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-24 | Budgeted Labor Cost | 2012-06-01: 37632.6; 2012-07-01: 51791.4
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-24 | Actual Labor Units
EC1730 | Install Exterior Windows and Sliding Glass Doors Floor 1 | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-24 | Budgeted Labor Units | 2012-06-01: 364; 2012-07-01: 500
EC1740 | Mobilize Scaffolding | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-05 | Actual Labor Cost
EC1740 | Mobilize Scaffolding | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-05 | Budgeted Labor Cost | 2012-06-01: 21816; 2012-07-01: 4104
EC1740 | Mobilize Scaffolding | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-05 | Actual Labor Units
EC1740 | Mobilize Scaffolding | EC00630.2.3 | 0% | 2012-06-14 | 2012-07-05 | Budgeted Labor Units | 2012-06-01: 182; 2012-07-01: 34
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.2.3 | 0% | 2012-07-17 | 2012-08-21 | Actual Labor Cost
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.2.3 | 0% | 2012-07-17 | 2012-08-21 | Budgeted Labor Cost | 2012-07-01: 34320.6; 2012-08-01: 46161
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.2.3 | 0% | 2012-07-17 | 2012-08-21 | Actual Labor Units
EC1800 | Install Exterior Windows and Sliding Glass Doors Floor 2 | EC00630.2.3 | 0% | 2012-07-17 | 2012-08-21 | Budgeted Labor Units | 2012-07-01: 332; 2012-08-01: 446
EC1830 | Install Backing & Cauld Windows Floor1 | EC00630.2.3 | 0% | 2012-07-18 | 2012-08-07 | Actual Labor Cost
EC1830 | Install Backing & Cauld Windows Floor1 | EC00630.2.3 | 0% | 2012-07-18 | 2012-08-07 | Budgeted Labor Cost | 2012-07-01: 17976; 2012-08-01: 7944
EC1830 | Install Backing & Cauld Windows Floor1 | EC00630.2.3 | 0% | 2012-07-18 | 2012-08-07 | Actual Labor Units
EC1830 | Install Backing & Cauld Windows Floor1 | EC00630.2.3 | 0% | 2012-07-18 | 2012-08-07 | Budgeted Labor Units | 2012-07-01: 150; 2012-08-01: 66
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.2.3 | 0% | 2012-08-14 | 2012-09-18 | Actual Labor Cost
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.2.3 | 0% | 2012-08-14 | 2012-09-18 | Budgeted Labor Cost | 2012-08-01: 46368; 2012-09-01: 34113.6
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.2.3 | 0% | 2012-08-14 | 2012-09-18 | Actual Labor Units
EC1880 | Install Exterior Windows and Sliding Glass Doors Floor 3 | EC00630.2.3 | 0% | 2012-08-14 | 2012-09-18 | Budgeted Labor Units | 2012-08-01: 448; 2012-09-01: 330
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00630.2.3 | 0% | 2012-08-15 | 2012-08-29 | Actual Labor Cost
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00630.2.3 | 0% | 2012-08-15 | 2012-08-29 | Budgeted Labor Cost | 2012-08-01: 20736
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00630.2.3 | 0% | 2012-08-15 | 2012-08-29 | Actual Labor Units
EC1890 | Install Backing & Cauld Windows Floor 2 | EC00630.2.3 | 0% | 2012-08-15 | 2012-08-29 | Budgeted Labor Units | 2012-08-01: 173
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.2.3 | 0% | 2012-09-11 | 2012-10-18 | Actual Labor Cost
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.2.3 | 0% | 2012-09-11 | 2012-10-18 | Budgeted Labor Cost | 2012-09-01: 45581.4; 2012-10-01: 43842.6
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.2.3 | 0% | 2012-09-11 | 2012-10-18 | Actual Labor Units
EC1920 | Install Exterior Windows and Sliding Glass Doors Floor 4 | EC00630.2.3 | 0% | 2012-09-11 | 2012-10-18 | Budgeted Labor Units | 2012-09-01: 440; 2012-10-01: 424
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00630.2.3 | 0% | 2012-09-12 | 2012-10-01 | Actual Labor Cost
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00630.2.3 | 0% | 2012-09-12 | 2012-10-01 | Budgeted Labor Cost | 2012-09-01: 24504; 2012-10-01: 1416
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00630.2.3 | 0% | 2012-09-12 | 2012-10-01 | Actual Labor Units
EC1930 | Install Backing & Cauld Windows Floor 3 | EC00630.2.3 | 0% | 2012-09-12 | 2012-10-01 | Budgeted Labor Units | 2012-09-01: 204; 2012-10-01: 12
EC1940 | Stucco Bands | EC00630.2.3 | 0% | 2012-10-17 | 2012-11-06 | Actual Labor Cost
EC1940 | Stucco Bands | EC00630.2.3 | 0% | 2012-10-17 | 2012-11-06 | Budgeted Labor Cost | 2012-10-01: 19704; 2012-11-01: 6216
EC1940 | Stucco Bands | EC00630.2.3 | 0% | 2012-10-17 | 2012-11-06 | Actual Labor Units
EC1940 | Stucco Bands | EC00630.2.3 | 0% | 2012-10-17 | 2012-11-06 | Budgeted Labor Units | 2012-10-01: 164; 2012-11-01: 52
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00630.2.3 | 0% | 2012-10-12 | 2012-10-31 | Actual Labor Cost
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00630.2.3 | 0% | 2012-10-12 | 2012-10-31 | Budgeted Labor Cost | 2012-10-01: 25920
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00630.2.3 | 0% | 2012-10-12 | 2012-10-31 | Actual Labor Units
EC1960 | Install Backing & Cauld Windows Floor 4 | EC00630.2.3 | 0% | 2012-10-12 | 2012-10-31 | Budgeted Labor Units | 2012-10-01: 216
EC1970 | Stucco Grey | EC00630.2.3 | 0% | 2012-11-06 | 2012-12-14 | Actual Labor Cost
EC1970 | Stucco Grey | EC00630.2.3 | 0% | 2012-11-06 | 2012-12-14 | Budgeted Labor Cost | 2012-11-01: 16992; 2012-12-01: 8928
EC1970 | Stucco Grey | EC00630.2.3 | 0% | 2012-11-06 | 2012-12-14 | Actual Labor Units
EC1970 | Stucco Grey | EC00630.2.3 | 0% | 2012-11-06 | 2012-12-14 | Budgeted Labor Units | 2012-11-01: 142; 2012-12-01: 74
EC2050 | Stucco Finish Coat | EC00630.2.3 | 0% | 2012-12-14 | 2013-01-24 | Actual Labor Cost
EC2050 | Stucco Finish Coat | EC00630.2.3 | 0% | 2012-12-14 | 2013-01-24 | Budgeted Labor Cost | 2012-12-01: 10272; 2013-01-01: 15648
EC2050 | Stucco Finish Coat | EC00630.2.3 | 0% | 2012-12-14 | 2013-01-24 | Actual Labor Units
EC2050 | Stucco Finish Coat | EC00630.2.3 | 0% | 2012-12-14 | 2013-01-24 | Budgeted Labor Units | 2012-12-01: 86; 2013-01-01: 130
EC2130 | Caulk | EC00630.2.3 | 0% | 2013-01-24 | 2013-02-12 | Actual Labor Cost
EC2130 | Caulk | EC00630.2.3 | 0% | 2013-01-24 | 2013-02-12 | Budgeted Labor Cost | 2013-01-01: 5472; 2013-02-01: 7488
EC2130 | Caulk | EC00630.2.3 | 0% | 2013-01-24 | 2013-02-12 | Actual Labor Units
EC2130 | Caulk | EC00630.2.3 | 0% | 2013-01-24 | 2013-02-12 | Budgeted Labor Units | 2013-01-01: 46; 2013-02-01: 62
EC2160 | Stucco Band Trim | EC00630.2.3 | 0% | 2013-02-12 | 2013-03-21 | Actual Labor Cost
EC2160 | Stucco Band Trim | EC00630.2.3 | 0% | 2013-02-12 | 2013-03-21 | Budgeted Labor Cost | 2013-02-01: 11712; 2013-03-01: 14208
EC2160 | Stucco Band Trim | EC00630.2.3 | 0% | 2013-02-12 | 2013-03-21 | Actual Labor Units
EC2160 | Stucco Band Trim | EC00630.2.3 | 0% | 2013-02-12 | 2013-03-21 | Budgeted Labor Units | 2013-02-01: 98; 2013-03-01: 118
EC2220 | Paint Exterior | EC00630.2.3 | 0% | 2013-03-28 | 2013-06-13 | Actual Labor Cost
EC2220 | Paint Exterior | EC00630.2.3 | 0% | 2013-03-28 | 2013-06-13 | Budgeted Labor Cost | 2013-03-01: 2424; 2013-04-01: 42240; 2013-05-01: 42240; 2013-06-01: 16776
EC2220 | Paint Exterior | EC00630.2.3 | 0% | 2013-03-28 | 2013-06-13 | Actual Labor Units
EC2220 | Paint Exterior | EC00630.2.3 | 0% | 2013-03-28 | 2013-06-13 | Budgeted Labor Units | 2013-03-01: 20; 2013-04-01: 352; 2013-05-01: 352; 2013-06-01: 140
EC2230 | Install Railings | EC00630.2.3 | 0% | 2013-03-28 | 2013-05-24 | Actual Labor Cost
EC2230 | Install Railings | EC00630.2.3 | 0% | 2013-03-28 | 2013-05-24 | Budgeted Labor Cost | 2013-03-01: 2424; 2013-04-01: 42240; 2013-05-01: 33096
EC2230 | Install Railings | EC00630.2.3 | 0% | 2013-03-28 | 2013-05-24 | Actual Labor Units
EC2230 | Install Railings | EC00630.2.3 | 0% | 2013-03-28 | 2013-05-24 | Budgeted Labor Units | 2013-03-01: 20; 2013-04-01: 352; 2013-05-01: 276
EC2300 | Demobilize Scaffolding | EC00630.2.3 | 0% | 2013-06-13 | 2013-07-03 | Actual Labor Cost
EC2300 | Demobilize Scaffolding | EC00630.2.3 | 0% | 2013-06-13 | 2013-07-03 | Budgeted Labor Cost | 2013-06-01: 21624; 2013-07-01: 4296
EC2300 | Demobilize Scaffolding | EC00630.2.3 | 0% | 2013-06-13 | 2013-07-03 | Actual Labor Units
EC2300 | Demobilize Scaffolding | EC00630.2.3 | 0% | 2013-06-13 | 2013-07-03 | Budgeted Labor Units | 2013-06-01: 180; 2013-07-01: 36
EC2320 | Fountain/Water Feature | EC00630.2.3 | 0% |  | 2013-07-03 | Actual Labor Cost
EC2320 | Fountain/Water Feature | EC00630.2.3 | 0% |  | 2013-07-03 | Budgeted Labor Cost
EC2320 | Fountain/Water Feature | EC00630.2.3 | 0% |  | 2013-07-03 | Actual Labor Units
EC2320 | Fountain/Water Feature | EC00630.2.3 | 0% |  | 2013-07-03 | Budgeted Labor Units
EC00630.2.4 Interior Finishes |  |  | 0% | 2012-09-28 | 2014-01-21 | Actual Labor Cost
EC00630.2.4 Interior Finishes |  |  | 0% | 2012-09-28 | 2014-01-21 | Budgeted Labor Cost | 2012-09-01: 562.86; 2012-10-01: 75897.46; 2012-11-01: 119344.61; 2012-12-01: 118935.88; 2013-01-01: 122279.44; 2013-02-01: 73436.55; 2013-03-01: 74373.62; 2013-04-01: 77882.63; 2013-05-01: 77882.63; 2013-06-01: 70802.39; 2013-07-01: 77882.63; 2013-08-01: 68895.53; 2013-09-01: 17988.29; 2013-10-01: 18814; 2013-11-01: 13789.25; 2013-12-01: 14238; 2014-01-01: 9924.23
EC00630.2.4 Interior Finishes |  |  | 0% | 2012-09-28 | 2014-01-21 | Actual Labor Units
EC00630.2.4 Interior Finishes |  |  | 0% | 2012-09-28 | 2014-01-21 | Budgeted Labor Units | 2012-09-01: 10; 2012-10-01: 1083; 2012-11-01: 1797; 2012-12-01: 1800; 2013-01-01: 1879; 2013-02-01: 1261; 2013-03-01: 1285; 2013-04-01: 1345; 2013-05-01: 1345; 2013-06-01: 1223; 2013-07-01: 1345; 2013-08-01: 1190; 2013-09-01: 310; 2013-10-01: 322; 2013-11-01: 243; 2013-12-01: 252; 2014-01-01: 176
EC2000 | Unit Finishes Building North - Floor 1 | EC00630.2.4 | 0% | 2012-09-28 | 2013-08-19 | Actual Labor Cost
EC2000 | Unit Finishes Building North - Floor 1 | EC00630.2.4 | 0% | 2012-09-28 | 2013-08-19 | Budgeted Labor Cost | 2012-09-01: 562.86; 2012-10-01: 12945.71; 2012-11-01: 11820; 2012-12-01: 11257.14; 2013-01-01: 11622.86; 2013-02-01: 9923.81; 2013-03-01: 10420; 2013-04-01: 10916.19; 2013-05-01: 10916.19; 2013-06-01: 9923.81; 2013-07-01: 10916.19; 2013-08-01: 6351.24
EC2000 | Unit Finishes Building North - Floor 1 | EC00630.2.4 | 0% | 2012-09-28 | 2013-08-19 | Actual Labor Units
EC2000 | Unit Finishes Building North - Floor 1 | EC00630.2.4 | 0% | 2012-09-28 | 2013-08-19 | Budgeted Labor Units | 2012-09-01: 10; 2012-10-01: 219; 2012-11-01: 200; 2012-12-01: 190; 2013-01-01: 199; 2013-02-01: 171; 2013-03-01: 180; 2013-04-01: 189; 2013-05-01: 189; 2013-06-01: 171; 2013-07-01: 189; 2013-08-01: 110
EC2030 | Unit Finishes Building South - Floor 1 | EC00630.2.4 | 0% | 2012-10-05 | 2013-08-26 | Actual Labor Cost
EC2030 | Unit Finishes Building South - Floor 1 | EC00630.2.4 | 0% | 2012-10-05 | 2013-08-26 | Budgeted Labor Cost | 2012-10-01: 10694.29; 2012-11-01: 11820; 2012-12-01: 11257.14; 2013-01-01: 11956.19; 2013-02-01: 9923.81; 2013-03-01: 10420; 2013-04-01: 10916.19; 2013-05-01: 10916.19; 2013-06-01: 9923.81; 2013-07-01: 10916.19; 2013-08-01: 8832.19
EC2030 | Unit Finishes Building South - Floor 1 | EC00630.2.4 | 0% | 2012-10-05 | 2013-08-26 | Actual Labor Units
EC2030 | Unit Finishes Building South - Floor 1 | EC00630.2.4 | 0% | 2012-10-05 | 2013-08-26 | Budgeted Labor Units | 2012-10-01: 181; 2012-11-01: 200; 2012-12-01: 190; 2013-01-01: 203; 2013-02-01: 171; 2013-03-01: 180; 2013-04-01: 189; 2013-05-01: 189; 2013-06-01: 171; 2013-07-01: 189; 2013-08-01: 153
EC2040 | Building 1 Elevators Complete | EC00630.2.4 | 0% | 2012-10-05 | 2013-01-28 | Actual Labor Cost
EC2040 | Building 1 Elevators Complete | EC00630.2.4 | 0% | 2012-10-05 | 2013-01-28 | Budgeted Labor Cost | 2012-10-01: 36689.66; 2012-11-01: 40551.72; 2012-12-01: 38620.69; 2013-01-01: 35337.93
EC2040 | Building 1 Elevators Complete | EC00630.2.4 | 0% | 2012-10-05 | 2013-01-28 | Actual Labor Units
EC2040 | Building 1 Elevators Complete | EC00630.2.4 | 0% | 2012-10-05 | 2013-01-28 | Budgeted Labor Units | 2012-10-01: 419; 2012-11-01: 463; 2012-12-01: 441; 2013-01-01: 404
EC2070 | Unit Finishes Building North - Floor 2 | EC00630.2.4 | 0% | 2012-10-12 | 2013-08-26 | Actual Labor Cost
EC2070 | Unit Finishes Building North - Floor 2 | EC00630.2.4 | 0% | 2012-10-12 | 2013-08-26 | Budgeted Labor Cost | 2012-10-01: 8072.2; 2012-11-01: 12108.29; 2012-12-01: 11531.71; 2013-01-01: 12466.34; 2013-02-01: 10165.85; 2013-03-01: 10674.15; 2013-04-01: 11182.44; 2013-05-01: 11182.44; 2013-06-01: 10165.85; 2013-07-01: 11182.44; 2013-08-01: 8844.29
EC2070 | Unit Finishes Building North - Floor 2 | EC00630.2.4 | 0% | 2012-10-12 | 2013-08-26 | Actual Labor Units
EC2070 | Unit Finishes Building North - Floor 2 | EC00630.2.4 | 0% | 2012-10-12 | 2013-08-26 | Budgeted Labor Units | 2012-10-01: 137; 2012-11-01: 205; 2012-12-01: 195; 2013-01-01: 212; 2013-02-01: 176; 2013-03-01: 184; 2013-04-01: 193; 2013-05-01: 193; 2013-06-01: 176; 2013-07-01: 193; 2013-08-01: 153
EC2120 | Unit Finishes Building South - Floor 2 | EC00630.2.4 | 0% | 2012-10-19 | 2013-09-03 | Actual Labor Cost
EC2120 | Unit Finishes Building South - Floor 2 | EC00630.2.4 | 0% | 2012-10-19 | 2013-09-03 | Budgeted Labor Cost | 2012-10-01: 5189.27; 2012-11-01: 12108.29; 2012-12-01: 11531.71; 2013-01-01: 12684.88; 2013-02-01: 10288.78; 2013-03-01: 10674.15; 2013-04-01: 11182.44; 2013-05-01: 11182.44; 2013-06-01: 10165.85; 2013-07-01: 11182.44; 2013-08-01: 11182.44; 2013-09-01: 203.32
EC2120 | Unit Finishes Building South - Floor 2 | EC00630.2.4 | 0% | 2012-10-19 | 2013-09-03 | Actual Labor Units
EC2120 | Unit Finishes Building South - Floor 2 | EC00630.2.4 | 0% | 2012-10-19 | 2013-09-03 | Budgeted Labor Units | 2012-10-01: 88; 2012-11-01: 205; 2012-12-01: 195; 2013-01-01: 215; 2013-02-01: 177; 2013-03-01: 184; 2013-04-01: 193; 2013-05-01: 193; 2013-06-01: 176; 2013-07-01: 193; 2013-08-01: 193; 2013-09-01: 4
EC2150 | Unit Finishes Building North - Floor 3 | EC00630.2.4 | 0% | 2012-10-26 | 2013-09-10 | Actual Labor Cost
EC2150 | Unit Finishes Building North - Floor 3 | EC00630.2.4 | 0% | 2012-10-26 | 2013-09-10 | Budgeted Labor Cost | 2012-10-01: 2306.34; 2012-11-01: 12108.29; 2012-12-01: 11531.71; 2013-01-01: 12684.88; 2013-02-01: 10630.24; 2013-03-01: 10674.15; 2013-04-01: 11182.44; 2013-05-01: 11182.44; 2013-06-01: 10165.85; 2013-07-01: 11182.44; 2013-08-01: 11182.44; 2013-09-01: 2744.78
EC2150 | Unit Finishes Building North - Floor 3 | EC00630.2.4 | 0% | 2012-10-26 | 2013-09-10 | Actual Labor Units
EC2150 | Unit Finishes Building North - Floor 3 | EC00630.2.4 | 0% | 2012-10-26 | 2013-09-10 | Budgeted Labor Units | 2012-10-01: 39; 2012-11-01: 205; 2012-12-01: 195; 2013-01-01: 215; 2013-02-01: 182; 2013-03-01: 184; 2013-04-01: 193; 2013-05-01: 193; 2013-06-01: 176; 2013-07-01: 193; 2013-08-01: 193; 2013-09-01: 47
EC2170 | Unit Finishes Building South - Floor 3 | EC00630.2.4 | 0% | 2012-11-02 | 2013-09-17 | Actual Labor Cost
EC2170 | Unit Finishes Building South - Floor 3 | EC00630.2.4 | 0% | 2012-11-02 | 2013-09-17 | Budgeted Labor Cost | 2012-11-01: 11531.71; 2012-12-01: 11531.71; 2013-01-01: 12684.88; 2013-02-01: 10971.71; 2013-03-01: 10674.15; 2013-04-01: 11182.44; 2013-05-01: 11182.44; 2013-06-01: 10165.85; 2013-07-01: 11182.44; 2013-08-01: 11182.44; 2013-09-01: 5286.24
EC2170 | Unit Finishes Building South - Floor 3 | EC00630.2.4 | 0% | 2012-11-02 | 2013-09-17 | Actual Labor Units
EC2170 | Unit Finishes Building South - Floor 3 | EC00630.2.4 | 0% | 2012-11-02 | 2013-09-17 | Budgeted Labor Units | 2012-11-01: 195; 2012-12-01: 195; 2013-01-01: 215; 2013-02-01: 187; 2013-03-01: 184; 2013-04-01: 193; 2013-05-01: 193; 2013-06-01: 176; 2013-07-01: 193; 2013-08-01: 193; 2013-09-01: 91
EC2200 | Unit Finishes Building North - Floor 4 | EC00630.2.4 | 0% | 2012-11-09 | 2013-09-19 | Actual Labor Cost
EC2200 | Unit Finishes Building North - Floor 4 | EC00630.2.4 | 0% | 2012-11-09 | 2013-09-19 | Budgeted Labor Cost | 2012-11-01: 4377.78; 2012-12-01: 5837.04; 2013-01-01: 6420.74; 2013-02-01: 5695.31; 2013-03-01: 5402.96; 2013-04-01: 5660.25; 2013-05-01: 5660.25; 2013-06-01: 5145.68; 2013-07-01: 5660.25; 2013-08-01: 5660.25; 2013-09-01: 3267.5
EC2200 | Unit Finishes Building North - Floor 4 | EC00630.2.4 | 0% | 2012-11-09 | 2013-09-19 | Actual Labor Units
EC2200 | Unit Finishes Building North - Floor 4 | EC00630.2.4 | 0% | 2012-11-09 | 2013-09-19 | Budgeted Labor Units | 2012-11-01: 74; 2012-12-01: 99; 2013-01-01: 109; 2013-02-01: 97; 2013-03-01: 93; 2013-04-01: 98; 2013-05-01: 98; 2013-06-01: 89; 2013-07-01: 98; 2013-08-01: 98; 2013-09-01: 56
EC2210 | Unit Finishes Building South - Floor 4 | EC00630.2.4 | 0% | 2012-11-16 | 2013-09-26 | Actual Labor Cost
EC2210 | Unit Finishes Building South - Floor 4 | EC00630.2.4 | 0% | 2012-11-16 | 2013-09-26 | Budgeted Labor Cost | 2012-11-01: 2918.52; 2012-12-01: 5837.04; 2013-01-01: 6420.74; 2013-02-01: 5837.04; 2013-03-01: 5434.07; 2013-04-01: 5660.25; 2013-05-01: 5660.25; 2013-06-01: 5145.68; 2013-07-01: 5660.25; 2013-08-01: 5660.25; 2013-09-01: 4553.92
EC2210 | Unit Finishes Building South - Floor 4 | EC00630.2.4 | 0% | 2012-11-16 | 2013-09-26 | Actual Labor Units
EC2210 | Unit Finishes Building South - Floor 4 | EC00630.2.4 | 0% | 2012-11-16 | 2013-09-26 | Budgeted Labor Units | 2012-11-01: 49; 2012-12-01: 99; 2013-01-01: 109; 2013-02-01: 99; 2013-03-01: 94; 2013-04-01: 98; 2013-05-01: 98; 2013-06-01: 89; 2013-07-01: 98; 2013-08-01: 98; 2013-09-01: 79
EC2410 | Final Inspections and Punchlist | EC00630.2.4 | 0% | 2013-09-26 | 2014-01-21 | Actual Labor Cost
EC2410 | Final Inspections and Punchlist | EC00630.2.4 | 0% | 2013-09-26 | 2014-01-21 | Budgeted Labor Cost | 2013-09-01: 1932.53; 2013-10-01: 18814; 2013-11-01: 13789.25; 2013-12-01: 14238; 2014-01-01: 9924.23
EC2410 | Final Inspections and Punchlist | EC00630.2.4 | 0% | 2013-09-26 | 2014-01-21 | Actual Labor Units
EC2410 | Final Inspections and Punchlist | EC00630.2.4 | 0% | 2013-09-26 | 2014-01-21 | Budgeted Labor Units | 2013-09-01: 33; 2013-10-01: 322; 2013-11-01: 243; 2013-12-01: 252; 2014-01-01: 176
EC00630.2.5 Courtyard |  |  | 0% | 2013-07-03 | 2013-11-27 | Actual Labor Cost
EC00630.2.5 Courtyard |  |  | 0% | 2013-07-03 | 2013-11-27 | Budgeted Labor Cost | 2013-07-01: 12481.58; 2013-08-01: 13894.74; 2013-09-01: 12631.58; 2013-10-01: 14526.32; 2013-11-01: 11265.79
EC00630.2.5 Courtyard |  |  | 0% | 2013-07-03 | 2013-11-27 | Actual Labor Units
EC00630.2.5 Courtyard |  |  | 0% | 2013-07-03 | 2013-11-27 | Budgeted Labor Units | 2013-07-01: 312; 2013-08-01: 347; 2013-09-01: 316; 2013-10-01: 363; 2013-11-01: 282
EC2330 | Courtyard Walks and Amenities | EC00630.2.5 | 0% | 2013-07-03 | 2013-11-27 | Actual Labor Cost
EC2330 | Courtyard Walks and Amenities | EC00630.2.5 | 0% | 2013-07-03 | 2013-11-27 | Budgeted Labor Cost | 2013-07-01: 12481.58; 2013-08-01: 13894.74; 2013-09-01: 12631.58; 2013-10-01: 14526.32; 2013-11-01: 11265.79
EC2330 | Courtyard Walks and Amenities | EC00630.2.5 | 0% | 2013-07-03 | 2013-11-27 | Actual Labor Units
EC2330 | Courtyard Walks and Amenities | EC00630.2.5 | 0% | 2013-07-03 | 2013-11-27 | Budgeted Labor Units | 2013-07-01: 312; 2013-08-01: 347; 2013-09-01: 316; 2013-10-01: 363; 2013-11-01: 282
EC00630.5 Garage 1 |  |  | 0% | 2012-02-24 | 2013-10-29 | Actual Labor Cost
EC00630.5 Garage 1 |  |  | 0% | 2012-02-24 | 2013-10-29 | Budgeted Labor Cost | 2012-02-01: 2885.42; 2012-03-01: 19091.53; 2012-04-01: 18223.73; 2012-05-01: 19091.53; 2012-06-01: 17735.59; 2012-07-01: 20501.69; 2012-08-01: 22454.24; 2012-09-01: 18549.15; 2012-10-01: 21710.15; 2012-11-01: 20703.53; 2012-12-01: 19717.65; 2013-01-01: 21689.41; 2013-02-01: 19717.65; 2013-03-01: 19811.77; 2013-04-01: 24200; 2013-05-01: 24200; 2013-06-01: 42800; 2013-07-01: 42900; 2013-08-01: 35200; 2013-09-01: 32000; 2013-10-01: 36640
EC00630.5 Garage 1 |  |  | 0% | 2012-02-24 | 2013-10-29 | Actual Labor Units
EC00630.5 Garage 1 |  |  | 0% | 2012-02-24 | 2013-10-29 | Budgeted Labor Units | 2012-02-01: 40; 2012-03-01: 286; 2012-04-01: 273; 2012-05-01: 286; 2012-06-01: 265; 2012-07-01: 273; 2012-08-01: 299; 2012-09-01: 247; 2012-10-01: 279; 2012-11-01: 256; 2012-12-01: 244; 2013-01-01: 268; 2013-02-01: 244; 2013-03-01: 247; 2013-04-01: 293; 2013-05-01: 293; 2013-06-01: 544; 2013-07-01: 563; 2013-08-01: 469; 2013-09-01: 427; 2013-10-01: 517
EC1420 | Start Garage | EC00630.5 | 0% | 2012-03-06 |  | Actual Labor Cost
EC1420 | Start Garage | EC00630.5 | 0% | 2012-03-06 |  | Budgeted Labor Cost
EC1420 | Start Garage | EC00630.5 | 0% | 2012-03-06 |  | Actual Labor Units
EC1420 | Start Garage | EC00630.5 | 0% | 2012-03-06 |  | Budgeted Labor Units
EC1430 | Shop Drawings, Review & Approval | EC00630.5 | 0% | 2012-02-24 | 2012-06-21 | Actual Labor Cost
EC1430 | Shop Drawings, Review & Approval | EC00630.5 | 0% | 2012-02-24 | 2012-06-21 | Budgeted Labor Cost | 2012-02-01: 2885.42; 2012-03-01: 19091.53; 2012-04-01: 18223.73; 2012-05-01: 19091.53; 2012-06-01: 9827.8
EC1430 | Shop Drawings, Review & Approval | EC00630.5 | 0% | 2012-02-24 | 2012-06-21 | Actual Labor Units
EC1430 | Shop Drawings, Review & Approval | EC00630.5 | 0% | 2012-02-24 | 2012-06-21 | Budgeted Labor Units | 2012-02-01: 40; 2012-03-01: 286; 2012-04-01: 273; 2012-05-01: 286; 2012-06-01: 156
EC1810 | Fab & Delivery | EC00630.5 | 0% | 2012-06-19 | 2012-10-12 | Actual Labor Cost
EC1810 | Fab & Delivery | EC00630.5 | 0% | 2012-06-19 | 2012-10-12 | Budgeted Labor Cost | 2012-06-01: 7907.8; 2012-07-01: 20501.69; 2012-08-01: 22454.24; 2012-09-01: 18549.15; 2012-10-01: 7907.8
EC1810 | Fab & Delivery | EC00630.5 | 0% | 2012-06-19 | 2012-10-12 | Actual Labor Units
EC1810 | Fab & Delivery | EC00630.5 | 0% | 2012-06-19 | 2012-10-12 | Budgeted Labor Units | 2012-06-01: 108; 2012-07-01: 273; 2012-08-01: 299; 2012-09-01: 247; 2012-10-01: 108
EC2090 | Erect Precast Structure | EC00630.5 | 0% | 2012-10-12 | 2013-03-18 | Actual Labor Cost
EC2090 | Erect Precast Structure | EC00630.5 | 0% | 2012-10-12 | 2013-03-18 | Budgeted Labor Cost | 2012-10-01: 13802.35; 2012-11-01: 20703.53; 2012-12-01: 19717.65; 2013-01-01: 21689.41; 2013-02-01: 19717.65; 2013-03-01: 8811.77
EC2090 | Erect Precast Structure | EC00630.5 | 0% | 2012-10-12 | 2013-03-18 | Actual Labor Units
EC2090 | Erect Precast Structure | EC00630.5 | 0% | 2012-10-12 | 2013-03-18 | Budgeted Labor Units | 2012-10-01: 171; 2012-11-01: 256; 2012-12-01: 244; 2013-01-01: 268; 2013-02-01: 244; 2013-03-01: 114
EC2280 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-03-18 | 2013-07-11 | Actual Labor Cost
EC2280 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-03-18 | 2013-07-11 | Budgeted Labor Cost | 2013-03-01: 11000; 2013-04-01: 24200; 2013-05-01: 24200; 2013-06-01: 22000; 2013-07-01: 7700
EC2280 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-03-18 | 2013-07-11 | Actual Labor Units
EC2280 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-03-18 | 2013-07-11 | Budgeted Labor Units | 2013-03-01: 133; 2013-04-01: 293; 2013-05-01: 293; 2013-06-01: 267; 2013-07-01: 93
EC2310 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-06-12 | 2013-10-07 | Actual Labor Cost
EC2310 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-06-12 | 2013-10-07 | Budgeted Labor Cost | 2013-06-01: 20800; 2013-07-01: 35200; 2013-08-01: 35200; 2013-09-01: 32000; 2013-10-01: 6400
EC2310 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-06-12 | 2013-10-07 | Actual Labor Units
EC2310 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-06-12 | 2013-10-07 | Budgeted Labor Units | 2013-06-01: 277; 2013-07-01: 469; 2013-08-01: 469; 2013-09-01: 427; 2013-10-01: 85
EC2380 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-10-07 | 2013-10-29 | Actual Labor Cost
EC2380 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-10-07 | 2013-10-29 | Budgeted Labor Cost | 2013-10-01: 30240
EC2380 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-10-07 | 2013-10-29 | Actual Labor Units
EC2380 | Entry Feature/Sign Wall | EC00630.5 | 0% | 2013-10-07 | 2013-10-29 | Budgeted Labor Units | 2013-10-01: 432
EC2390 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Actual Labor Cost
EC2390 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Budgeted Labor Cost
EC2390 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Actual Labor Units
EC2390 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Budgeted Labor Units
EC2400 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Actual Labor Cost
EC2400 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Budgeted Labor Cost
EC2400 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Actual Labor Units
EC2400 | Entry Feature/Sign Wall | EC00630.5 | 0% |  | 2013-10-29 | Budgeted Labor Units
EC00630.6 Garage 2 |  |  | 0% | 2011-06-01 | 2013-04-17 | Actual Labor Cost
EC00630.6 Garage 2 |  |  | 0% | 2011-06-01 | 2013-04-17 | Budgeted Labor Cost | 2011-06-01: 28637.29; 2011-07-01: 26033.9; 2011-08-01: 29938.98; 2011-09-01: 25504.07; 2011-10-01: 20160; 2011-11-01: 20160; 2011-12-01: 20160; 2012-01-01: 17756.1; 2012-02-01: 16363.64; 2012-03-01: 17142.86; 2012-04-01: 16363.64; 2012-05-01: 17142.86; 2012-06-01: 14319.2; 2012-07-01: 23692.31; 2012-08-01: 25948.72; 2012-09-01: 36950.18; 2012-10-01: 39544.14; 2012-11-01: 28800; 2012-12-01: 27428.57; 2013-01-01: 27374.29; 2013-02-01: 10000; 2013-03-01: 10500; 2013-04-01: 5440
EC00630.6 Garage 2 |  |  | 0% | 2011-06-01 | 2013-04-17 | Actual Labor Units
EC00630.6 Garage 2 |  |  | 0% | 2011-06-01 | 2013-04-17 | Budgeted Labor Units | 2011-06-01: 382; 2011-07-01: 347; 2011-08-01: 399; 2011-09-01: 345; 2011-10-01: 269; 2011-11-01: 269; 2011-12-01: 269; 2012-01-01: 231; 2012-02-01: 196; 2012-03-01: 206; 2012-04-01: 196; 2012-05-01: 206; 2012-06-01: 183; 2012-07-01: 287; 2012-08-01: 315; 2012-09-01: 463; 2012-10-01: 519; 2012-11-01: 384; 2012-12-01: 366; 2013-01-01: 369; 2013-02-01: 120; 2013-03-01: 126; 2013-04-01: 64
EC1020 | Start Garage | EC00630.6 | 0% | 2011-06-01 |  | Actual Labor Cost
EC1020 | Start Garage | EC00630.6 | 0% | 2011-06-01 |  | Budgeted Labor Cost
EC1020 | Start Garage | EC00630.6 | 0% | 2011-06-01 |  | Actual Labor Units
EC1020 | Start Garage | EC00630.6 | 0% | 2011-06-01 |  | Budgeted Labor Units
EC1030 | Shop Drawings, Review and Approval | EC00630.6 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Cost
EC1030 | Shop Drawings, Review and Approval | EC00630.6 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Cost | 2011-06-01: 28637.29; 2011-07-01: 26033.9; 2011-08-01: 29938.98; 2011-09-01: 18484.07
EC1030 | Shop Drawings, Review and Approval | EC00630.6 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Units
EC1030 | Shop Drawings, Review and Approval | EC00630.6 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Units | 2011-06-01: 382; 2011-07-01: 347; 2011-08-01: 399; 2011-09-01: 254
EC1180 | Fab & Delivery | EC00630.6 | 0% | 2011-09-21 | 2012-01-20 | Actual Labor Cost
EC1180 | Fab & Delivery | EC00630.6 | 0% | 2011-09-21 | 2012-01-20 | Budgeted Labor Cost | 2011-09-01: 7020; 2011-10-01: 20160; 2011-11-01: 20160; 2011-12-01: 20160; 2012-01-01: 10260
EC1180 | Fab & Delivery | EC00630.6 | 0% | 2011-09-21 | 2012-01-20 | Actual Labor Units
EC1180 | Fab & Delivery | EC00630.6 | 0% | 2011-09-21 | 2012-01-20 | Budgeted Labor Units | 2011-09-01: 91; 2011-10-01: 269; 2011-11-01: 269; 2011-12-01: 269; 2012-01-01: 140
EC1280 | Erect Precast Structure | EC00630.6 | 0% | 2012-01-17 | 2012-06-18 | Actual Labor Cost
EC1280 | Erect Precast Structure | EC00630.6 | 0% | 2012-01-17 | 2012-06-18 | Budgeted Labor Cost | 2012-01-01: 7496.1; 2012-02-01: 16363.64; 2012-03-01: 17142.86; 2012-04-01: 16363.64; 2012-05-01: 17142.86; 2012-06-01: 4597.4
EC1280 | Erect Precast Structure | EC00630.6 | 0% | 2012-01-17 | 2012-06-18 | Actual Labor Units
EC1280 | Erect Precast Structure | EC00630.6 | 0% | 2012-01-17 | 2012-06-18 | Budgeted Labor Units | 2012-01-01: 92; 2012-02-01: 196; 2012-03-01: 206; 2012-04-01: 196; 2012-05-01: 206; 2012-06-01: 64
EC1590 | Fire Protection and Lighting | EC00630.6 | 0% | 2012-06-18 | 2012-10-11 | Actual Labor Cost
EC1590 | Fire Protection and Lighting | EC00630.6 | 0% | 2012-06-18 | 2012-10-11 | Budgeted Labor Cost | 2012-06-01: 9721.8; 2012-07-01: 23692.31; 2012-08-01: 25948.72; 2012-09-01: 21435.9; 2012-10-01: 8001.28
EC1590 | Fire Protection and Lighting | EC00630.6 | 0% | 2012-06-18 | 2012-10-11 | Actual Labor Units
EC1590 | Fire Protection and Lighting | EC00630.6 | 0% | 2012-06-18 | 2012-10-11 | Budgeted Labor Units | 2012-06-01: 120; 2012-07-01: 287; 2012-08-01: 315; 2012-09-01: 260; 2012-10-01: 99
EC1680 | Finishes and Striping | EC00630.6 | 0% | 2012-09-13 | 2013-01-31 | Actual Labor Cost
EC1680 | Finishes and Striping | EC00630.6 | 0% | 2012-09-13 | 2013-01-31 | Budgeted Labor Cost | 2012-09-01: 15514.29; 2012-10-01: 31542.86; 2012-11-01: 28800; 2012-12-01: 27428.57; 2013-01-01: 26314.29
EC1680 | Finishes and Striping | EC00630.6 | 0% | 2012-09-13 | 2013-01-31 | Actual Labor Units
EC1680 | Finishes and Striping | EC00630.6 | 0% | 2012-09-13 | 2013-01-31 | Budgeted Labor Units | 2012-09-01: 203; 2012-10-01: 421; 2012-11-01: 384; 2012-12-01: 366; 2013-01-01: 355
EC2060 | Punch List Garage | EC00630.6 | 0% | 2013-01-28 | 2013-04-17 | Actual Labor Cost
EC2060 | Punch List Garage | EC00630.6 | 0% | 2013-01-28 | 2013-04-17 | Budgeted Labor Cost | 2013-01-01: 1060; 2013-02-01: 10000; 2013-03-01: 10500; 2013-04-01: 5440
EC2060 | Punch List Garage | EC00630.6 | 0% | 2013-01-28 | 2013-04-17 | Actual Labor Units
EC2060 | Punch List Garage | EC00630.6 | 0% | 2013-01-28 | 2013-04-17 | Budgeted Labor Units | 2013-01-01: 14; 2013-02-01: 120; 2013-03-01: 126; 2013-04-01: 64
EC2180 | Complete Garage 2 | EC00630.6 | 0% |  | 2013-04-12 | Actual Labor Cost
EC2180 | Complete Garage 2 | EC00630.6 | 0% |  | 2013-04-12 | Budgeted Labor Cost
EC2180 | Complete Garage 2 | EC00630.6 | 0% |  | 2013-04-12 | Actual Labor Units
EC2180 | Complete Garage 2 | EC00630.6 | 0% |  | 2013-04-12 | Budgeted Labor Units
EC2190 | Complete Garage | EC00630.6 | 0% |  | 2013-04-12 | Actual Labor Cost
EC2190 | Complete Garage | EC00630.6 | 0% |  | 2013-04-12 | Budgeted Labor Cost
EC2190 | Complete Garage | EC00630.6 | 0% |  | 2013-04-12 | Actual Labor Units
EC2190 | Complete Garage | EC00630.6 | 0% |  | 2013-04-12 | Budgeted Labor Units
EC00630.7 Roads, Utilities & Pavers |  |  | 0% | 2011-06-01 | 2013-11-07 | Actual Labor Cost
EC00630.7 Roads, Utilities & Pavers |  |  | 0% | 2011-06-01 | 2013-11-07 | Budgeted Labor Cost | 2011-06-01: 177800; 2011-07-01: 148800; 2011-08-01: 171120; 2011-09-01: 118106.29; 2011-10-01: 10560; 2011-11-01: 10560; 2011-12-01: 10560; 2012-01-01: 15261.71; 2012-02-01: 21840; 2012-03-01: 22880; 2012-04-01: 2288; 2012-05-01: 32091; 2012-06-01: 69497; 2012-07-01: 107520; 2012-08-01: 117760; 2012-09-01: 76899; 2012-10-01: 5985; 2013-03-01: 52960; 2013-04-01: 101728; 2013-05-01: 101728; 2013-06-01: 92480; 2013-07-01: 111634; 2013-08-01: 100086.4; 2013-09-01: 54368; 2013-10-01: 47840; 2013-11-01: 9022
EC00630.7 Roads, Utilities & Pavers |  |  | 0% | 2011-06-01 | 2013-11-07 | Actual Labor Units
EC00630.7 Roads, Utilities & Pavers |  |  | 0% | 2011-06-01 | 2013-11-07 | Budgeted Labor Units | 2011-06-01: 1816; 2011-07-01: 1600; 2011-08-01: 1840; 2011-09-01: 1316; 2011-10-01: 264; 2011-11-01: 264; 2011-12-01: 264; 2012-01-01: 223; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 18; 2012-05-01: 338; 2012-06-01: 674; 2012-07-01: 1008; 2012-08-01: 1104; 2012-09-01: 744; 2012-10-01: 63; 2013-03-01: 544; 2013-04-01: 1056; 2013-05-01: 1056; 2013-06-01: 960; 2013-07-01: 1132; 2013-08-01: 1026; 2013-09-01: 442; 2013-10-01: 368; 2013-11-01: 69
EC1000 | Curbs & Paving | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Cost
EC1000 | Curbs & Paving | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Cost | 2011-06-01: 45760; 2011-07-01: 41600; 2011-08-01: 47840; 2011-09-01: 33280
EC1000 | Curbs & Paving | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Units
EC1000 | Curbs & Paving | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Units | 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 368; 2011-09-01: 256
EC1040 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Cost
EC1040 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Cost | 2011-06-01: 33440; 2011-07-01: 30400; 2011-08-01: 34960; 2011-09-01: 24320
EC1040 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Units
EC1040 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Units | 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 368; 2011-09-01: 256
EC1050 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-21 | Actual Labor Cost
EC1050 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-21 | Budgeted Labor Cost | 2011-06-01: 33440; 2011-07-01: 30400; 2011-08-01: 34960; 2011-09-01: 20216
EC1050 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-21 | Actual Labor Units
EC1050 | Site Cleanup | EC00630.7 | 0% | 2011-06-01 | 2011-09-21 | Budgeted Labor Units | 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 368; 2011-09-01: 213
EC1100 | Storm Drainage Site Work | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Cost
EC1100 | Storm Drainage Site Work | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Cost | 2011-06-01: 36960; 2011-07-01: 33600; 2011-08-01: 38640; 2011-09-01: 26880
EC1100 | Storm Drainage Site Work | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Actual Labor Units
EC1100 | Storm Drainage Site Work | EC00630.7 | 0% | 2011-06-01 | 2011-09-26 | Budgeted Labor Units | 2011-06-01: 352; 2011-07-01: 320; 2011-08-01: 368; 2011-09-01: 256
EC1110 | Site Electrical Work & Temp Power | EC00630.7 | 0% | 2011-06-01 | 2011-06-20 | Actual Labor Cost
EC1110 | Site Electrical Work & Temp Power | EC00630.7 | 0% | 2011-06-01 | 2011-06-20 | Budgeted Labor Cost | 2011-06-01: 20520
EC1110 | Site Electrical Work & Temp Power | EC00630.7 | 0% | 2011-06-01 | 2011-06-20 | Actual Labor Units
EC1110 | Site Electrical Work & Temp Power | EC00630.7 | 0% | 2011-06-01 | 2011-06-20 | Budgeted Labor Units | 2011-06-01: 216
EC1130 | Curbs & Paving | EC00630.7 | 0% | 2011-06-15 | 2011-09-30 | Actual Labor Cost
EC1130 | Curbs & Paving | EC00630.7 | 0% | 2011-06-15 | 2011-09-30 | Budgeted Labor Cost | 2011-06-01: 7680; 2011-07-01: 12800; 2011-08-01: 14720; 2011-09-01: 13184
EC1130 | Curbs & Paving | EC00630.7 | 0% | 2011-06-15 | 2011-09-30 | Actual Labor Units
EC1130 | Curbs & Paving | EC00630.7 | 0% | 2011-06-15 | 2011-09-30 | Budgeted Labor Units | 2011-06-01: 192; 2011-07-01: 320; 2011-08-01: 368; 2011-09-01: 330
EC1200 | Curbs & Paving | EC00630.7 | 0% | 2011-09-30 | 2012-01-19 | Actual Labor Cost
EC1200 | Curbs & Paving | EC00630.7 | 0% | 2011-09-30 | 2012-01-19 | Budgeted Labor Cost | 2011-09-01: 226.29; 2011-10-01: 10560; 2011-11-01: 10560; 2011-12-01: 10560; 2012-01-01: 6109.71
EC1200 | Curbs & Paving | EC00630.7 | 0% | 2011-09-30 | 2012-01-19 | Actual Labor Units
EC1200 | Curbs & Paving | EC00630.7 | 0% | 2011-09-30 | 2012-01-19 | Budgeted Labor Units | 2011-09-01: 6; 2011-10-01: 264; 2011-11-01: 264; 2011-12-01: 264; 2012-01-01: 153
EC1270 | Curbs & Paving | EC00630.7 | 0% | 2012-01-19 | 2012-04-04 | Actual Labor Cost
EC1270 | Curbs & Paving | EC00630.7 | 0% | 2012-01-19 | 2012-04-04 | Budgeted Labor Cost | 2012-01-01: 9152; 2012-02-01: 21840; 2012-03-01: 22880; 2012-04-01: 2288
EC1270 | Curbs & Paving | EC00630.7 | 0% | 2012-01-19 | 2012-04-04 | Actual Labor Units
EC1270 | Curbs & Paving | EC00630.7 | 0% | 2012-01-19 | 2012-04-04 | Budgeted Labor Units | 2012-01-01: 70; 2012-02-01: 168; 2012-03-01: 176; 2012-04-01: 18
EC1440 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-05-01 | 2012-09-26 | Actual Labor Cost
EC1440 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-05-01 | 2012-09-26 | Budgeted Labor Cost | 2012-05-01: 32091; 2012-06-01: 31920; 2012-07-01: 31920; 2012-08-01: 34960; 2012-09-01: 25061
EC1440 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-05-01 | 2012-09-26 | Actual Labor Units
EC1440 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-05-01 | 2012-09-26 | Budgeted Labor Units | 2012-05-01: 338; 2012-06-01: 336; 2012-07-01: 336; 2012-08-01: 368; 2012-09-01: 264
EC1610 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-06-18 | 2012-09-19 | Actual Labor Cost
EC1610 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-06-18 | 2012-09-19 | Budgeted Labor Cost | 2012-06-01: 20306; 2012-07-01: 43680; 2012-08-01: 47840; 2012-09-01: 22958
EC1610 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-06-18 | 2012-09-19 | Actual Labor Units
EC1610 | Electric to Building 2 Power Vault | EC00630.7 | 0% | 2012-06-18 | 2012-09-19 | Budgeted Labor Units | 2012-06-01: 156; 2012-07-01: 336; 2012-08-01: 368; 2012-09-01: 177
EC1750 | Electric to Building 1 Power Vault | EC00630.7 | 0% | 2012-06-14 | 2012-10-05 | Actual Labor Cost
EC1750 | Electric to Building 1 Power Vault | EC00630.7 | 0% | 2012-06-14 | 2012-10-05 | Budgeted Labor Cost | 2012-06-01: 17271; 2012-07-01: 31920; 2012-08-01: 34960; 2012-09-01: 28880; 2012-10-01: 5985
EC1750 | Electric to Building 1 Power Vault | EC00630.7 | 0% | 2012-06-14 | 2012-10-05 | Actual Labor Units
EC1750 | Electric to Building 1 Power Vault | EC00630.7 | 0% | 2012-06-14 | 2012-10-05 | Budgeted Labor Units | 2012-06-01: 182; 2012-07-01: 336; 2012-08-01: 368; 2012-09-01: 304; 2012-10-01: 63
EC2250 | Fountain/Water Feature | EC00630.7 | 0% | 2013-03-12 | 2013-09-12 | Actual Labor Cost
EC2250 | Fountain/Water Feature | EC00630.7 | 0% | 2013-03-12 | 2013-09-12 | Budgeted Labor Cost | 2013-03-01: 23520; 2013-04-01: 36960; 2013-05-01: 36960; 2013-06-01: 33600; 2013-07-01: 36960; 2013-08-01: 36960; 2013-09-01: 12768
EC2250 | Fountain/Water Feature | EC00630.7 | 0% | 2013-03-12 | 2013-09-12 | Actual Labor Units
EC2250 | Fountain/Water Feature | EC00630.7 | 0% | 2013-03-12 | 2013-09-12 | Budgeted Labor Units | 2013-03-01: 224; 2013-04-01: 352; 2013-05-01: 352; 2013-06-01: 320; 2013-07-01: 352; 2013-08-01: 352; 2013-09-01: 122
EC2260 | Entry Feature/Sign Wall | EC00630.7 | 0% | 2013-03-18 | 2013-08-29 | Actual Labor Cost
EC2260 | Entry Feature/Sign Wall | EC00630.7 | 0% | 2013-03-18 | 2013-08-29 | Budgeted Labor Cost | 2013-03-01: 8640; 2013-04-01: 19008; 2013-05-01: 19008; 2013-06-01: 17280; 2013-07-01: 19008; 2013-08-01: 17366.4
EC2260 | Entry Feature/Sign Wall | EC00630.7 | 0% | 2013-03-18 | 2013-08-29 | Actual Labor Units
EC2260 | Entry Feature/Sign Wall | EC00630.7 | 0% | 2013-03-18 | 2013-08-29 | Budgeted Labor Units | 2013-03-01: 160; 2013-04-01: 352; 2013-05-01: 352; 2013-06-01: 320; 2013-07-01: 352; 2013-08-01: 322
EC2290 | Curbs & Paving | EC00630.7 | 0% | 2013-03-18 | 2013-07-11 | Actual Labor Cost
EC2290 | Curbs & Paving | EC00630.7 | 0% | 2013-03-18 | 2013-07-11 | Budgeted Labor Cost | 2013-03-01: 20800; 2013-04-01: 45760; 2013-05-01: 45760; 2013-06-01: 41600; 2013-07-01: 14560
EC2290 | Curbs & Paving | EC00630.7 | 0% | 2013-03-18 | 2013-07-11 | Actual Labor Units
EC2290 | Curbs & Paving | EC00630.7 | 0% | 2013-03-18 | 2013-07-11 | Budgeted Labor Units | 2013-03-01: 160; 2013-04-01: 352; 2013-05-01: 352; 2013-06-01: 320; 2013-07-01: 112
EC2340 | Fountain/Water Feature | EC00630.7 | 0% | 2013-07-03 | 2013-11-07 | Actual Labor Cost
EC2340 | Fountain/Water Feature | EC00630.7 | 0% | 2013-07-03 | 2013-11-07 | Budgeted Labor Cost | 2013-07-01: 41106; 2013-08-01: 45760; 2013-09-01: 41600; 2013-10-01: 47840; 2013-11-01: 9022
EC2340 | Fountain/Water Feature | EC00630.7 | 0% | 2013-07-03 | 2013-11-07 | Actual Labor Units
EC2340 | Fountain/Water Feature | EC00630.7 | 0% | 2013-07-03 | 2013-11-07 | Budgeted Labor Units | 2013-07-01: 316; 2013-08-01: 352; 2013-09-01: 320; 2013-10-01: 368; 2013-11-01: 69
EC00630.8 Landscape & Irrigation |  |  | 0% | 2012-01-05 | 2015-01-05 | Actual Labor Cost
EC00630.8 Landscape & Irrigation |  |  | 0% | 2012-01-05 | 2015-01-05 | Budgeted Labor Cost | 2012-01-01: 6080; 2012-02-01: 6720; 2012-03-01: 4480; 2013-10-01: 9370.95; 2013-11-01: 9729.73; 2013-12-01: 10216.22; 2014-01-01: 9532.43; 2014-02-01: 5405.41; 2014-03-01: 5675.68; 2014-04-01: 5945.95; 2014-05-01: 5945.95; 2014-06-01: 5675.68; 2014-07-01: 6216.22; 2014-08-01: 5675.68; 2014-09-01: 5945.95; 2014-10-01: 6216.22; 2014-11-01: 5405.41; 2014-12-01: 6216.22; 2015-01-01: 739.86
EC00630.8 Landscape & Irrigation |  |  | 0% | 2012-01-05 | 2015-01-05 | Actual Labor Units
EC00630.8 Landscape & Irrigation |  |  | 0% | 2012-01-05 | 2015-01-05 | Budgeted Labor Units | 2012-01-01: 152; 2012-02-01: 168; 2012-03-01: 112; 2013-10-01: 208; 2013-11-01: 216; 2013-12-01: 227; 2014-01-01: 207; 2014-02-01: 108; 2014-03-01: 114; 2014-04-01: 119; 2014-05-01: 119; 2014-06-01: 114; 2014-07-01: 124; 2014-08-01: 114; 2014-09-01: 119; 2014-10-01: 124; 2014-11-01: 108; 2014-12-01: 124; 2015-01-01: 15
EC1600 | Curbs & Paving | EC00630.8 | 0% | 2012-01-05 | 2012-03-20 | Actual Labor Cost
EC1600 | Curbs & Paving | EC00630.8 | 0% | 2012-01-05 | 2012-03-20 | Budgeted Labor Cost | 2012-01-01: 6080; 2012-02-01: 6720; 2012-03-01: 4480
EC1600 | Curbs & Paving | EC00630.8 | 0% | 2012-01-05 | 2012-03-20 | Actual Labor Units
EC1600 | Curbs & Paving | EC00630.8 | 0% | 2012-01-05 | 2012-03-20 | Budgeted Labor Units | 2012-01-01: 152; 2012-02-01: 168; 2012-03-01: 112
EC2360 | Landscape & Irrigation | EC00630.8 | 0% | 2013-10-04 | 2015-01-05 | Actual Labor Cost
EC2360 | Landscape & Irrigation | EC00630.8 | 0% | 2013-10-04 | 2015-01-05 | Budgeted Labor Cost | 2013-10-01: 9370.95; 2013-11-01: 9729.73; 2013-12-01: 10216.22; 2014-01-01: 9532.43; 2014-02-01: 5405.41; 2014-03-01: 5675.68; 2014-04-01: 5945.95; 2014-05-01: 5945.95; 2014-06-01: 5675.68; 2014-07-01: 6216.22; 2014-08-01: 5675.68; 2014-09-01: 5945.95; 2014-10-01: 6216.22; 2014-11-01: 5405.41; 2014-12-01: 6216.22; 2015-01-01: 739.86
EC2360 | Landscape & Irrigation | EC00630.8 | 0% | 2013-10-04 | 2015-01-05 | Actual Labor Units
EC2360 | Landscape & Irrigation | EC00630.8 | 0% | 2013-10-04 | 2015-01-05 | Budgeted Labor Units | 2013-10-01: 208; 2013-11-01: 216; 2013-12-01: 227; 2014-01-01: 207; 2014-02-01: 108; 2014-03-01: 114; 2014-04-01: 119; 2014-05-01: 119; 2014-06-01: 114; 2014-07-01: 124; 2014-08-01: 114; 2014-09-01: 119; 2014-10-01: 124; 2014-11-01: 108; 2014-12-01: 124; 2015-01-01: 15