## WBS
WBS Code | WBS Name
BG-01 | Fidility Prime Update 2
BG-01.planning | planning
BG-01.Product&D | Product Design And Development
BG-01.Process Design | Process Design And Development
BG-01.Process Design.Die | Die
BG-01.Process Design.Die.Design | Die Design
BG-01.Process Design.Die.Constraction | Die Constraction
BG-01.Process Design.Die.Validation | Die Validation
BG-01.Process Design.CF | CF
BG-01.Process Design.CF.Design | CF Design
BG-01.Process Design.CF.Constraction | CF Constraction
BG-01.Process Design.CF.Validation | CF Validation
BG-01.Process Design.PF | PF
BG-01.Process Design.PF.Design | PF Design
BG-01.Process Design.PF.Constraction | PF Constraction
BG-01.Process Design.PF.Validation | PF Validation
BG-01.Phase 4 | Validation Product And Process
BG-01.Phase 4.3 | Production
BG-01.Phase 4.3.1 | Pre catalyst
BG-01.Phase 4.3.2 | Main Catalyst and Muffler
BG-01.Phase 4.3.3 | pipe Down

## Activities
Activity ID | Activity Name | WBS | Start | Finish | Schedule % Complete | Spreadsheet Field | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
Fidility Prime Update 2 |  |  | 04-Jul-2023 A | 2024-06-29 | 23.61% | Cum Actual Labor Units | 3.29 | 4.52 | 5.06 | 6.88 | 16.4 | 27.88 | 27.88 | 27.88 | 27.88 | 27.88 | 27.88 | 27.88
Fidility Prime Update 2 |  |  | 04-Jul-2023 A | 2024-06-29 | 23.61% | Cum BL Project Labor Units | 3.29 | 4.52 | 5.29 | 6.72 | 15.89 | 34.81 | 64.03 | 81.53 | 92.14 | 94.69 | 98.3 | 100
Fidility Prime Update 2 |  |  | 04-Jul-2023 A | 2024-06-29 | 23.61% | Cum Remaining Labor Units | 2023-12-01: 13.93; 2024-01-01: 41.12; 2024-02-01: 61.05; 2024-03-01: 68.35; 2024-04-01: 71.29; 2024-05-01: 73.12; 2024-06-01: 74.8
planning |  |  | 04-Jul-2023 A | 2023-12-24 | 88.52% | Cum Actual Labor Units | 2.57 | 3.18 | 3.68 | 3.93 | 4.52 | 4.52 | 4.52 | 4.52 | 4.52 | 4.52 | 4.52 | 4.52
planning |  |  | 04-Jul-2023 A | 2023-12-24 | 88.52% | Cum BL Project Labor Units | 2.57 | 3.18 | 3.68 | 3.93 | 4.52 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1
planning |  |  | 04-Jul-2023 A | 2023-12-24 | 88.52% | Cum Remaining Labor Units | 2023-12-01: 1.76; 2024-01-01: 1.76; 2024-02-01: 1.76; 2024-03-01: 1.76; 2024-04-01: 1.76; 2024-05-01: 1.76; 2024-06-01: 1.76
Pln1011 | ارسال آناليز قيمت به مشتري جهت تائيد همکاري | BG-01.planning | 22-Aug-2023 A | 23-Aug-2023 A | 100% | Cum Actual Labor Units |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1011 | ارسال آناليز قيمت به مشتري جهت تائيد همکاري | BG-01.planning | 22-Aug-2023 A | 23-Aug-2023 A | 100% | Cum BL Project Labor Units |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1011 | ارسال آناليز قيمت به مشتري جهت تائيد همکاري | BG-01.planning | 22-Aug-2023 A | 23-Aug-2023 A | 100% | Cum Remaining Labor Units
Pln1007 | استعلام از پيمانکاران و تامين کنندگان | BG-01.planning | 11-Jul-2023 A | 15-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1007 | استعلام از پيمانکاران و تامين کنندگان | BG-01.planning | 11-Jul-2023 A | 15-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1007 | استعلام از پيمانکاران و تامين کنندگان | BG-01.planning | 11-Jul-2023 A | 15-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1015 | انتخاب مدير پروژه | BG-01.planning | 26-Sep-2023 A | 27-Sep-2023 A | 100% | Cum Actual Labor Units |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1015 | انتخاب مدير پروژه | BG-01.planning | 26-Sep-2023 A | 27-Sep-2023 A | 100% | Cum BL Project Labor Units |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1015 | انتخاب مدير پروژه | BG-01.planning | 26-Sep-2023 A | 27-Sep-2023 A | 100% | Cum Remaining Labor Units
Pln1010 | انتخاب پيمانکاران و تامين کنندگان جهت انعقاد قرارداد(کميسون) | BG-01.planning | 01-Aug-2023 A | 05-Aug-2023 A | 100% | Cum Actual Labor Units |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1010 | انتخاب پيمانکاران و تامين کنندگان جهت انعقاد قرارداد(کميسون) | BG-01.planning | 01-Aug-2023 A | 05-Aug-2023 A | 100% | Cum BL Project Labor Units |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1010 | انتخاب پيمانکاران و تامين کنندگان جهت انعقاد قرارداد(کميسون) | BG-01.planning | 01-Aug-2023 A | 05-Aug-2023 A | 100% | Cum Remaining Labor Units
Pln1012 | انعقاد قرارداد با شرکت بهمن موتور | BG-01.planning | 19-Nov-2023 A | 22-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59
Pln1012 | انعقاد قرارداد با شرکت بهمن موتور | BG-01.planning | 19-Nov-2023 A | 22-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59
Pln1012 | انعقاد قرارداد با شرکت بهمن موتور | BG-01.planning | 19-Nov-2023 A | 22-Nov-2023 A | 100% | Cum Remaining Labor Units
Pln1014 | انعقاد قرارداد با پيمانکاران و تامين کنندگان | BG-01.planning | 19-Dec-2023 A | 2023-12-24 | 0% | Cum Actual Labor Units
Pln1014 | انعقاد قرارداد با پيمانکاران و تامين کنندگان | BG-01.planning | 19-Dec-2023 A | 2023-12-24 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.59; 2024-01-01: 0.59; 2024-02-01: 0.59; 2024-03-01: 0.59; 2024-04-01: 0.59; 2024-05-01: 0.59; 2024-06-01: 0.59
Pln1014 | انعقاد قرارداد با پيمانکاران و تامين کنندگان | BG-01.planning | 19-Dec-2023 A | 2023-12-24 | 0% | Cum Remaining Labor Units | 2023-12-01: 1.76; 2024-01-01: 1.76; 2024-02-01: 1.76; 2024-03-01: 1.76; 2024-04-01: 1.76; 2024-05-01: 1.76; 2024-06-01: 1.76
Pln1006 | اوليه BOMتهيه | BG-01.planning | 11-Jul-2023 A | 12-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1006 | اوليه BOMتهيه | BG-01.planning | 11-Jul-2023 A | 12-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1006 | اوليه BOMتهيه | BG-01.planning | 11-Jul-2023 A | 12-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1008 | بررسي و آناليز قيمت محصول | BG-01.planning | 24-Jul-2023 A | 25-Jul-2023 A | 100% | Cum Actual Labor Units | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Pln1008 | بررسي و آناليز قيمت محصول | BG-01.planning | 24-Jul-2023 A | 25-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Pln1008 | بررسي و آناليز قيمت محصول | BG-01.planning | 24-Jul-2023 A | 25-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1016 | برگزاري جلسه افتتاحيه | BG-01.planning | 02-Oct-2023 A | 03-Oct-2023 A | 100% | Cum Actual Labor Units |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1016 | برگزاري جلسه افتتاحيه | BG-01.planning | 02-Oct-2023 A | 03-Oct-2023 A | 100% | Cum BL Project Labor Units |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1016 | برگزاري جلسه افتتاحيه | BG-01.planning | 02-Oct-2023 A | 03-Oct-2023 A | 100% | Cum Remaining Labor Units
Pln1009 | تائيد آناليز قيمت توسط قائم مقام محترم | BG-01.planning | 26-Jul-2023 A | 05-Aug-2023 A | 100% | Cum Actual Labor Units | 0.14 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1009 | تائيد آناليز قيمت توسط قائم مقام محترم | BG-01.planning | 26-Jul-2023 A | 05-Aug-2023 A | 100% | Cum BL Project Labor Units | 0.14 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1009 | تائيد آناليز قيمت توسط قائم مقام محترم | BG-01.planning | 26-Jul-2023 A | 05-Aug-2023 A | 100% | Cum Remaining Labor Units
Pln1005 | تهيه ليست تجهيزات برون سپاري | BG-01.planning | 10-Jul-2023 A | 10-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1005 | تهيه ليست تجهيزات برون سپاري | BG-01.planning | 10-Jul-2023 A | 10-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1005 | تهيه ليست تجهيزات برون سپاري | BG-01.planning | 10-Jul-2023 A | 10-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1003 | تهيه گزارش امکان سنجي محصول | BG-01.planning | 05-Jul-2023 A | 08-Jul-2023 A | 100% | Cum Actual Labor Units | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42
Pln1003 | تهيه گزارش امکان سنجي محصول | BG-01.planning | 05-Jul-2023 A | 08-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42
Pln1003 | تهيه گزارش امکان سنجي محصول | BG-01.planning | 05-Jul-2023 A | 08-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1013 | درخواست تعريف کد مرکز هزينه پروژه | BG-01.planning | 25-Sep-2023 A | 26-Sep-2023 A | 100% | Cum Actual Labor Units |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1013 | درخواست تعريف کد مرکز هزينه پروژه | BG-01.planning | 25-Sep-2023 A | 26-Sep-2023 A | 100% | Cum BL Project Labor Units |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1013 | درخواست تعريف کد مرکز هزينه پروژه | BG-01.planning | 25-Sep-2023 A | 26-Sep-2023 A | 100% | Cum Remaining Labor Units
Pln1001 | دريافت نقشه و مدل هاي سه بعدي از شرکت بهمن موتورز | BG-01.planning | 04-Jul-2023 A | 04-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1001 | دريافت نقشه و مدل هاي سه بعدي از شرکت بهمن موتورز | BG-01.planning | 04-Jul-2023 A | 04-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1001 | دريافت نقشه و مدل هاي سه بعدي از شرکت بهمن موتورز | BG-01.planning | 04-Jul-2023 A | 04-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1002 | دريافت نمونه مرجع کاتاليست از شرکت بهمن موتورز | BG-01.planning | 04-Jul-2023 A | 04-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1002 | دريافت نمونه مرجع کاتاليست از شرکت بهمن موتورز | BG-01.planning | 04-Jul-2023 A | 04-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1002 | دريافت نمونه مرجع کاتاليست از شرکت بهمن موتورز | BG-01.planning | 04-Jul-2023 A | 04-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1004 | طراحي فرآيند توليد محصول | BG-01.planning | 09-Jul-2023 A | 09-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1004 | طراحي فرآيند توليد محصول | BG-01.planning | 09-Jul-2023 A | 09-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Pln1004 | طراحي فرآيند توليد محصول | BG-01.planning | 09-Jul-2023 A | 09-Jul-2023 A | 100% | Cum Remaining Labor Units
Pln1017 | پايان فاز برنامه ريزي | BG-01.planning |  | 2023-12-24 | 0% | Cum Actual Labor Units
Pln1017 | پايان فاز برنامه ريزي | BG-01.planning |  | 2023-12-24 | 0% | Cum BL Project Labor Units
Pln1017 | پايان فاز برنامه ريزي | BG-01.planning |  | 2023-12-24 | 0% | Cum Remaining Labor Units
Product Design And Development |  |  | 05-Jul-2023 A | 2024-06-08 | 59.03% | Cum Actual Labor Units | 0.72 | 1.34 | 1.37 | 2.02 | 2.85 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48
Product Design And Development |  |  | 05-Jul-2023 A | 2024-06-08 | 59.03% | Cum BL Project Labor Units | 0.72 | 1.34 | 1.36 | 1.89 | 2.62 | 3.52 | 4.21 | 4.38 | 4.5 | 4.65 | 4.83 | 4.93
Product Design And Development |  |  | 05-Jul-2023 A | 2024-06-08 | 59.03% | Cum Remaining Labor Units | 2023-12-01: 1.58; 2024-01-01: 1.78; 2024-02-01: 1.95; 2024-03-01: 2.08; 2024-04-01: 2.22; 2024-05-01: 2.4; 2024-06-01: 2.46
Product1011 | ارسال نمونه به مرکز تست آلايندگي جهت تست آلايندگي | BG-01.Product&D | 2023-12-26 | 2023-12-30 | 0% | Cum Actual Labor Units
Product1011 | ارسال نمونه به مرکز تست آلايندگي جهت تست آلايندگي | BG-01.Product&D | 2023-12-26 | 2023-12-30 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.25; 2024-02-01: 0.25; 2024-03-01: 0.25; 2024-04-01: 0.25; 2024-05-01: 0.25; 2024-06-01: 0.25
Product1011 | ارسال نمونه به مرکز تست آلايندگي جهت تست آلايندگي | BG-01.Product&D | 2023-12-26 | 2023-12-30 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.25; 2024-01-01: 0.25; 2024-02-01: 0.25; 2024-03-01: 0.25; 2024-04-01: 0.25; 2024-05-01: 0.25; 2024-06-01: 0.25
Product1002 | تخريب و استخراج مونوليت از کاتاليست | BG-01.Product&D | 19-Jul-2023 A | 19-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Product1002 | تخريب و استخراج مونوليت از کاتاليست | BG-01.Product&D | 19-Jul-2023 A | 19-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Product1002 | تخريب و استخراج مونوليت از کاتاليست | BG-01.Product&D | 19-Jul-2023 A | 19-Jul-2023 A | 100% | Cum Remaining Labor Units
Product1008 | توليد نمونه اوليه مونوليت ايران دلکويي فيدليتي پرايم | BG-01.Product&D | 16-Dec-2023 A | 18-Dec-2023 A | 0% | Cum Actual Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
Product1008 | توليد نمونه اوليه مونوليت ايران دلکويي فيدليتي پرايم | BG-01.Product&D | 16-Dec-2023 A | 18-Dec-2023 A | 0% | Cum BL Project Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
Product1008 | توليد نمونه اوليه مونوليت ايران دلکويي فيدليتي پرايم | BG-01.Product&D | 16-Dec-2023 A | 18-Dec-2023 A | 0% | Cum Remaining Labor Units
Product1005 | ثبت درخواست ساخت تجهيزات در نرم افزار ساخت | BG-01.Product&D | 31-Oct-2023 A | 04-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  | 0.01 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Product1005 | ثبت درخواست ساخت تجهيزات در نرم افزار ساخت | BG-01.Product&D | 31-Oct-2023 A | 04-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  | 0.01 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Product1005 | ثبت درخواست ساخت تجهيزات در نرم افزار ساخت | BG-01.Product&D | 31-Oct-2023 A | 04-Nov-2023 A | 100% | Cum Remaining Labor Units
Product1001 | ثبت درخواست ساخت فيکسچر نمونه سازي | BG-01.Product&D | 05-Jul-2023 A | 05-Jul-2023 A | 100% | Cum Actual Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Product1001 | ثبت درخواست ساخت فيکسچر نمونه سازي | BG-01.Product&D | 05-Jul-2023 A | 05-Jul-2023 A | 100% | Cum BL Project Labor Units | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Product1001 | ثبت درخواست ساخت فيکسچر نمونه سازي | BG-01.Product&D | 05-Jul-2023 A | 05-Jul-2023 A | 100% | Cum Remaining Labor Units
Product1009 | جازني مونوليت کوت شده ايران دلکويي در نمونه مرجع | BG-01.Product&D | 17-Dec-2023 A | 2023-12-25 | 0% | Cum Actual Labor Units
Product1009 | جازني مونوليت کوت شده ايران دلکويي در نمونه مرجع | BG-01.Product&D | 17-Dec-2023 A | 2023-12-25 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.01; 2024-01-01: 0.25; 2024-02-01: 0.25; 2024-03-01: 0.25; 2024-04-01: 0.25; 2024-05-01: 0.25; 2024-06-01: 0.25
Product1009 | جازني مونوليت کوت شده ايران دلکويي در نمونه مرجع | BG-01.Product&D | 17-Dec-2023 A | 2023-12-25 | 0% | Cum Remaining Labor Units | 2023-12-01: 1.25; 2024-01-01: 1.25; 2024-02-01: 1.25; 2024-03-01: 1.25; 2024-04-01: 1.25; 2024-05-01: 1.25; 2024-06-01: 1.25
Product1012 | دريافت تائيديه تست آلايندگي | BG-01.Product&D |  | 2023-12-30 | 0% | Cum Actual Labor Units
Product1012 | دريافت تائيديه تست آلايندگي | BG-01.Product&D |  | 2023-12-30 | 0% | Cum BL Project Labor Units
Product1012 | دريافت تائيديه تست آلايندگي | BG-01.Product&D |  | 2023-12-30 | 0% | Cum Remaining Labor Units
Product1010 | دريافت نمونه اوليه فلکسيبل | BG-01.Product&D | 27-Sep-2023 A | 02-Dec-2023 A | 89.31% | Cum Actual Labor Units |  |  | 0.01 | 0.26 | 0.49 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Product1010 | دريافت نمونه اوليه فلکسيبل | BG-01.Product&D | 27-Sep-2023 A | 02-Dec-2023 A | 89.31% | Cum BL Project Labor Units |  |  | 0.01 | 0.19 | 0.35 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Product1010 | دريافت نمونه اوليه فلکسيبل | BG-01.Product&D | 27-Sep-2023 A | 02-Dec-2023 A | 89.31% | Cum Remaining Labor Units
Product1006 | دريافت نمونه مونوليت از تامين کننده خارجي | BG-01.Product&D | 27-Sep-2023 A | 16-Dec-2023 A | 89.31% | Cum Actual Labor Units |  |  | 0.01 | 0.18 | 0.34 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42
Product1006 | دريافت نمونه مونوليت از تامين کننده خارجي | BG-01.Product&D | 27-Sep-2023 A | 16-Dec-2023 A | 89.31% | Cum BL Project Labor Units |  |  | 0.01 | 0.15 | 0.29 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42
Product1006 | دريافت نمونه مونوليت از تامين کننده خارجي | BG-01.Product&D | 27-Sep-2023 A | 16-Dec-2023 A | 89.31% | Cum Remaining Labor Units
Product1007 | سفارش گذاري و خريد فلکسيبل | BG-01.Product&D | 27-Sep-2023 A | 2024-06-08 | 33.36% | Cum Actual Labor Units |  |  | 0.01 | 0.11 | 0.21 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28
Product1007 | سفارش گذاري و خريد فلکسيبل | BG-01.Product&D | 27-Sep-2023 A | 2024-06-08 | 33.36% | Cum BL Project Labor Units |  |  | 0 | 0.1 | 0.19 | 0.29 | 0.39 | 0.48 | 0.54 | 0.61 | 0.7 | 0.75
Product1007 | سفارش گذاري و خريد فلکسيبل | BG-01.Product&D | 27-Sep-2023 A | 2024-06-08 | 33.36% | Cum Remaining Labor Units | 2023-12-01: 0.04; 2024-01-01: 0.14; 2024-02-01: 0.22; 2024-03-01: 0.29; 2024-04-01: 0.36; 2024-05-01: 0.45; 2024-06-01: 0.48
Product1004 | سفارش گذاري و خريد مونوليت مطابق ابعاد نقشه | BG-01.Product&D | 27-Sep-2023 A | 2024-06-08 | 33.36% | Cum Actual Labor Units |  |  | 0.01 | 0.11 | 0.21 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28
Product1004 | سفارش گذاري و خريد مونوليت مطابق ابعاد نقشه | BG-01.Product&D | 27-Sep-2023 A | 2024-06-08 | 33.36% | Cum BL Project Labor Units |  |  | 0 | 0.1 | 0.19 | 0.29 | 0.39 | 0.48 | 0.54 | 0.61 | 0.7 | 0.75
Product1004 | سفارش گذاري و خريد مونوليت مطابق ابعاد نقشه | BG-01.Product&D | 27-Sep-2023 A | 2024-06-08 | 33.36% | Cum Remaining Labor Units | 2023-12-01: 0.04; 2024-01-01: 0.14; 2024-02-01: 0.22; 2024-03-01: 0.29; 2024-04-01: 0.36; 2024-05-01: 0.45; 2024-06-01: 0.48
Product1003 | فرمولاسيون و مواد سازي کوت مونوليت | BG-01.Product&D | 22-Jul-2023 A | 30-Aug-2023 A | 100% | Cum Actual Labor Units | 0.22 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84
Product1003 | فرمولاسيون و مواد سازي کوت مونوليت | BG-01.Product&D | 22-Jul-2023 A | 30-Aug-2023 A | 100% | Cum BL Project Labor Units | 0.22 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84
Product1003 | فرمولاسيون و مواد سازي کوت مونوليت | BG-01.Product&D | 22-Jul-2023 A | 30-Aug-2023 A | 100% | Cum Remaining Labor Units
Process Design And Development |  |  | 30-Oct-2023 A | 2024-06-29 | 17.84% | Cum Actual Labor Units |  |  |  | 0.92 | 9.03 | 19.87 | 19.87 | 19.87 | 19.87 | 19.87 | 19.87 | 19.87
Process Design And Development |  |  | 30-Oct-2023 A | 2024-06-29 | 17.84% | Cum BL Project Labor Units |  |  |  | 0.65 | 8.5 | 25.85 | 54.06 | 71.38 | 81.87 | 84.28 | 87.71 | 89.3
Process Design And Development |  |  | 30-Oct-2023 A | 2024-06-29 | 17.84% | Cum Remaining Labor Units | 2023-12-01: 10.28; 2024-01-01: 36.95; 2024-02-01: 56.68; 2024-03-01: 63.86; 2024-04-01: 66.65; 2024-05-01: 68.3; 2024-06-01: 69.93
Die |  |  | 07-Nov-2023 A | 2024-06-29 | 21.87% | Cum Actual Labor Units |  |  |  |  | 2.14 | 7.01 | 7.01 | 7.01 | 7.01 | 7.01 | 7.01 | 7.01
Die |  |  | 07-Nov-2023 A | 2024-06-29 | 21.87% | Cum BL Project Labor Units |  |  |  |  | 2.14 | 12.99 | 24.33 | 29.7 | 29.97 | 30.29 | 30.68 | 32.27
Die |  |  | 07-Nov-2023 A | 2024-06-29 | 21.87% | Cum Remaining Labor Units | 2023-12-01: 6.37; 2024-01-01: 16.8; 2024-02-01: 22.66; 2024-03-01: 22.92; 2024-04-01: 23.24; 2024-05-01: 23.64; 2024-06-01: 25.27
Die Design |  |  | 07-Nov-2023 A | 2024-01-09 | 56.09% | Cum Actual Labor Units |  |  |  |  | 2.01 | 5.26 | 5.26 | 5.26 | 5.26 | 5.26 | 5.26 | 5.26
Die Design |  |  | 07-Nov-2023 A | 2024-01-09 | 56.09% | Cum BL Project Labor Units |  |  |  |  | 2.01 | 8.45 | 10.03 | 10.03 | 10.03 | 10.03 | 10.03 | 10.03
Die Design |  |  | 07-Nov-2023 A | 2024-01-09 | 56.09% | Cum Remaining Labor Units | 2023-12-01: 3.19; 2024-01-01: 4.78; 2024-02-01: 4.78; 2024-03-01: 4.78; 2024-04-01: 4.78; 2024-05-01: 4.78; 2024-06-01: 4.78
D-DIE1010 | سايلنسر کاتاليست دوم Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 2023-12-23 | 2023-12-24 | 0% | Cum Actual Labor Units
D-DIE1010 | سايلنسر کاتاليست دوم Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 2023-12-23 | 2023-12-24 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1010 | سايلنسر کاتاليست دوم Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 2023-12-23 | 2023-12-24 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1011 | سايلنسر کاتاليست دوم Uطراحي قالب فرم | BG-01.Process Design.Die.Design | 2023-12-23 | 2023-12-24 | 0% | Cum Actual Labor Units
D-DIE1011 | سايلنسر کاتاليست دوم Uطراحي قالب فرم | BG-01.Process Design.Die.Design | 2023-12-23 | 2023-12-24 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1011 | سايلنسر کاتاليست دوم Uطراحي قالب فرم | BG-01.Process Design.Die.Design | 2023-12-23 | 2023-12-24 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1002 | شل Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 25-Nov-2023 A | 29-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1002 | شل Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 25-Nov-2023 A | 29-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1002 | شل Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 25-Nov-2023 A | 29-Nov-2023 A | 100% | Cum Remaining Labor Units
D-DIE1005 | طراحي قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Design | 10-Dec-2023 A | 16-Dec-2023 A | 100% | Cum Actual Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1005 | طراحي قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Design | 10-Dec-2023 A | 16-Dec-2023 A | 100% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1005 | طراحي قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Design | 10-Dec-2023 A | 16-Dec-2023 A | 100% | Cum Remaining Labor Units
D-DIE1004 | طراحي قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Design | 29-Nov-2023 A | 10-Dec-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.01 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1004 | طراحي قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Design | 29-Nov-2023 A | 10-Dec-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.01 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1004 | طراحي قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Design | 29-Nov-2023 A | 10-Dec-2023 A | 100% | Cum Remaining Labor Units
D-DIE1012 | طراحي قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 2023-12-19 | 2023-12-20 | 52.63% | Cum Actual Labor Units
D-DIE1012 | طراحي قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 2023-12-19 | 2023-12-20 | 52.63% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1012 | طراحي قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 2023-12-19 | 2023-12-20 | 52.63% | Cum Remaining Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1003 | طراحي قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Design | 07-Nov-2023 A | 29-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1003 | طراحي قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Design | 07-Nov-2023 A | 29-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1003 | طراحي قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Design | 07-Nov-2023 A | 29-Nov-2023 A | 100% | Cum Remaining Labor Units
D-DIE1009 | طراحي قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Actual Labor Units | 2023-12-01: 0.48; 2024-01-01: 0.48; 2024-02-01: 0.48; 2024-03-01: 0.48; 2024-04-01: 0.48; 2024-05-01: 0.48; 2024-06-01: 0.48
D-DIE1009 | طراحي قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1009 | طراحي قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Remaining Labor Units | 2023-12-01: 0.19; 2024-01-01: 0.19; 2024-02-01: 0.19; 2024-03-01: 0.19; 2024-04-01: 0.19; 2024-05-01: 0.19; 2024-06-01: 0.19
D-DIE1013 | طراحي قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 2023-12-25 | 2024-01-03 | 0% | Cum Actual Labor Units
D-DIE1013 | طراحي قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 2023-12-25 | 2024-01-03 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1013 | طراحي قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 2023-12-25 | 2024-01-03 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1008 | طراحي قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Actual Labor Units | 2023-12-01: 0.48; 2024-01-01: 0.48; 2024-02-01: 0.48; 2024-03-01: 0.48; 2024-04-01: 0.48; 2024-05-01: 0.48; 2024-06-01: 0.48
D-DIE1008 | طراحي قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1008 | طراحي قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Remaining Labor Units | 2023-12-01: 0.19; 2024-01-01: 0.19; 2024-02-01: 0.19; 2024-03-01: 0.19; 2024-04-01: 0.19; 2024-05-01: 0.19; 2024-06-01: 0.19
D-DIE1006 | طراحي قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Actual Labor Units | 2023-12-01: 0.48; 2024-01-01: 0.48; 2024-02-01: 0.48; 2024-03-01: 0.48; 2024-04-01: 0.48; 2024-05-01: 0.48; 2024-06-01: 0.48
D-DIE1006 | طراحي قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1006 | طراحي قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Remaining Labor Units | 2023-12-01: 0.19; 2024-01-01: 0.19; 2024-02-01: 0.19; 2024-03-01: 0.19; 2024-04-01: 0.19; 2024-05-01: 0.19; 2024-06-01: 0.19
D-DIE1007 | طراحي قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Actual Labor Units | 2023-12-01: 0.48; 2024-01-01: 0.48; 2024-02-01: 0.48; 2024-03-01: 0.48; 2024-04-01: 0.48; 2024-05-01: 0.48; 2024-06-01: 0.48
D-DIE1007 | طراحي قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1007 | طراحي قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Design | 11-Dec-2023 A | 2023-12-20 | 72.18% | Cum Remaining Labor Units | 2023-12-01: 0.19; 2024-01-01: 0.19; 2024-02-01: 0.19; 2024-03-01: 0.19; 2024-04-01: 0.19; 2024-05-01: 0.19; 2024-06-01: 0.19
D-DIE1001 | طراحي قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Design | 18-Nov-2023 A | 25-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1001 | طراحي قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Design | 18-Nov-2023 A | 25-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-DIE1001 | طراحي قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Design | 18-Nov-2023 A | 25-Nov-2023 A | 100% | Cum Remaining Labor Units
D-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uطراحي قالب فرم | BG-01.Process Design.Die.Design | 2024-01-06 | 2024-01-09 | 0% | Cum Actual Labor Units
D-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uطراحي قالب فرم | BG-01.Process Design.Die.Design | 2024-01-06 | 2024-01-09 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uطراحي قالب فرم | BG-01.Process Design.Die.Design | 2024-01-06 | 2024-01-09 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 2024-01-06 | 2024-01-09 | 0% | Cum Actual Labor Units
D-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 2024-01-06 | 2024-01-09 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oطراحي قالب فرم | BG-01.Process Design.Die.Design | 2024-01-06 | 2024-01-09 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-DIE1016 | پايان طراحي قالب هاي مجموعه | BG-01.Process Design.Die.Design |  | 2024-01-09 | 0% | Cum Actual Labor Units
D-DIE1016 | پايان طراحي قالب هاي مجموعه | BG-01.Process Design.Die.Design |  | 2024-01-09 | 0% | Cum BL Project Labor Units
D-DIE1016 | پايان طراحي قالب هاي مجموعه | BG-01.Process Design.Die.Design |  | 2024-01-09 | 0% | Cum Remaining Labor Units
Die Constraction |  |  | 25-Nov-2023 A | 2024-06-26 | 10.01% | Cum Actual Labor Units |  |  |  |  | 0.13 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75
Die Constraction |  |  | 25-Nov-2023 A | 2024-06-26 | 10.01% | Cum BL Project Labor Units |  |  |  |  | 0.12 | 4.12 | 10.95 | 12.98 | 13.25 | 13.56 | 13.96 | 14.3
Die Constraction |  |  | 25-Nov-2023 A | 2024-06-26 | 10.01% | Cum Remaining Labor Units | 2023-12-01: 2.34; 2024-01-01: 9.1; 2024-02-01: 11.19; 2024-03-01: 11.46; 2024-04-01: 11.78; 2024-05-01: 12.17; 2024-06-01: 12.55
C-DIE1005 | ساخت قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Constraction | 17-Dec-2023 A | 2024-02-12 | 12.03% | Cum Actual Labor Units | 2023-12-01: 0.04; 2024-01-01: 0.04; 2024-02-01: 0.04; 2024-03-01: 0.04; 2024-04-01: 0.04; 2024-05-01: 0.04; 2024-06-01: 0.04
C-DIE1005 | ساخت قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Constraction | 17-Dec-2023 A | 2024-02-12 | 12.03% | Cum BL Project Labor Units | 2023-12-01: 0.25; 2024-01-01: 0.66; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1005 | ساخت قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Constraction | 17-Dec-2023 A | 2024-02-12 | 12.03% | Cum Remaining Labor Units | 2023-12-01: 0.16; 2024-01-01: 0.57; 2024-02-01: 0.72; 2024-03-01: 0.72; 2024-04-01: 0.72; 2024-05-01: 0.72; 2024-06-01: 0.72
C-DIE1016 | ساخت قالب ال سيل | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-01-17 | 0% | Cum Actual Labor Units
C-DIE1016 | ساخت قالب ال سيل | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-01-17 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1016 | ساخت قالب ال سيل | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-01-17 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1004 | ساخت قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Constraction | 10-Dec-2023 A | 2024-01-01 | 24.21% | Cum Actual Labor Units | 2023-12-01: 0.45; 2024-01-01: 0.45; 2024-02-01: 0.45; 2024-03-01: 0.45; 2024-04-01: 0.45; 2024-05-01: 0.45; 2024-06-01: 0.45
C-DIE1004 | ساخت قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Constraction | 10-Dec-2023 A | 2024-01-01 | 24.21% | Cum BL Project Labor Units | 2023-12-01: 0.45; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1004 | ساخت قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Constraction | 10-Dec-2023 A | 2024-01-01 | 24.21% | Cum Remaining Labor Units | 2023-12-01: 0.27; 2024-01-01: 0.3; 2024-02-01: 0.3; 2024-03-01: 0.3; 2024-04-01: 0.3; 2024-05-01: 0.3; 2024-06-01: 0.3
C-DIE1012 | ساخت قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-01-06 | 0% | Cum Actual Labor Units
C-DIE1012 | ساخت قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-01-06 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.55; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1012 | ساخت قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-01-06 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.48; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1003 | ساخت قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Constraction | 29-Nov-2023 A | 16-Dec-2023 A | 45.01% | Cum Actual Labor Units |  |  |  |  | 0 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-DIE1003 | ساخت قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Constraction | 29-Nov-2023 A | 16-Dec-2023 A | 45.01% | Cum BL Project Labor Units |  |  |  |  | 0 | 0.57 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-DIE1003 | ساخت قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Constraction | 29-Nov-2023 A | 16-Dec-2023 A | 45.01% | Cum Remaining Labor Units
C-DIE1009 | ساخت قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Actual Labor Units
C-DIE1009 | ساخت قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1009 | ساخت قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1018 | ساخت قالب هاي براکت ها | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum Actual Labor Units
C-DIE1018 | ساخت قالب هاي براکت ها | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.04; 2024-01-01: 0.19; 2024-02-01: 0.31; 2024-03-01: 0.4; 2024-04-01: 0.51; 2024-05-01: 0.64; 2024-06-01: 0.75
C-DIE1018 | ساخت قالب هاي براکت ها | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.03; 2024-01-01: 0.18; 2024-02-01: 0.3; 2024-03-01: 0.39; 2024-04-01: 0.5; 2024-05-01: 0.63; 2024-06-01: 0.75
C-DIE1017 | ساخت قالب هاي پوسته ورودي و خروجي | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum Actual Labor Units
C-DIE1017 | ساخت قالب هاي پوسته ورودي و خروجي | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.04; 2024-01-01: 0.19; 2024-02-01: 0.31; 2024-03-01: 0.4; 2024-04-01: 0.51; 2024-05-01: 0.64; 2024-06-01: 0.75
C-DIE1017 | ساخت قالب هاي پوسته ورودي و خروجي | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.03; 2024-01-01: 0.18; 2024-02-01: 0.3; 2024-03-01: 0.39; 2024-04-01: 0.5; 2024-05-01: 0.63; 2024-06-01: 0.75
C-DIE1019 | ساخت قالب هاي کاور حرارتي | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum Actual Labor Units
C-DIE1019 | ساخت قالب هاي کاور حرارتي | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.04; 2024-01-01: 0.19; 2024-02-01: 0.31; 2024-03-01: 0.4; 2024-04-01: 0.51; 2024-05-01: 0.64; 2024-06-01: 0.75
C-DIE1019 | ساخت قالب هاي کاور حرارتي | BG-01.Process Design.Die.Constraction | 2023-12-24 | 2024-06-26 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.03; 2024-01-01: 0.18; 2024-02-01: 0.3; 2024-03-01: 0.39; 2024-04-01: 0.5; 2024-05-01: 0.63; 2024-06-01: 0.75
C-DIE1013 | ساخت قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2024-01-06 | 2024-02-13 | 0% | Cum Actual Labor Units
C-DIE1013 | ساخت قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2024-01-06 | 2024-02-13 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.52; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1013 | ساخت قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2024-01-06 | 2024-02-13 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.52; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1008 | ساخت قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Actual Labor Units
C-DIE1008 | ساخت قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1008 | ساخت قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1006 | ساخت قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Actual Labor Units
C-DIE1006 | ساخت قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1006 | ساخت قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1007 | ساخت قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Actual Labor Units
C-DIE1007 | ساخت قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1007 | ساخت قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Constraction | 2023-12-23 | 2024-02-13 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.58; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1001 | ساخت قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Constraction | 25-Nov-2023 A | 2023-12-30 | 68.21% | Cum Actual Labor Units |  |  |  |  | 0.12 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51
C-DIE1001 | ساخت قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Constraction | 25-Nov-2023 A | 2023-12-30 | 68.21% | Cum BL Project Labor Units |  |  |  |  | 0.12 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-DIE1001 | ساخت قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Constraction | 25-Nov-2023 A | 2023-12-30 | 68.21% | Cum Remaining Labor Units | 2023-12-01: 0.24; 2024-01-01: 0.24; 2024-02-01: 0.24; 2024-03-01: 0.24; 2024-04-01: 0.24; 2024-05-01: 0.24; 2024-06-01: 0.24
C-DIE1010 | سايلنسر کاتاليست دوم Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2023-12-25 | 2024-01-23 | 0% | Cum Actual Labor Units
C-DIE1010 | سايلنسر کاتاليست دوم Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2023-12-25 | 2024-01-23 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.17; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1010 | سايلنسر کاتاليست دوم Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2023-12-25 | 2024-01-23 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.17; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1011 | سايلنسر کاتاليست دوم Uساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2023-12-25 | 2024-01-23 | 0% | Cum Actual Labor Units
C-DIE1011 | سايلنسر کاتاليست دوم Uساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2023-12-25 | 2024-01-23 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.17; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1011 | سايلنسر کاتاليست دوم Uساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2023-12-25 | 2024-01-23 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.17; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1002 | شل کاتاليست اول Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 29-Nov-2023 A | 2024-01-31 | 40.79% | Cum Actual Labor Units
C-DIE1002 | شل کاتاليست اول Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 29-Nov-2023 A | 2024-01-31 | 40.79% | Cum BL Project Labor Units |  |  |  |  | 0 | 0.52 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-DIE1002 | شل کاتاليست اول Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 29-Nov-2023 A | 2024-01-31 | 40.79% | Cum Remaining Labor Units | 2023-12-01: 0.21; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-02-18 | 0% | Cum Actual Labor Units
C-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-02-18 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.43; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-02-18 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.43; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-02-18 | 0% | Cum Actual Labor Units
C-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-02-18 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.43; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oساخت قالب فرم | BG-01.Process Design.Die.Constraction | 2024-01-10 | 2024-02-18 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.43; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-DIE1020 | پايان ساخت قالب هاي مجموعه | BG-01.Process Design.Die.Constraction |  | 2024-06-26 | 0% | Cum Actual Labor Units
C-DIE1020 | پايان ساخت قالب هاي مجموعه | BG-01.Process Design.Die.Constraction |  | 2024-06-26 | 0% | Cum BL Project Labor Units
C-DIE1020 | پايان ساخت قالب هاي مجموعه | BG-01.Process Design.Die.Constraction |  | 2024-06-26 | 0% | Cum Remaining Labor Units
Die Validation |  |  | 2023-12-19 | 2024-06-29 | 0% | Cum Actual Labor Units
Die Validation |  |  | 2023-12-19 | 2024-06-29 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.42; 2024-01-01: 3.34; 2024-02-01: 6.69; 2024-03-01: 6.69; 2024-04-01: 6.69; 2024-05-01: 6.69; 2024-06-01: 7.94
Die Validation |  |  | 2023-12-19 | 2024-06-29 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.84; 2024-01-01: 2.93; 2024-02-01: 6.69; 2024-03-01: 6.69; 2024-04-01: 6.69; 2024-05-01: 6.69; 2024-06-01: 7.94
V-DIE1010 | سايلنسر کاتاليست دوم Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-01-24 | 2024-01-24 | 0% | Cum Actual Labor Units
V-DIE1010 | سايلنسر کاتاليست دوم Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-01-24 | 2024-01-24 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1010 | سايلنسر کاتاليست دوم Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-01-24 | 2024-01-24 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1011 | سايلنسر کاتاليست دوم Uصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-01-24 | 2024-01-24 | 0% | Cum Actual Labor Units
V-DIE1011 | سايلنسر کاتاليست دوم Uصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-01-24 | 2024-01-24 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1011 | سايلنسر کاتاليست دوم Uصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-01-24 | 2024-01-24 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1002 | شل کاتاليست اول Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-03 | 2024-02-03 | 0% | Cum Actual Labor Units
V-DIE1002 | شل کاتاليست اول Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-03 | 2024-02-03 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1002 | شل کاتاليست اول Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-03 | 2024-02-03 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1019 | صحه گذاري قالب هاي کاور حرارتي | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum Actual Labor Units
V-DIE1019 | صحه گذاري قالب هاي کاور حرارتي | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum BL Project Labor Units | 2024-06-01: 0.42
V-DIE1019 | صحه گذاري قالب هاي کاور حرارتي | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum Remaining Labor Units | 2024-06-01: 0.42
V-DIE1005 | صحه گذاري قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Validation | 2024-02-13 | 2024-02-13 | 0% | Cum Actual Labor Units
V-DIE1005 | صحه گذاري قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Validation | 2024-02-13 | 2024-02-13 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1005 | صحه گذاري قالب افزايش قطر دوسر شل کاتاليست اول | BG-01.Process Design.Die.Validation | 2024-02-13 | 2024-02-13 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1016 | صحه گذاري قالب ال سيل | BG-01.Process Design.Die.Validation | 2024-01-20 | 2024-01-20 | 0% | Cum Actual Labor Units
V-DIE1016 | صحه گذاري قالب ال سيل | BG-01.Process Design.Die.Validation | 2024-01-20 | 2024-01-20 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1016 | صحه گذاري قالب ال سيل | BG-01.Process Design.Die.Validation | 2024-01-20 | 2024-01-20 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1004 | صحه گذاري قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Validation | 2024-01-02 | 2024-01-02 | 0% | Cum Actual Labor Units
V-DIE1004 | صحه گذاري قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Validation | 2024-01-02 | 2024-01-02 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1004 | صحه گذاري قالب جازني مونوليت کاتاليست اول | BG-01.Process Design.Die.Validation | 2024-01-02 | 2024-01-02 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1012 | صحه گذاري قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-01-07 | 2024-01-07 | 0% | Cum Actual Labor Units
V-DIE1012 | صحه گذاري قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-01-07 | 2024-01-07 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1012 | صحه گذاري قالب درز جوش سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-01-07 | 2024-01-07 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1003 | صحه گذاري قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Validation | 2023-12-19 | 2023-12-19 | 0% | Cum Actual Labor Units
V-DIE1003 | صحه گذاري قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Validation | 2023-12-19 | 2023-12-19 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1003 | صحه گذاري قالب درز جوش کاتاليست اول | BG-01.Process Design.Die.Validation | 2023-12-19 | 2023-12-19 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1009 | صحه گذاري قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Actual Labor Units
V-DIE1009 | صحه گذاري قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1009 | صحه گذاري قالب فرم پله انتهايي بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1018 | صحه گذاري قالب هاي براکت ها | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum Actual Labor Units
V-DIE1018 | صحه گذاري قالب هاي براکت ها | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum BL Project Labor Units | 2024-06-01: 0.42
V-DIE1018 | صحه گذاري قالب هاي براکت ها | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum Remaining Labor Units | 2024-06-01: 0.42
V-DIE1017 | صحه گذاري قالب هاي پوسته ورودي و خروجي | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum Actual Labor Units
V-DIE1017 | صحه گذاري قالب هاي پوسته ورودي و خروجي | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum BL Project Labor Units | 2024-06-01: 0.42
V-DIE1017 | صحه گذاري قالب هاي پوسته ورودي و خروجي | BG-01.Process Design.Die.Validation | 2024-06-26 | 2024-06-29 | 0% | Cum Remaining Labor Units | 2024-06-01: 0.42
V-DIE1013 | صحه گذاري قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Actual Labor Units
V-DIE1013 | صحه گذاري قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1013 | صحه گذاري قالب پانچ لوله توري قطر 55 سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1008 | صحه گذاري قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Actual Labor Units
V-DIE1008 | صحه گذاري قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1008 | صحه گذاري قالب پانچ و دوربر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1006 | صحه گذاري قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Actual Labor Units
V-DIE1006 | صحه گذاري قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1006 | صحه گذاري قالب پولک بر بشقابي سايلنسر کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1007 | صحه گذاري قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Actual Labor Units
V-DIE1007 | صحه گذاري قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1007 | صحه گذاري قالب کشش بشقابي کاتاليست دوم | BG-01.Process Design.Die.Validation | 2024-02-14 | 2024-02-14 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1001 | صحه گذاري قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Validation | 2023-12-31 | 2023-12-31 | 0% | Cum Actual Labor Units
V-DIE1001 | صحه گذاري قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Validation | 2023-12-31 | 2023-12-31 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1001 | صحه گذاري قالب کوتر مونوليت کاتاليست اول | BG-01.Process Design.Die.Validation | 2023-12-31 | 2023-12-31 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum Actual Labor Units
V-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1014 | لوله توري قطر 55 کاتاليست دوم Uصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum Actual Labor Units
V-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1015 | لوله توري قطر 55 کاتاليست دوم Oصحه گذاري قالب فرم | BG-01.Process Design.Die.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-DIE1020 | پايان صحه گذاري قالب ها مجموعه | BG-01.Process Design.Die.Validation |  | 2024-06-29 | 0% | Cum Actual Labor Units
V-DIE1020 | پايان صحه گذاري قالب ها مجموعه | BG-01.Process Design.Die.Validation |  | 2024-06-29 | 0% | Cum BL Project Labor Units
V-DIE1020 | پايان صحه گذاري قالب ها مجموعه | BG-01.Process Design.Die.Validation |  | 2024-06-29 | 0% | Cum Remaining Labor Units
CF |  |  | 29-Nov-2023 A | 2024-05-01 | 4.26% | Cum Actual Labor Units |  |  |  |  | 0.01 | 4.67 | 4.67 | 4.67 | 4.67 | 4.67 | 4.67 | 4.67
CF |  |  | 29-Nov-2023 A | 2024-05-01 | 4.26% | Cum BL Project Labor Units |  |  |  |  | 0 | 3.21 | 8.44 | 11.7 | 16.95 | 19.04 | 22.07 | 22.07
CF |  |  | 29-Nov-2023 A | 2024-05-01 | 4.26% | Cum Remaining Labor Units | 2023-12-01: 2.27; 2024-01-01: 7.07; 2024-02-01: 11.16; 2024-03-01: 14.18; 2024-04-01: 16.65; 2024-05-01: 17.9; 2024-06-01: 17.9
CF Design |  |  | 29-Nov-2023 A | 2024-02-28 | 11.26% | Cum Actual Labor Units |  |  |  |  | 0.01 | 3.57 | 3.57 | 3.57 | 3.57 | 3.57 | 3.57 | 3.57
CF Design |  |  | 29-Nov-2023 A | 2024-02-28 | 11.26% | Cum BL Project Labor Units |  |  |  |  | 0 | 2.52 | 3.36 | 4.69 | 8.03 | 8.03 | 8.03 | 8.03
CF Design |  |  | 29-Nov-2023 A | 2024-02-28 | 11.26% | Cum Remaining Labor Units | 2023-12-01: 1.62; 2024-01-01: 1.78; 2024-02-01: 4.46; 2024-03-01: 4.46; 2024-04-01: 4.46; 2024-05-01: 4.46; 2024-06-01: 4.46
D-CF1011 | طراحي فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum Actual Labor Units
D-CF1011 | طراحي فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1011 | طراحي فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1008 | طراحي فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Design | 05-Dec-2023 A | 09-Dec-2023 A | 0% | Cum Actual Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1008 | طراحي فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Design | 05-Dec-2023 A | 09-Dec-2023 A | 0% | Cum BL Project Labor Units | 2024-02-01: 0.01; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1008 | طراحي فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Design | 05-Dec-2023 A | 09-Dec-2023 A | 0% | Cum Remaining Labor Units
D-CF1009 | طراحي فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Design | 12-Dec-2023 A | 16-Dec-2023 A | 0% | Cum Actual Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1009 | طراحي فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Design | 12-Dec-2023 A | 16-Dec-2023 A | 0% | Cum BL Project Labor Units | 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1009 | طراحي فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Design | 12-Dec-2023 A | 16-Dec-2023 A | 0% | Cum Remaining Labor Units
D-CF1005 | طراحي فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 04-Dec-2023 A | 09-Dec-2023 A | 0% | Cum Actual Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1005 | طراحي فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 04-Dec-2023 A | 09-Dec-2023 A | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1005 | طراحي فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 04-Dec-2023 A | 09-Dec-2023 A | 0% | Cum Remaining Labor Units
D-CF1007 | طراحي فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Design | 30-Nov-2023 A | 04-Dec-2023 A | 0% | Cum Actual Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1007 | طراحي فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Design | 30-Nov-2023 A | 04-Dec-2023 A | 0% | Cum BL Project Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1007 | طراحي فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Design | 30-Nov-2023 A | 04-Dec-2023 A | 0% | Cum Remaining Labor Units
D-CF1006 | طراحي فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Design | 2024-02-03 | 2024-02-04 | 0% | Cum Actual Labor Units
D-CF1006 | طراحي فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Design | 2024-02-03 | 2024-02-04 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.02; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1006 | طراحي فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Design | 2024-02-03 | 2024-02-04 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1012 | طراحي فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum Actual Labor Units
D-CF1012 | طراحي فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1012 | طراحي فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1010 | طراحي فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum Actual Labor Units
D-CF1010 | طراحي فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1010 | طراحي فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Design | 2024-02-26 | 2024-02-28 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1001 | طراحي گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Design | 29-Nov-2023 A | 09-Dec-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.01 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-CF1001 | طراحي گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Design | 29-Nov-2023 A | 09-Dec-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-CF1001 | طراحي گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Design | 29-Nov-2023 A | 09-Dec-2023 A | 100% | Cum Remaining Labor Units
D-CF1004 | طراحي گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Design | 2023-12-27 | 2024-01-01 | 0% | Cum Actual Labor Units
D-CF1004 | طراحي گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Design | 2023-12-27 | 2024-01-01 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.51; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1004 | طراحي گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Design | 2023-12-27 | 2024-01-01 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.5; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1002 | طراحي گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Design | 10-Dec-2023 A | 2023-12-20 | 35.09% | Cum Actual Labor Units | 2023-12-01: 0.22; 2024-01-01: 0.22; 2024-02-01: 0.22; 2024-03-01: 0.22; 2024-04-01: 0.22; 2024-05-01: 0.22; 2024-06-01: 0.22
D-CF1002 | طراحي گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Design | 10-Dec-2023 A | 2023-12-20 | 35.09% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1002 | طراحي گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Design | 10-Dec-2023 A | 2023-12-20 | 35.09% | Cum Remaining Labor Units | 2023-12-01: 0.45; 2024-01-01: 0.45; 2024-02-01: 0.45; 2024-03-01: 0.45; 2024-04-01: 0.45; 2024-05-01: 0.45; 2024-06-01: 0.45
D-CF1003 | طراحي گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Design | 2023-12-23 | 2023-12-26 | 0% | Cum Actual Labor Units
D-CF1003 | طراحي گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Design | 2023-12-23 | 2023-12-26 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1003 | طراحي گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Design | 2023-12-23 | 2023-12-26 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.67; 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-CF1013 | پايان طراحي فيکسچر هاي کنترلي | BG-01.Process Design.CF.Design |  | 2024-02-28 | 0% | Cum Actual Labor Units
D-CF1013 | پايان طراحي فيکسچر هاي کنترلي | BG-01.Process Design.CF.Design |  | 2024-02-28 | 0% | Cum BL Project Labor Units
D-CF1013 | پايان طراحي فيکسچر هاي کنترلي | BG-01.Process Design.CF.Design |  | 2024-02-28 | 0% | Cum Remaining Labor Units
CF Constraction |  |  | 04-Dec-2023 A | 2024-04-30 | 0.4% | Cum Actual Labor Units | 2023-12-01: 1.1; 2024-01-01: 1.1; 2024-02-01: 1.1; 2024-03-01: 1.1; 2024-04-01: 1.1; 2024-05-01: 1.1; 2024-06-01: 1.1
CF Constraction |  |  | 04-Dec-2023 A | 2024-04-30 | 0.4% | Cum BL Project Labor Units | 2023-12-01: 0.69; 2024-01-01: 3.41; 2024-02-01: 4.92; 2024-03-01: 5.99; 2024-04-01: 8.09; 2024-05-01: 9.03; 2024-06-01: 9.03
CF Constraction |  |  | 04-Dec-2023 A | 2024-04-30 | 0.4% | Cum Remaining Labor Units | 2023-12-01: 0.65; 2024-01-01: 3.2; 2024-02-01: 4.61; 2024-03-01: 6.79; 2024-04-01: 8.43; 2024-05-01: 8.43; 2024-06-01: 8.43
C-CF1005 | ساخت فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-01-30 | 0% | Cum Actual Labor Units | 2023-12-01: 0.36; 2024-01-01: 0.36; 2024-02-01: 0.36; 2024-03-01: 0.36; 2024-04-01: 0.36; 2024-05-01: 0.36; 2024-06-01: 0.36
C-CF1005 | ساخت فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-01-30 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.4; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1005 | ساخت فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-01-30 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.4; 2024-02-01: 0.4; 2024-03-01: 0.4; 2024-04-01: 0.4; 2024-05-01: 0.4; 2024-06-01: 0.4
C-CF1004 | ساخت گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2024-01-02 | 2024-01-29 | 0% | Cum Actual Labor Units
C-CF1004 | ساخت گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2024-01-02 | 2024-01-29 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1004 | ساخت گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2024-01-02 | 2024-01-29 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1011 | ساخت فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum Actual Labor Units
C-CF1011 | ساخت فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.1; 2024-04-01: 0.51; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1011 | ساخت فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.34; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1008 | ساخت فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-03-10 | 0% | Cum Actual Labor Units | 2023-12-01: 0.49; 2024-01-01: 0.49; 2024-02-01: 0.49; 2024-03-01: 0.49; 2024-04-01: 0.49; 2024-05-01: 0.49; 2024-06-01: 0.49
C-CF1008 | ساخت فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-03-10 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.26; 2024-04-01: 0.7; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1008 | ساخت فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-03-10 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.08; 2024-03-01: 0.26; 2024-04-01: 0.26; 2024-05-01: 0.26; 2024-06-01: 0.26
C-CF1009 | ساخت فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 16-Dec-2023 A | 2024-04-22 | 0% | Cum Actual Labor Units | 2023-12-01: 0.05; 2024-01-01: 0.05; 2024-02-01: 0.05; 2024-03-01: 0.05; 2024-04-01: 0.05; 2024-05-01: 0.05; 2024-06-01: 0.05
C-CF1009 | ساخت فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 16-Dec-2023 A | 2024-04-22 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.17; 2024-04-01: 0.58; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1009 | ساخت فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 16-Dec-2023 A | 2024-04-22 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.07; 2024-03-01: 0.41; 2024-04-01: 0.7; 2024-05-01: 0.7; 2024-06-01: 0.7
C-CF1007 | ساخت فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 04-Dec-2023 A | 2024-04-08 | 0% | Cum Actual Labor Units
C-CF1007 | ساخت فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 04-Dec-2023 A | 2024-04-08 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.54; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1007 | ساخت فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 04-Dec-2023 A | 2024-04-08 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.65; 2024-03-01: 1.15; 2024-04-01: 1.25; 2024-05-01: 1.25; 2024-06-01: 1.25
C-CF1006 | ساخت فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 2024-02-05 | 2024-03-05 | 0% | Cum Actual Labor Units
C-CF1006 | ساخت فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 2024-02-05 | 2024-03-05 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.62; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1006 | ساخت فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 2024-02-05 | 2024-03-05 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.62; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1012 | ساخت فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum Actual Labor Units
C-CF1012 | ساخت فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.1; 2024-04-01: 0.51; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1012 | ساخت فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.34; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1010 | ساخت فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum Actual Labor Units
C-CF1010 | ساخت فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.1; 2024-04-01: 0.51; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1010 | ساخت فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Constraction | 2024-03-02 | 2024-04-30 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.34; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1001 | ساخت گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-01-09 | 4.78% | Cum Actual Labor Units | 2023-12-01: 0.21; 2024-01-01: 0.21; 2024-02-01: 0.21; 2024-03-01: 0.21; 2024-04-01: 0.21; 2024-05-01: 0.21; 2024-06-01: 0.21
C-CF1001 | ساخت گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-01-09 | 4.78% | Cum BL Project Labor Units | 2023-12-01: 0.34; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1001 | ساخت گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Constraction | 09-Dec-2023 A | 2024-01-09 | 4.78% | Cum Remaining Labor Units | 2023-12-01: 0.31; 2024-01-01: 0.55; 2024-02-01: 0.55; 2024-03-01: 0.55; 2024-04-01: 0.55; 2024-05-01: 0.55; 2024-06-01: 0.55
C-CF1002 | ساخت گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2023-12-23 | 2024-01-21 | 0% | Cum Actual Labor Units
C-CF1002 | ساخت گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2023-12-23 | 2024-01-21 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.24; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1002 | ساخت گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2023-12-23 | 2024-01-21 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.24; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1003 | ساخت گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2023-12-27 | 2024-01-24 | 0% | Cum Actual Labor Units
C-CF1003 | ساخت گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2023-12-27 | 2024-01-24 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.11; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1003 | ساخت گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Constraction | 2023-12-27 | 2024-01-24 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.11; 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-CF1013 | پايان ساخت فيکسچر هاي کنترلي | BG-01.Process Design.CF.Constraction |  | 2024-04-30 | 0% | Cum Actual Labor Units
C-CF1013 | پايان ساخت فيکسچر هاي کنترلي | BG-01.Process Design.CF.Constraction |  | 2024-04-30 | 0% | Cum BL Project Labor Units
C-CF1013 | پايان ساخت فيکسچر هاي کنترلي | BG-01.Process Design.CF.Constraction |  | 2024-04-30 | 0% | Cum Remaining Labor Units
CF Validation |  |  | 2024-01-10 | 2024-05-01 | 0% | Cum Actual Labor Units
CF Validation |  |  | 2024-01-10 | 2024-05-01 | 0% | Cum BL Project Labor Units | 2024-01-01: 1.67; 2024-02-01: 2.09; 2024-03-01: 2.93; 2024-04-01: 2.93; 2024-05-01: 5.02; 2024-06-01: 5.02
CF Validation |  |  | 2024-01-10 | 2024-05-01 | 0% | Cum Remaining Labor Units | 2024-01-01: 2.09; 2024-02-01: 2.09; 2024-03-01: 2.93; 2024-04-01: 3.76; 2024-05-01: 5.02; 2024-06-01: 5.02
V-CF1011 | صحه گذاري فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum Actual Labor Units
V-CF1011 | صحه گذاري فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum BL Project Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1011 | صحه گذاري فيکسچر تست نشتي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum Remaining Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1008 | صحه گذاري فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-03-11 | 2024-03-11 | 0% | Cum Actual Labor Units
V-CF1008 | صحه گذاري فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-03-11 | 2024-03-11 | 0% | Cum BL Project Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1008 | صحه گذاري فيکسچر تست نشتي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-03-11 | 2024-03-11 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1009 | صحه گذاري فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-04-24 | 2024-04-24 | 0% | Cum Actual Labor Units
V-CF1009 | صحه گذاري فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-04-24 | 2024-04-24 | 0% | Cum BL Project Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1009 | صحه گذاري فيکسچر تست نشتي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-04-24 | 2024-04-24 | 0% | Cum Remaining Labor Units | 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1005 | صحه گذاري فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-01-31 | 2024-01-31 | 0% | Cum Actual Labor Units
V-CF1005 | صحه گذاري فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-01-31 | 2024-01-31 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1005 | صحه گذاري فيکسچر کنترل آويز هاي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-01-31 | 2024-01-31 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1007 | صحه گذاري فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-04-09 | 2024-04-09 | 0% | Cum Actual Labor Units
V-CF1007 | صحه گذاري فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-04-09 | 2024-04-09 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1007 | صحه گذاري فيکسچر کنترل آويز هاي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-04-09 | 2024-04-09 | 0% | Cum Remaining Labor Units | 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1006 | صحه گذاري فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-03-06 | 2024-03-06 | 0% | Cum Actual Labor Units
V-CF1006 | صحه گذاري فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-03-06 | 2024-03-06 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1006 | صحه گذاري فيکسچر کنترل خم لوله خروجي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-03-06 | 2024-03-06 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1012 | صحه گذاري فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum Actual Labor Units
V-CF1012 | صحه گذاري فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum BL Project Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1012 | صحه گذاري فيکسچر کنترل نهايي لوله فلکسيبل دار | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum Remaining Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1010 | صحه گذاري فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum Actual Labor Units
V-CF1010 | صحه گذاري فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum BL Project Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1010 | صحه گذاري فيکسچر کنترل نهايي کاتاليست دوم | BG-01.Process Design.CF.Validation | 2024-05-01 | 2024-05-01 | 0% | Cum Remaining Labor Units | 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1001 | صحه گذاري گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-10 | 2024-01-10 | 0% | Cum Actual Labor Units
V-CF1001 | صحه گذاري گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-10 | 2024-01-10 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1001 | صحه گذاري گيج کنترل فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-10 | 2024-01-10 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1004 | صحه گذاري گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-30 | 2024-01-30 | 0% | Cum Actual Labor Units
V-CF1004 | صحه گذاري گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-30 | 2024-01-30 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1004 | صحه گذاري گيچ کنترل تعامد فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-30 | 2024-01-30 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1002 | صحه گذاري گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-22 | 2024-01-22 | 0% | Cum Actual Labor Units
V-CF1002 | صحه گذاري گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-22 | 2024-01-22 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1002 | صحه گذاري گيچ کنترل تعامد فلنچ ورودي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-22 | 2024-01-22 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1003 | صحه گذاري گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-27 | 2024-01-27 | 0% | Cum Actual Labor Units
V-CF1003 | صحه گذاري گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-27 | 2024-01-27 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1003 | صحه گذاري گيچ کنترل فلنچ خروجي کاتاليست اول | BG-01.Process Design.CF.Validation | 2024-01-27 | 2024-01-27 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-CF1013 | پايان تست و صحه گذاري فيکسچر هاي کنترلي | BG-01.Process Design.CF.Validation |  | 2024-05-01 | 0% | Cum Actual Labor Units
V-CF1013 | پايان تست و صحه گذاري فيکسچر هاي کنترلي | BG-01.Process Design.CF.Validation |  | 2024-05-01 | 0% | Cum BL Project Labor Units
V-CF1013 | پايان تست و صحه گذاري فيکسچر هاي کنترلي | BG-01.Process Design.CF.Validation |  | 2024-05-01 | 0% | Cum Remaining Labor Units
PF |  |  | 30-Oct-2023 A | 2024-03-10 | 22.7% | Cum Actual Labor Units |  |  |  | 0.92 | 6.89 | 8.19 | 8.19 | 8.19 | 8.19 | 8.19 | 8.19 | 8.19
PF |  |  | 30-Oct-2023 A | 2024-03-10 | 22.7% | Cum BL Project Labor Units |  |  |  | 0.65 | 6.36 | 9.64 | 21.28 | 29.98 | 34.95 | 34.95 | 34.95 | 34.95
PF |  |  | 30-Oct-2023 A | 2024-03-10 | 22.7% | Cum Remaining Labor Units | 2023-12-01: 1.65; 2024-01-01: 13.08; 2024-02-01: 22.86; 2024-03-01: 26.76; 2024-04-01: 26.76; 2024-05-01: 26.76; 2024-06-01: 26.76
PF Design |  |  | 30-Oct-2023 A | 2024-02-25 | 36.84% | Cum Actual Labor Units |  |  |  | 0.92 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68
PF Design |  |  | 30-Oct-2023 A | 2024-02-25 | 36.84% | Cum BL Project Labor Units |  |  |  | 0.65 | 4.68 | 4.68 | 9.36 | 12.71 | 12.71 | 12.71 | 12.71 | 12.71
PF Design |  |  | 30-Oct-2023 A | 2024-02-25 | 36.84% | Cum Remaining Labor Units | 2024-01-01: 4.68; 2024-02-01: 8.03; 2024-03-01: 8.03; 2024-04-01: 8.03; 2024-05-01: 8.03; 2024-06-01: 8.03
D-P1007 | طراحي فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Design | 08-Nov-2023 A | 28-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1007 | طراحي فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Design | 08-Nov-2023 A | 28-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1007 | طراحي فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Design | 08-Nov-2023 A | 28-Nov-2023 A | 100% | Cum Remaining Labor Units
D-P1003 | طراحي فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 05-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  | 0.18 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1003 | طراحي فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 05-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  | 0.18 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1003 | طراحي فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 05-Nov-2023 A | 100% | Cum Remaining Labor Units
D-P1001 | طراحي فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 01-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  | 0.34 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1001 | طراحي فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 01-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  | 0.18 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1001 | طراحي فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 01-Nov-2023 A | 100% | Cum Remaining Labor Units
D-P1017 | طراحي فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Design | 2024-02-13 | 2024-02-17 | 0% | Cum Actual Labor Units
D-P1017 | طراحي فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Design | 2024-02-13 | 2024-02-17 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1017 | طراحي فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Design | 2024-02-13 | 2024-02-17 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1012 | طراحي فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-20 | 2024-01-23 | 0% | Cum Actual Labor Units
D-P1012 | طراحي فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-20 | 2024-01-23 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1012 | طراحي فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-20 | 2024-01-23 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1011 | طراحي فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-17 | 2024-01-17 | 0% | Cum Actual Labor Units
D-P1011 | طراحي فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-17 | 2024-01-17 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1011 | طراحي فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-17 | 2024-01-17 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1018 | طراحي فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-18 | 2024-02-21 | 0% | Cum Actual Labor Units
D-P1018 | طراحي فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-18 | 2024-02-21 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1018 | طراحي فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-18 | 2024-02-21 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1004 | طراحي فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 07-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  | 0.22 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1004 | طراحي فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 07-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  | 0.12 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1004 | طراحي فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 07-Nov-2023 A | 100% | Cum Remaining Labor Units
D-P1014 | طراحي فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-01-28 | 2024-01-31 | 0% | Cum Actual Labor Units
D-P1014 | طراحي فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-01-28 | 2024-01-31 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1014 | طراحي فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-01-28 | 2024-01-31 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1016 | طراحي فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-11 | 2024-02-12 | 0% | Cum Actual Labor Units
D-P1016 | طراحي فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-11 | 2024-02-12 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1016 | طراحي فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-11 | 2024-02-12 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1013 | طراحي فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-24 | 2024-01-27 | 0% | Cum Actual Labor Units
D-P1013 | طراحي فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-24 | 2024-01-27 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1013 | طراحي فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-24 | 2024-01-27 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1005 | طراحي فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Design | 05-Nov-2023 A | 08-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1005 | طراحي فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Design | 05-Nov-2023 A | 08-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1005 | طراحي فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Design | 05-Nov-2023 A | 08-Nov-2023 A | 100% | Cum Remaining Labor Units
D-P1015 | طراحي فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-05 | 2024-02-10 | 0% | Cum Actual Labor Units
D-P1015 | طراحي فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-05 | 2024-02-10 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1015 | طراحي فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-05 | 2024-02-10 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1002 | طراحي فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 05-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  | 0.18 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1002 | طراحي فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 05-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  | 0.18 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1002 | طراحي فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Design | 30-Oct-2023 A | 05-Nov-2023 A | 100% | Cum Remaining Labor Units
D-P1009 | طراحي فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-03 | 2024-01-07 | 0% | Cum Actual Labor Units
D-P1009 | طراحي فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-03 | 2024-01-07 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1009 | طراحي فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-03 | 2024-01-07 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1006 | طراحي فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Design | 05-Nov-2023 A | 08-Nov-2023 A | 100% | Cum Actual Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1006 | طراحي فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Design | 05-Nov-2023 A | 08-Nov-2023 A | 100% | Cum BL Project Labor Units |  |  |  |  | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
D-P1006 | طراحي فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Design | 05-Nov-2023 A | 08-Nov-2023 A | 100% | Cum Remaining Labor Units
D-P1019 | طراحي فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-24 | 2024-02-25 | 0% | Cum Actual Labor Units
D-P1019 | طراحي فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-24 | 2024-02-25 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1019 | طراحي فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Design | 2024-02-24 | 2024-02-25 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1008 | طراحي فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-02 | 2024-01-02 | 0% | Cum Actual Labor Units
D-P1008 | طراحي فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-02 | 2024-01-02 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1008 | طراحي فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-02 | 2024-01-02 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1010 | طراحي فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-08 | 2024-01-16 | 0% | Cum Actual Labor Units
D-P1010 | طراحي فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-08 | 2024-01-16 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1010 | طراحي فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Design | 2024-01-08 | 2024-01-16 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.67; 2024-02-01: 0.67; 2024-03-01: 0.67; 2024-04-01: 0.67; 2024-05-01: 0.67; 2024-06-01: 0.67
D-P1020 | پايان طراحي فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Design |  | 2024-02-25 | 0% | Cum Actual Labor Units
D-P1020 | پايان طراحي فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Design |  | 2024-02-25 | 0% | Cum BL Project Labor Units
D-P1020 | پايان طراحي فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Design |  | 2024-02-25 | 0% | Cum Remaining Labor Units
PF Constraction |  |  | 04-Nov-2023 A | 2024-03-09 | 22.73% | Cum Actual Labor Units |  |  |  |  | 2.2 | 3.51 | 3.51 | 3.51 | 3.51 | 3.51 | 3.51 | 3.51
PF Constraction |  |  | 04-Nov-2023 A | 2024-03-09 | 22.73% | Cum BL Project Labor Units |  |  |  |  | 1.68 | 4.13 | 8.16 | 12.25 | 14.3 | 14.3 | 14.3 | 14.3
PF Constraction |  |  | 04-Nov-2023 A | 2024-03-09 | 22.73% | Cum Remaining Labor Units | 2023-12-01: 0.81; 2024-01-01: 4.63; 2024-02-01: 9.82; 2024-03-01: 10.79; 2024-04-01: 10.79; 2024-05-01: 10.79; 2024-06-01: 10.79
C-P1007 | ساخت فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Constraction | 28-Nov-2023 A | 2024-01-22 | 42.58% | Cum Actual Labor Units |  |  |  |  | 0.01 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18
C-P1007 | ساخت فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Constraction | 28-Nov-2023 A | 2024-01-22 | 42.58% | Cum BL Project Labor Units |  |  |  |  | 0.02 | 0.53 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-P1007 | ساخت فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Constraction | 28-Nov-2023 A | 2024-01-22 | 42.58% | Cum Remaining Labor Units | 2023-12-01: 0.21; 2024-01-01: 0.57; 2024-02-01: 0.57; 2024-03-01: 0.57; 2024-04-01: 0.57; 2024-05-01: 0.57; 2024-06-01: 0.57
C-P1003 | ساخت فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Constraction | 05-Nov-2023 A | 2024-01-03 | 79.62% | Cum Actual Labor Units |  |  |  |  | 0.3 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52
C-P1003 | ساخت فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Constraction | 05-Nov-2023 A | 2024-01-03 | 79.62% | Cum BL Project Labor Units |  |  |  |  | 0.35 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-P1003 | ساخت فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Constraction | 05-Nov-2023 A | 2024-01-03 | 79.62% | Cum Remaining Labor Units | 2023-12-01: 0.17; 2024-01-01: 0.23; 2024-02-01: 0.23; 2024-03-01: 0.23; 2024-04-01: 0.23; 2024-05-01: 0.23; 2024-06-01: 0.23
C-P1001 | ساخت فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Constraction | 04-Nov-2023 A | 29-Nov-2023 A | 97.04% | Cum Actual Labor Units |  |  |  |  | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-P1001 | ساخت فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Constraction | 04-Nov-2023 A | 29-Nov-2023 A | 97.04% | Cum BL Project Labor Units |  |  |  |  | 0.42 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-P1001 | ساخت فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Constraction | 04-Nov-2023 A | 29-Nov-2023 A | 97.04% | Cum Remaining Labor Units
C-P1017 | ساخت فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Constraction | 2024-02-18 | 2024-02-28 | 0% | Cum Actual Labor Units
C-P1017 | ساخت فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Constraction | 2024-02-18 | 2024-02-28 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.51; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1017 | ساخت فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Constraction | 2024-02-18 | 2024-02-28 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1012 | ساخت فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-24 | 2024-03-02 | 0% | Cum Actual Labor Units
C-P1012 | ساخت فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-24 | 2024-03-02 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.17; 2024-02-01: 0.73; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1012 | ساخت فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-24 | 2024-03-02 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.17; 2024-02-01: 0.72; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1011 | ساخت فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-20 | 2024-01-24 | 0% | Cum Actual Labor Units
C-P1011 | ساخت فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-20 | 2024-01-24 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1011 | ساخت فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-20 | 2024-01-24 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1018 | ساخت فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-24 | 2024-03-04 | 0% | Cum Actual Labor Units
C-P1018 | ساخت فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-24 | 2024-03-04 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.19; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1018 | ساخت فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-24 | 2024-03-04 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.47; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1004 | ساخت فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Constraction | 07-Nov-2023 A | 2024-03-04 | 35% | Cum Actual Labor Units |  |  |  |  | 0.14 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
C-P1004 | ساخت فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Constraction | 07-Nov-2023 A | 2024-03-04 | 35% | Cum BL Project Labor Units |  |  |  |  | 0.15 | 0.34 | 0.55 | 0.73 | 0.75 | 0.75 | 0.75 | 0.75
C-P1004 | ساخت فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Constraction | 07-Nov-2023 A | 2024-03-04 | 35% | Cum Remaining Labor Units | 2023-12-01: 0.08; 2024-01-01: 0.29; 2024-02-01: 0.47; 2024-03-01: 0.5; 2024-04-01: 0.5; 2024-05-01: 0.5; 2024-06-01: 0.5
C-P1014 | ساخت فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-03 | 2024-02-18 | 0% | Cum Actual Labor Units
C-P1014 | ساخت فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-03 | 2024-02-18 | 0% | Cum BL Project Labor Units | 2024-01-01: 0; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1014 | ساخت فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-03 | 2024-02-18 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1016 | ساخت فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-13 | 2024-02-28 | 0% | Cum Actual Labor Units
C-P1016 | ساخت فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-13 | 2024-02-28 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.57; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1016 | ساخت فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-13 | 2024-02-28 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1013 | ساخت فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-28 | 2024-02-26 | 0% | Cum Actual Labor Units
C-P1013 | ساخت فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-28 | 2024-02-26 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.14; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1013 | ساخت فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-28 | 2024-02-26 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.14; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1005 | ساخت فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Constraction | 08-Nov-2023 A | 2024-01-08 | 59.69% | Cum Actual Labor Units |  |  |  |  | 0.27 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51
C-P1005 | ساخت فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Constraction | 08-Nov-2023 A | 2024-01-08 | 59.69% | Cum BL Project Labor Units |  |  |  |  | 0.24 | 0.59 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-P1005 | ساخت فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Constraction | 08-Nov-2023 A | 2024-01-08 | 59.69% | Cum Remaining Labor Units | 2023-12-01: 0.14; 2024-01-01: 0.24; 2024-02-01: 0.24; 2024-03-01: 0.24; 2024-04-01: 0.24; 2024-05-01: 0.24; 2024-06-01: 0.24
C-P1015 | ساخت فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-11 | 2024-03-04 | 0% | Cum Actual Labor Units
C-P1015 | ساخت فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-11 | 2024-03-04 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.49; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1015 | ساخت فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-11 | 2024-03-04 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.62; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1002 | ساخت فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Constraction | 05-Nov-2023 A | 2023-12-25 | 66.07% | Cum Actual Labor Units |  |  |  |  | 0.39 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
C-P1002 | ساخت فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Constraction | 05-Nov-2023 A | 2023-12-25 | 66.07% | Cum BL Project Labor Units |  |  |  |  | 0.29 | 0.64 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-P1002 | ساخت فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Constraction | 05-Nov-2023 A | 2023-12-25 | 66.07% | Cum Remaining Labor Units | 2023-12-01: 0.08; 2024-01-01: 0.08; 2024-02-01: 0.08; 2024-03-01: 0.08; 2024-04-01: 0.08; 2024-05-01: 0.08; 2024-06-01: 0.08
C-P1009 | ساخت فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-08 | 2024-01-29 | 0% | Cum Actual Labor Units
C-P1009 | ساخت فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-08 | 2024-01-29 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1009 | ساخت فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-08 | 2024-01-29 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1006 | ساخت فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Constraction | 08-Nov-2023 A | 2024-01-01 | 51.95% | Cum Actual Labor Units |  |  |  |  | 0.33 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61
C-P1006 | ساخت فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Constraction | 08-Nov-2023 A | 2024-01-01 | 51.95% | Cum BL Project Labor Units |  |  |  |  | 0.21 | 0.52 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
C-P1006 | ساخت فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Constraction | 08-Nov-2023 A | 2024-01-01 | 51.95% | Cum Remaining Labor Units | 2023-12-01: 0.13; 2024-01-01: 0.14; 2024-02-01: 0.14; 2024-03-01: 0.14; 2024-04-01: 0.14; 2024-05-01: 0.14; 2024-06-01: 0.14
C-P1019 | ساخت فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-26 | 2024-03-09 | 0% | Cum Actual Labor Units
C-P1019 | ساخت فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-26 | 2024-03-09 | 0% | Cum BL Project Labor Units | 2024-02-01: 0; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1019 | ساخت فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Constraction | 2024-02-26 | 2024-03-09 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.25; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1008 | ساخت فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-03 | 2024-01-17 | 0% | Cum Actual Labor Units
C-P1008 | ساخت فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-03 | 2024-01-17 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1008 | ساخت فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-03 | 2024-01-17 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.75; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1010 | ساخت فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-17 | 2024-02-07 | 0% | Cum Actual Labor Units
C-P1010 | ساخت فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-17 | 2024-02-07 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.52; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1010 | ساخت فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Constraction | 2024-01-17 | 2024-02-07 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.52; 2024-02-01: 0.75; 2024-03-01: 0.75; 2024-04-01: 0.75; 2024-05-01: 0.75; 2024-06-01: 0.75
C-P1020 | پايان ساخت فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Constraction |  | 2024-03-09 | 0% | Cum Actual Labor Units
C-P1020 | پايان ساخت فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Constraction |  | 2024-03-09 | 0% | Cum BL Project Labor Units
C-P1020 | پايان ساخت فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Constraction |  | 2024-03-09 | 0% | Cum Remaining Labor Units
PF Validation |  |  | 2023-12-19 | 2024-03-10 | 0% | Cum Actual Labor Units
PF Validation |  |  | 2023-12-19 | 2024-03-10 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.84; 2024-01-01: 3.76; 2024-02-01: 5.02; 2024-03-01: 7.94; 2024-04-01: 7.94; 2024-05-01: 7.94; 2024-06-01: 7.94
PF Validation |  |  | 2023-12-19 | 2024-03-10 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.84; 2024-01-01: 3.76; 2024-02-01: 5.02; 2024-03-01: 7.94; 2024-04-01: 7.94; 2024-05-01: 7.94; 2024-06-01: 7.94
V-P1007 | صحه گذاري فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-23 | 2024-01-23 | 0% | Cum Actual Labor Units
V-P1007 | صحه گذاري فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-23 | 2024-01-23 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1007 | صحه گذاري فيکسچر براکت بالايي و پائيني به مجموعه کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-23 | 2024-01-23 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1003 | صحه گذاري فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-06 | 2024-01-06 | 0% | Cum Actual Labor Units
V-P1003 | صحه گذاري فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-06 | 2024-01-06 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1003 | صحه گذاري فيکسچر درز جوش پوسته هاي خروجي کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-06 | 2024-01-06 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1001 | صحه گذاري فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Validation | 2023-12-19 | 2023-12-19 | 0% | Cum Actual Labor Units
V-P1001 | صحه گذاري فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Validation | 2023-12-19 | 2023-12-19 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1001 | صحه گذاري فيکسچر درز جوش پوسته هاي ورودي کاتاليست اول | BG-01.Process Design.PF.Validation | 2023-12-19 | 2023-12-19 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1017 | صحه گذاري فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Validation | 2024-03-02 | 2024-03-02 | 0% | Cum Actual Labor Units
V-P1017 | صحه گذاري فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Validation | 2024-03-02 | 2024-03-02 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1017 | صحه گذاري فيکسچر دورجوش فلنچ به لوله مشترک | BG-01.Process Design.PF.Validation | 2024-03-02 | 2024-03-02 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1012 | صحه گذاري فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-03-03 | 2024-03-03 | 0% | Cum Actual Labor Units
V-P1012 | صحه گذاري فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-03-03 | 2024-03-03 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1012 | صحه گذاري فيکسچر دورجوش کاسه اي ورودي و خروجي به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-03-03 | 2024-03-03 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1011 | صحه گذاري فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-27 | 2024-01-27 | 0% | Cum Actual Labor Units
V-P1011 | صحه گذاري فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-27 | 2024-01-27 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1011 | صحه گذاري فيکسچر دورجوش کاسه اي ورودي و خروجي به کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-27 | 2024-01-27 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1018 | صحه گذاري فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum Actual Labor Units
V-P1018 | صحه گذاري فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1018 | صحه گذاري فيکسچر سوراخکاري محل مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1004 | صحه گذاري فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum Actual Labor Units
V-P1004 | صحه گذاري فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1004 | صحه گذاري فيکسچر مونتاژ آويز ها به مجموعه کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1014 | صحه گذاري فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum Actual Labor Units
V-P1014 | صحه گذاري فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1014 | صحه گذاري فيکسچر مونتاژ آويز و قلاب آويز به مجموعه فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-02-19 | 2024-02-19 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1016 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-02 | 2024-03-02 | 0% | Cum Actual Labor Units
V-P1016 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-02 | 2024-03-02 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1016 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به لوله خروجي لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-02 | 2024-03-02 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1013 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-02-27 | 2024-02-27 | 0% | Cum Actual Labor Units
V-P1013 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-02-27 | 2024-02-27 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1013 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به لوله خروجي و دورجوش دستي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-02-27 | 2024-02-27 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1005 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-09 | 2024-01-09 | 0% | Cum Actual Labor Units
V-P1005 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-09 | 2024-01-09 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1005 | صحه گذاري فيکسچر مونتاژ فلنچ خروجي به کاسه اي خروجي کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-09 | 2024-01-09 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1015 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum Actual Labor Units
V-P1015 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1015 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به لوله ورودي لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-05 | 2024-03-05 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1002 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Validation | 2023-12-26 | 2023-12-26 | 0% | Cum Actual Labor Units
V-P1002 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Validation | 2023-12-26 | 2023-12-26 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1002 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به کاسه اي ورودي کاتاليست اول | BG-01.Process Design.PF.Validation | 2023-12-26 | 2023-12-26 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.42; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1009 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-30 | 2024-01-30 | 0% | Cum Actual Labor Units
V-P1009 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-30 | 2024-01-30 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1009 | صحه گذاري فيکسچر مونتاژ فلنچ ورودي به کاسه اي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-30 | 2024-01-30 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1006 | صحه گذاري فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-02 | 2024-01-02 | 0% | Cum Actual Labor Units
V-P1006 | صحه گذاري فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-02 | 2024-01-02 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1006 | صحه گذاري فيکسچر مونتاژ مجموعه ورودي و خروجي به کاتاباکس کاتاليست اول | BG-01.Process Design.PF.Validation | 2024-01-02 | 2024-01-02 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1019 | صحه گذاري فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-10 | 2024-03-10 | 0% | Cum Actual Labor Units
V-P1019 | صحه گذاري فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-10 | 2024-03-10 | 0% | Cum BL Project Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1019 | صحه گذاري فيکسچر مونتاژ و دورجوش مهره سنسور لوله فلکسيبل دار | BG-01.Process Design.PF.Validation | 2024-03-10 | 2024-03-10 | 0% | Cum Remaining Labor Units | 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1008 | صحه گذاري فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-20 | 2024-01-20 | 0% | Cum Actual Labor Units
V-P1008 | صحه گذاري فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-20 | 2024-01-20 | 0% | Cum BL Project Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1008 | صحه گذاري فيکسچر مونتاژ پيچ به فلنچ ورودي کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-01-20 | 2024-01-20 | 0% | Cum Remaining Labor Units | 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1010 | صحه گذاري فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-02-10 | 2024-02-10 | 0% | Cum Actual Labor Units
V-P1010 | صحه گذاري فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-02-10 | 2024-02-10 | 0% | Cum BL Project Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1010 | صحه گذاري فيکسچر مونتاژ کاسه اي ورودي و خروجي و لوله پانچ به سايلنسر کاتاليست دوم | BG-01.Process Design.PF.Validation | 2024-02-10 | 2024-02-10 | 0% | Cum Remaining Labor Units | 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
V-P1020 | پايان تست و صحه گذاري فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Validation |  | 2024-03-10 | 0% | Cum Actual Labor Units
V-P1020 | پايان تست و صحه گذاري فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Validation |  | 2024-03-10 | 0% | Cum BL Project Labor Units
V-P1020 | پايان تست و صحه گذاري فيکسچر هاي مونتاژي | BG-01.Process Design.PF.Validation |  | 2024-03-10 | 0% | Cum Remaining Labor Units
Validation Product And Process |  |  | 27-Sep-2023 A | 2024-06-29 | 37.5% | Cum Actual Labor Units |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Validation Product And Process |  |  | 27-Sep-2023 A | 2024-06-29 | 37.5% | Cum BL Project Labor Units |  |  | 0.25 | 0.25 | 0.25 | 0.35 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
Validation Product And Process |  |  | 27-Sep-2023 A | 2024-06-29 | 37.5% | Cum Remaining Labor Units | 2023-12-01: 0.31; 2024-01-01: 0.63; 2024-02-01: 0.66; 2024-03-01: 0.66; 2024-04-01: 0.66; 2024-05-01: 0.66; 2024-06-01: 0.66
Production |  |  | 27-Sep-2023 A | 2024-06-29 | 37.5% | Cum Actual Labor Units |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Production |  |  | 27-Sep-2023 A | 2024-06-29 | 37.5% | Cum BL Project Labor Units |  |  | 0.25 | 0.25 | 0.25 | 0.35 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
Production |  |  | 27-Sep-2023 A | 2024-06-29 | 37.5% | Cum Remaining Labor Units | 2023-12-01: 0.31; 2024-01-01: 0.63; 2024-02-01: 0.66; 2024-03-01: 0.66; 2024-04-01: 0.66; 2024-05-01: 0.66; 2024-06-01: 0.66
Launch1003 | ERPثبت اطلاعات نرم افزار | BG-01.Phase 4.3 | 27-Sep-2023 A | 2023-12-19 | 100% | Cum Actual Labor Units |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Launch1003 | ERPثبت اطلاعات نرم افزار | BG-01.Phase 4.3 | 27-Sep-2023 A | 2023-12-19 | 100% | Cum BL Project Labor Units |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Launch1003 | ERPثبت اطلاعات نرم افزار | BG-01.Phase 4.3 | 27-Sep-2023 A | 2023-12-19 | 100% | Cum Remaining Labor Units | 2023-12-01: 0.24; 2024-01-01: 0.24; 2024-02-01: 0.24; 2024-03-01: 0.24; 2024-04-01: 0.24; 2024-05-01: 0.24; 2024-06-01: 0.24
Launch1002 | دريافت قطعات استاندارد و اتصالات | BG-01.Phase 4.3 | 2023-12-24 | 2024-02-04 | 0% | Cum Actual Labor Units
Launch1002 | دريافت قطعات استاندارد و اتصالات | BG-01.Phase 4.3 | 2023-12-24 | 2024-02-04 | 0% | Cum BL Project Labor Units | 2023-12-01: 0.1; 2024-01-01: 0.42; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
Launch1002 | دريافت قطعات استاندارد و اتصالات | BG-01.Phase 4.3 | 2023-12-24 | 2024-02-04 | 0% | Cum Remaining Labor Units | 2023-12-01: 0.07; 2024-01-01: 0.39; 2024-02-01: 0.42; 2024-03-01: 0.42; 2024-04-01: 0.42; 2024-05-01: 0.42; 2024-06-01: 0.42
Launch1001 | دريافت نمونه قطعات منفصله از پيمانکار قالب ساز | BG-01.Phase 4.3 |  | 2024-04-27 | 0% | Cum Actual Labor Units
Launch1001 | دريافت نمونه قطعات منفصله از پيمانکار قالب ساز | BG-01.Phase 4.3 |  | 2024-04-27 | 0% | Cum BL Project Labor Units
Launch1001 | دريافت نمونه قطعات منفصله از پيمانکار قالب ساز | BG-01.Phase 4.3 |  | 2024-04-27 | 0% | Cum Remaining Labor Units
Pre catalyst |  |  | 2024-04-27 | 2024-06-29 | 0% | Cum Actual Labor Units
Pre catalyst |  |  | 2024-04-27 | 2024-06-29 | 0% | Cum BL Project Labor Units
Pre catalyst |  |  | 2024-04-27 | 2024-06-29 | 0% | Cum Remaining Labor Units
pre sample1001 | توليد نمونه اوليه کاتاليست اول | BG-01.Phase 4.3.1 |  | 2024-04-27 | 0% | Cum Actual Labor Units
pre sample1001 | توليد نمونه اوليه کاتاليست اول | BG-01.Phase 4.3.1 |  | 2024-04-27 | 0% | Cum BL Project Labor Units
pre sample1001 | توليد نمونه اوليه کاتاليست اول | BG-01.Phase 4.3.1 |  | 2024-04-27 | 0% | Cum Remaining Labor Units
pre sample1002 | توليد يک روز خط کاتاليست اول | BG-01.Phase 4.3.1 |  | 2024-06-29 | 0% | Cum Actual Labor Units
pre sample1002 | توليد يک روز خط کاتاليست اول | BG-01.Phase 4.3.1 |  | 2024-06-29 | 0% | Cum BL Project Labor Units
pre sample1002 | توليد يک روز خط کاتاليست اول | BG-01.Phase 4.3.1 |  | 2024-06-29 | 0% | Cum Remaining Labor Units
Main Catalyst and Muffler |  |  | 2024-03-03 | 2024-06-08 | 0% | Cum Actual Labor Units
Main Catalyst and Muffler |  |  | 2024-03-03 | 2024-06-08 | 0% | Cum BL Project Labor Units
Main Catalyst and Muffler |  |  | 2024-03-03 | 2024-06-08 | 0% | Cum Remaining Labor Units
Main sample1001 | توليد نمونه اوليه کاتاليست دوم | BG-01.Phase 4.3.2 |  | 2024-03-03 | 0% | Cum Actual Labor Units
Main sample1001 | توليد نمونه اوليه کاتاليست دوم | BG-01.Phase 4.3.2 |  | 2024-03-03 | 0% | Cum BL Project Labor Units
Main sample1001 | توليد نمونه اوليه کاتاليست دوم | BG-01.Phase 4.3.2 |  | 2024-03-03 | 0% | Cum Remaining Labor Units
Main sample1002 | توليد يک روز خط کاتاليست دوم | BG-01.Phase 4.3.2 |  | 2024-06-08 | 0% | Cum Actual Labor Units
Main sample1002 | توليد يک روز خط کاتاليست دوم | BG-01.Phase 4.3.2 |  | 2024-06-08 | 0% | Cum BL Project Labor Units
Main sample1002 | توليد يک روز خط کاتاليست دوم | BG-01.Phase 4.3.2 |  | 2024-06-08 | 0% | Cum Remaining Labor Units
pipe Down |  |  | 2024-03-10 | 2024-06-29 | 0% | Cum Actual Labor Units
pipe Down |  |  | 2024-03-10 | 2024-06-29 | 0% | Cum BL Project Labor Units
pipe Down |  |  | 2024-03-10 | 2024-06-29 | 0% | Cum Remaining Labor Units
Flx sample1012 | Project Closure | BG-01.Phase 4.3.3 |  | 2024-06-29 | 0% | Cum Actual Labor Units
Flx sample1012 | Project Closure | BG-01.Phase 4.3.3 |  | 2024-06-29 | 0% | Cum BL Project Labor Units
Flx sample1012 | Project Closure | BG-01.Phase 4.3.3 |  | 2024-06-29 | 0% | Cum Remaining Labor Units
Flx sample1001 | توليد نمونه اوليه لوله فلکسيبل دار | BG-01.Phase 4.3.3 |  | 2024-03-10 | 0% | Cum Actual Labor Units
Flx sample1001 | توليد نمونه اوليه لوله فلکسيبل دار | BG-01.Phase 4.3.3 |  | 2024-03-10 | 0% | Cum BL Project Labor Units
Flx sample1001 | توليد نمونه اوليه لوله فلکسيبل دار | BG-01.Phase 4.3.3 |  | 2024-03-10 | 0% | Cum Remaining Labor Units
Flx sample1002 | توليد يک روز خط لوله فلکسيبل دار | BG-01.Phase 4.3.3 |  | 2024-06-08 | 0% | Cum Actual Labor Units
Flx sample1002 | توليد يک روز خط لوله فلکسيبل دار | BG-01.Phase 4.3.3 |  | 2024-06-08 | 0% | Cum BL Project Labor Units
Flx sample1002 | توليد يک روز خط لوله فلکسيبل دار | BG-01.Phase 4.3.3 |  | 2024-06-08 | 0% | Cum Remaining Labor Units