## data
total | Mr.Bahmani | Mr.Alizadeh | Ms.Abbaszadeh | Mr.Karimi | Mr.Rezazadeh | Mr.Haji | نام نفرات
10 | 3 | 2 | 2 | 1 | 1 | 4 | Activities
10 | 3 | 2 | 2 | 1 | 1 | 4 | In progress
0 | 0 | 0 | 0 | 0 | 0 | 0 | Delay
0 | 0 | 0 | 0 | 0 | 0 | 0 | Allowed delay
0 | 0 | 0 | 0 | 0 | 0 | 0 | On time
0 | 0 | 0 | 0 | 0 | 0 | 0 | Ahead of schedule | -6
10 |  |  | W4 | W3 | W2 | W1 | Weekly Efficiency
|  |  | 0% | 0% | 0% | 0%

## Fidelity Elite
Form Code:: | Project Weekly Report
Revision Date:
# Revision:00
| Project manager | Project Name | Meeting date | Client name |  | Project deadline
| Mr. Bahmani | Respect front and Rear Muffler | 1404/07/06 | Bahman Khodro |  | 1404/07/21
Total activities | Health |  | % Complete |  |  | % Variance
14 | Good |  | 0%
Status | Activity Name | Resource Name | Planned | Actual | %complete | Description
Inprogress | نقشه دو بعدی میانی و انتهایی | Mr.Bahmani | 1404/07/07 | N/A | 0%
Inprogress | OPC مجموعه میانی و انتهایی | Mr.Alizadeh | 14047/07/07 | N/A | 0%
Inprogress | مشخصات مهم محصول و FEMA | Mr.Karimi | 1404/07/14 | N/A | 0%
Inprogress | BOM | Mr.Bahmani | 1404/07/07 | N/A | 0%
Inprogress | سوابق کیفی برگشتی QIR | Mr.Haji | 1404/07/07 | N/A | 0%
Inprogress | طرح کنترل CP | Mr.Haji | 1404/07/21 | N/A | 0%
Inprogress | تهیه تجهیزات لیست تولیدی | Mr.Alizadeh | 1404/07/15 | N/A | 0%
Inprogress | لیست کنترل | Mr.Haji | 1404/07/15 | N/A | 0%
Inprogress | Layout | Ms.Abbaszadeh | 1404/07/15 | N/A | 0%
Inprogress | طرح بسته بندی | Mr.Akbari | 1404/07/15 | N/A | 0%
Inprogress | نتایج کنترل ابعادی Data Sheet | Mr.Bahmani | 1404/07/15 | N/A | 0%
Inprogress | آنالیز مواد | Mr.Haji | 1404/07/15 | N/A | 0%
Inprogress | Gantt Chart | Mr.Rezazadeh | 1404/07/15 | N/A | 0%
Inprogress | FPC,SOS | Ms.Abbaszadeh | 1404/07/15 | N/A | 0%
Inprogress | طرح دوباره کاری | Mr.Bahmani | 1404/07/15 | N/A | 0%